## Table 1. Performance Indicator
Table 1. Performance Indicators for Achievement of City Goals and Objectives
S/N | Performance Indicator | Unit of Measure | Baseline | EFY 2013 | EFY 2014 | EFY 2015 | EFY 2017
|  |  | 2012 EFY | (2020/2021) | (2021/22) | (2022/2023) | (2024/25)
|  |  | 2019/20 GC | Physical plan | Physical plan | Physical plan | GTP III Target
|  |  | (Actual) |  | (GTP II Target)
1 | Asphalt road | km | 0 | 0 | 0 | 0
2 | Gravel road with drainage | km | 3.939
3 | Compacted earthen road | km | - | 0 | 0 | 0
4 | Cobble Stone Road | M2 | 48307 | 65686 | 70708.9 | 81315.235 |  | 44898.8
5 | Pedestrian walk way | M2 | - |  | 0 | 0 |  | 14570 | 30328.8
6 | Urban Drainage | m | 983.2 | 3401 | 3741.43 | 4227.8159 |  | 877 | 31205.8
7 | Culvert construction | No | 3 | 6 | 5 | 6
8 | Bridge construction | No | - | 2 | 2 | 3
9 | Ditch cover | No | 640 | 0 | 0 | 0
10 | Street Light | No | - | 60 | 70 | 90
11 | Public toilet | No | - | 0 | 0 | 0
12 | Retaining wall | m3 | 1229 | 4825.2 | 5219.5 | 6354.7
13 | Urban Greenery protection fence | km | 0.95 | 0.1 | 0 | 0
14 | Urban Greenery Development | m2 | 24400 | 37000 | 16950 | 19153.5
15 | Asphalt Median and Greenary | km | 0.93 | 0.1 | 0 | 0
16 | Low cost house | No | 8 | 16 | 19 | 23
17 | Buildings | No | 1 | 4 | 5 | 7
18 | Fence work | m
19 | MSE Shade | No | 30 | 0 | 0 | 0

## Table 2. City Financial Perform
Table 2. Key City Financial Performance & Sustainability Indicators
S/N | Performance Indicator | Unit of Measure | Baseline | EFY 2013 | EFY 2014 | EFY 2015 | EFY 2017
|  |  | 2012 EFY | (2020/21) | (2021/22) | (2022/23) | (2024/25)
|  |  | 2019/20 GC (Actual) | Budget | Budget | Target | GTP III Target
(GTP II Target)
1 | CIP Expenditures | Birr | 106865745.09 | 201800326.8281 | 207257794.7804 | 240648204.7277
2 | Municipal revenues (excluding land lease) | Birr | 56524149.29 | 76279153.6186 | 82711326.1396 | 94949734.0365
3 | Land lease | Birr | 8666083.59 | 6183802.313 | 6802182.5443 | 7482400.7987
4 | Municipal revenues (including land lease) | Birr | 65190232.88 | 82462955.9316 | 89513508.6839 | 102432134.8352 |  | 56524149.29 | 76279153.6186
5 | Land lease as a percentage of municipal revenues (3 divided by 4) | % | 13.29% | 7.499% | 7.599% | 7.305% |  |  | 82711326.1396
6 | State Revenues | Birr | 226370251 | 261660406 | 287826446.6 | 345391735.92 |  |  | 94949734.0365
7 | Operation and Maintenance (O & M) (total of a & b below) | Birr | 16146751.85 | 20185143.57 | 22203657.93 | 24424023.72
(a) | O & M for normal maintenance activities (Conditions 1 & 2)[1] | Birr | 2000000 | 2135150 | 2135150 | 2135150
(b) | O & M to cover maintenance deficit activities (Conditions 3, 4 and minor assets in 5) | Birr | 14146751.85 | 18049993.57 | 20068507.93 | 22288873.72
8 | O & M expenditures as a percentage of municipal revenues (excluding land lease) (7 divided by 2) | % | 28.57% | 26.46% | 26.84% | 25.72%
9 | Total maintenance deficit (TMD) (from AMP) | Birr | 47429742.11 | 37493697.42 | 41243067.162 | 45367373.8782
10 | Total Asset Replacement Cost (TARC)[2] | Birr | 2040130415.05 | 2101139520 | 2311253472 | 2542378819.2
11 | TMD Coverage Rate {(7) divided by 9} | % | 34.04% | 53.84% | 53.84% | 53.84%
(Maintenance Budget as a percentage of TMD)
12 | Maintenance Budget as a percentage of TARC | % | 0.7915% | 0.9607% | 0.9607% | 0.9607%
13 | Maintenance Budget as a percentage of CIP | % | 15.11% | 10% | 10.71% | 10.15%
14 | Maintenance Budget as a percentage of municipal revenues | % | 24.77% | 24.48% | 24.8% | 23.84%
15 | Operating Surplus (Deficit) | Birr | 26036241.23 | 6640648.4916 | 1162230.0039 | 9129595.9552
16 | Operating Surplus (Deficit) as a percentage of municipal revenues excl. land lease (11 divided by 2) | % | 46.06% | 8.706% | 1.405% | 9.615%
[1]For most cities this separation will only be reflected as from EFY 2009 budget which is the first year that the revised AMP manual is being used. It is now a requirement as per the revised AMP manual that all normal maintenance activities should be fully covered (provided for) in the annual budget.
[2]This can only be entered for two years i.e. CIP 1st year and current year (baseline) for which AMP is available

## Table 3. 1st Round Public Consu
Table 3. Participants & Community Groups in 1st Round -Consultations & Identification of Projects at Kebele Level
S/N |  | № of Participants |  |  | %
| Community Group | M | F | T | Group total as % of Total | Female share %
1 | Religion leaders | 5 | 2 | 7 | 2.482% | 28.57%
2 | Local elders | 11 | 6 | 17 | 6.028% | 35.29%
3 | MSE members | 9 | 25 | 34 | 12.06% | 73.53% | 32 | 1 | 19 | 33
4 | Edir leaders | 5 | 3 | 8 | 2.837% | 37.5% | 14 | 3 | 9 | 17
5 | Civil servants | 12 | 22 | 34 | 12.06% | 64.71% | 40 | 13 | 27 | 53
6 | City council members | 12 | 13 | 25 | 8.865% | 52% | 20 | 8 | 30 | 28
7 | House wives | 0 | 35 | 35 | 12.41% | 100% | 6 | 4 | 6 | 10
8 | Professionals | 15 | 18 | 33 | 11.7% | 54.55% | 25 | 11 | 14 | 36
9 | Traders | 15 | 19 | 34 | 12.06% | 55.88% | 137 | 40 | 105 | 177
10 | City Officials | 5 | 4 | 9 | 3.191% | 44.44%
11 | Students | 12 | 25 | 37 | 13.12% | 67.57%
12 | NGO members | 3 | 3 | 6 | 2.128% | 50%
13 | Disabled group | 1 | 2 | 3 | 1.064% | 66.67%
0
Total № of Participants |  | 105 | 177 | 282 | 100% | 62.77%

## Table 4. 2nd Round Public Consu
Table 4. Projects Identified by the Community at 2ndRound of Consultations at City Level
S/N |  | № of Participants |  |  | %
| Community Group | M | F | T | Group total as % of Total | Female share %
1 | Religion leaders |  |  |  | 0%
2 | Local elders |  |  |  | 0%
3 | MSE members |  |  |  | 0%
4 | Edir leaders |  |  |  | 0%
5 | Civil servants |  |  |  | 0%
6 | City council members |  |  |  | 0%
7 | House wives |  |  |  | 0%
8 | Professionals | 11 | 4 | 15 | 53.57% | 26.67%
9 | Traders |  |  |  | 0%
10 | City Officials | 10 | 3 | 13 | 46.43% | 23.08%
11 | Students |  |  |  | 0%
12 | NGO members |  |  |  | 0%
13 | Disabled group |  |  |  | 0%
0
Total № of Participants |  | 21 | 7 | 28 | 100% | 25%

## Table 5. Prioritized Projects
Table 5. Participants & Community Groups in 2nd Round -Prioritization and Ranking of Projects at City Level
No | Name of Project | Name of Kebele | Community Group/City office from which proposed
1 | Roads
1.1 | Cobblestone Road
1.1.1 | ASPHALT TO GETAHUN AYELE & GETAHUN LEMA TO GABALE TSARA | LIMAT | City officials & Professionals |  | City officials
1.1.2 | TAKELE TESEMA TO ELIYAS GAGA | LIMAT | City officials & Professionals |  | Professionals
1.1.3 | DESALEGN DATA TO MEKANEYESUS GUEST HOUSE | LIMAT | City officials & Professionals
1.1.4 | ZERIHUN ZUMA TO TESFAYE DURE | LIMAT | City officials & Professionals
1.1.5 | FROM CHICHE CHIBIRE TO TADELECH SHITAYE & LISANEWORK TO OLD BRIDGE | GURBA | City officials & Professionals
1.1.6 | FROM AREGAWIYAN TO GULCHA DOKILE & YAPA YAYA TO ZENEBE ZIDA | GURBA | City officials & Professionals
1.1.7 | HAILEMICHAEL HALALA TO BELAYNESH MERGIYA | NECH SAR | City officials & Professionals
1.1.8 | ASHEBIR ASFA THROUGH ASFAW DAGNIE TO G/MEDIHIN ADINEW | NECH SAR | City officials & Professionals | [7 empty] | 0.41962
1.1.9 | ABEBE GEZAHAGN THROUGH MENGISTU MARKA TO PETROS | NECH SAR | City officials & Professionals | [7 empty] | 1.4196
1.1.10 | SOLOMON CHODA TO BITANE MENZA | NECH SAR | City officials & Professionals | [7 empty] | 1.8392
1.1.11 | DAMENE TO SENODOS WOFCHO BET | NECH SAR | City officials & Professionals
1.1.12 | MATEYOS LOHA TO KES KETEMA, MENZA TO AWUDE AHMED & CHAIN ACADAMY TO ASNAKECH LENCHA | NECH SAR | City officials & Professionals | [6 empty] | 57194318
1.1.13 | HUSEN YIMER TO ASKALECH GIZACHEW, LIYU MEAZA TO NATINAEL, TAGESE CHAFO TO MEDIHANIT METASEBIYA & DESALEGN LAFAMO TO MEKONNEN | SHECHA | City officials & Professionals | [6 empty] | 24000000
1.1.14 | GETACHEW SEMERE TO ASPHALT | SHECHA | City officials & Professionals | [6 empty] | 24000000
1.1.15 | BOMBOLO AGIDEW TO ASPHALT | SHECHA | City officials & Professionals | [6 empty] | 105194318
1.1.16 | MOGES W/AMANUEL TO AEMIRO ALTO & MINALU BULGO TO TULO BOYZO | SHECHA | City officials & Professionals | [6 empty] | 153194318
1.1.17 | CHALACHEW TAMIRU TO TESFAYE HAILE & BEDILU TO TIRUYE | SHECHA | City officials & Professionals | [7 empty] | 0.41962
1.1.18 | WANSO WASHA TO THOMAS WASHE & JINKA BER TO MULUWONGEL | SHECHA | City officials & Professionals | [7 empty] | 0.83924
1.1.19 | TSIGEREDA KEBEDE TO MENGISTU WORKU & D/R TESFAYE TO TADELE YILMA | SHECHA | City officials & Professionals | [7 empty] | 1.8392
1.1.20 | LABIYAJO THROUGH TSEGAYE BEKELE TO MOLA HABTE | BERE EDGET BER | City officials & Professionals
1.1.21 | MOLA HABTE THROUGH ASCHENAKI MAMO TO NEW ASPHALT | BERE EDGET BER | City officials & Professionals
1.1.22 | SHEWAYE MINDAYE THROUGH NEW CULVERT TO WONDWOSEN WUBAYEHU | BERE EDGET BER | City officials & Professionals
1.1.23 | TESFAYE KOIRA THROUGH ALMAZ ALEMAYEHU TO GUDELA KUSIYA | BERE EDGET BER | City officials & Professionals
1.1.24 | KASAHUN GEZAHAGN TO MINJA, MINJA TO WONBERA, WONBERA TO DEBEBE LOFA | SIKELA | City officials & Professionals
1.1.25 | KASAHUN GEZAHAGN TO MENGISTU MEYA & ETENESH BEKELE TO DEREJE ALEMU | SIKELA | City officials & Professionals
1.1.26 | ADDIS ALEMAYEHU WOFCHO BET TO DEBEBE MAMACHA | SIKELA | City officials & Professionals
1.1.27 | ABUGIYA SHILE TO YIFTUSIRA MOLA | SIKELA | City officials & Professionals
1.1.28 | WADA DERE TO DEBEBE BIRHANE | SIKELA | City officials & Professionals
1.1.29 | RAHEL KULINO TO W/RO BIRHANE KASA | SIKELA | City officials & Professionals
1.1.30 | EJIGAYEHU DEBREWORK TO MESERET ADANE | SIKELA | City officials & Professionals
1.2 | Street Light
1.2.1 | From Konso sefer adebabay to Admasu house and from Fish Corporation to Zone Urban Dev't Office | SHECHA & NECH SAR | City officials & Professionals
1.3 | Bridges,Fords & Culvert construction
1.3.1 | HIBRET LELIMAT SCHOOL CULVERT | NECH SAR | City officials & Professionals
1.3.2 | SINODOS CULVERT | NECH SAR | City officials & Professionals
1.3.3 | CATHOLIC MISSION CULVERT | SHECHA | City officials & Professionals
1.3.4 | GURBA CULVERT | GURBA | City officials & Professionals
1.3.5 | TSEGAYE H/GIORGIS BRIDGE/GEBRIEL MESHAGERIYA | NECH SAR | City officials & Professionals
1.4 | Electric Line Expansion /Transformer /
1.4.1 | SENODOS SEFER & AT THE BACK OF TEXTILE FACTORY | LIMAT & NECH SAR | City officials & Professionals
1.5 | WATER SUPPLY
1.5.1 | WATER SUPPLY PROJECT AT THE BACK OF TEXTILE FACTORY | LIMAT | City officials & Professionals
1.6 | Drainage construction
1.6.1 | TESFAYE TEFERA TO BEZABIH WADA & AKIRSO KORA TO BONO | LIMAT | City officials & Professionals
1.6.2 | BRIDGE TO TESFAYE WORKINEH | LIMAT | City officials & Professionals
1.6.3 | GEDA GAZE TO MATEYOS ASHA | GURBA | City officials & Professionals
1.6.4 | GIRMA SANA TO BEKELE TADESE | NECH SAR | City officials & Professionals
1.6.5 | DAWIT DORKE THROUGH SAMSON TO GEZMO TINKU | NECH SAR | City officials & Professionals
1.6.6 | BIRKABY THROUGH ABERA MOTA TO ENDALE H/MESKEL | NECH SAR | City officials & Professionals
1.6.7 | KALEB KANKO TO DIDO ABUTE | SHECHA | City officials & Professionals
1.6.8 | YISIHAK MENA TO WONDIYIFRAW | SHECHA | City officials & Professionals
1.6.9 | CHAMO CAMPUS ASPHALT TO BEHAILU ABOTA | SHECHA | City officials & Professionals
1.6.10 | AZENEH TEKA TO GORGE & BIZUNEH BUSA TO BISAF LEMA | BERE EDGET BER | City officials & Professionals
1.6.11 | KULIFO GREENERY SITE DITCH | SIKELA | City officials & Professionals
1.6.12 | S/R YIRGEDU MENGESHA TO SIYERE MEKURIYA | BERE EDGET BER | City officials & Professionals
1.7 | Greenery development
1.7.1 | Public Park at the side of Kulufo river phase-IIII | SIKELA | City officials & Professionals
1.8 | Retaining wall construction
1.8.1 | Retaining wall at the side of Kulufo river phase-III | SIKELA | City officials & Professionals
|  |  |  | #REF! |  |  |  |  | #REF!
| 2755507.75 |  |  |  | 882100.33 |  | #REF!
| 69610194.25 |  |  |  | 3117899.33 |  | #REF! |  | 612642.26
| 72365702 |  |  |  | 3999999.66 |  | #REF! |  | #REF!
132365702
|  |  |  | 72365702 |  | 3000000
|  |  |  | 30000000 |  | 3000000
30000000
|  |  |  | 132365702 | 30000000
[5 empty] | 72365702 |  | 1.8291 | 0.41456
[5 empty] | 0.41456 |  |  | 0.82912
1.8291

## Table 6. Summary of Multi year
S/N | Sources of Funding | Amount of funding in Birr
|  | 2013 EFY | 2014 EFY | 2015 EFY | Total for 3 years
1 | IDA Performance Grant | 72365702 | 94217124.38 | 100999400.25 | 267582226.63
2 | Regional Contribution (41.46%) | 30000000 | 40000000 | 50000000 | 120000000
3 | City Contribution (41.46%) | 30000000 | 40000000 | 50000000 | 120000000
4 | Subtotal: UIIDP (1-3) | 132365702 | 174217124.38 | 200999400.25 | 507582226.63
| Carry over fund from previous year /UIIDP/ | 41900732.83 | 0 | 0 | 41900732.83
6 | Total UIIDP(4+5) | 174266434.83 | 174217124.38 | 200999400.25 | 549482959.46
7 | Additional Regional Fund for CIP | - | - | -
8 | Additional Municipal Fund from Surplus | 13448891.9981 | 16138670.4004 | 19366404.4777 | 48953966.8763
9 | Additional State Fund from Surplus | 14085000 | 16902000 | 20282400 | 51269400
10 | Community Contributions | - | - | -
11 | Other Capital Receipts | - | - | -
12 | Total Additional City & Regional Fund (7-11) | 27533891.9981 | 33040670.4004 | 39648804.4777 | 100223366.8763
13 | Other donor fund except UIIDP
14 | Total fund available for the CIP (6+13+14) | 201800326.8281 | 207257794.7804 | 240648204.7277 | 649706326.3363
174266434.83
41900732.83
132365702
2817000
|  | 105194318 | 123654115.516 | 142202232.8434
|  |  | 0.17548 | 0.15
[6 empty] | 132365702 | 60000000 | 72365702
|  | 7299999.9957 | 15117834.6243 | 22564573.6151 |  | 174217124.38 | 80000000 | 94217124.38
|  |  | 1.0709 | 0.49258 |  | 200999400.25 | 100000000 | 100999400.25
|  | 12699999.9957 | 20044531.7678 | 26919972.4736
|  |  | 0.57831 | 0.34301

## Table 7. Multi year forecast
| CIP Financial data | Actual | plan
Acc/ No. | Revenue item | 2012 | 2013 | 2014 | 2015 | 2013 | 2014 | 2015
A | Municipal Revenue Item | baseline | plan | plan | plan | Rate | Rate | rate
1701-1719 | Tax Revenues from Municipal Services | 7680823.87 | 10623174.79 | 11792523.385 | 13091650.5734 | 0.38308 | 0.11008 | 0.11017
1721-1729 | Municipal rent revenues | 37988738.23 | 60016200.74 | 63433109.8175 | 71781773.5016 | 0.57984 | 0.056933 | 0.13161
1731 | 10% of Lease income | 8666083.59 | 6183802.313 | 6802182.5443 | 7482400.7987 | -0.28644 | 0.1 | 0.1
1740-1749 | Municipal Service Charges | 3120185.12 | 1380689.3244 | 1762503.1157 | 2305220.4063 | -0.5575 | 0.27654 | 0.30792
1750-1789 | Property and Services Sales of Goods and Services | 7734402.07 | 4259088.7642 | 5723189.8214 | 7771089.5552 | -0.44933 | 0.34376 | 0.35782
4+5+6+7+8 | Total Municipal Own Operating Revenue (sum of above) | 65190232.88 | 82462955.9316 | 89513508.6839 | 102432134.8352 | 0.26496 | 0.0855 | 0.14432
Other Municipal Operating Revenues
1604 | Road Fund | 1896426.21 | 2135150 | 2348665 | 2583531.5 | 0.12588 | 0.1 | 0.1
| City state revenue cover for municipal recurrent expenditure | Actual 2012: 12187734.48; plan 2013: -1; plan 2014: #DIV/0!; plan 2015: #DIV/0!
11+12+13 | Sum of the Other Municipal Operating Revenues | 14084160.69 | 2135150 | 2348665 | 2583531.5 | -0.8484 | #DIV/0! | #DIV/0!
9+14 | Total Municipal Operating Revenue | 79274393.57 | 84598105.9316 | 91862173.6839 | 105015666.3352 | 0.067156 | #DIV/0! | #DIV/0!
Municipal Operating /Recurrent/Expenditure
6100 | Municipal Salary and Emblements | 22002981.08 | 18667085 | 25413443.15 | 26684115.3 | 0.1 | 0.05 | 0.05
6200 | Goods and services | 13088419.41 | 12804570.31 | 15836987.49 | 17420686.23 | 0.1 | 0.1 | 0.1
6245 | Routine Repair and maintenance of infrastructure by own budget | 14011601.85 | 18049993.57 | 19854992.93 | 21840492.22 | 0.1 | 0.1 | 0.1
| Routine Repair and maintenance of infrastructure by road fund | 2135150 | 2135150 | 2348665 | 2583531.5 | 0.9 | 0.9 | 0.9
16+17 | Total Routine Repair and maintenance of infrastructure | 16146751.85 | 20185143.57 | 22203657.93 | 24424023.72 | 1 | 1 | 1
6300 | Purchasing of Fixed Assets | 2000000 | 26300658.56 | 27245855.11 | 27357245.13 | 0.2 | 0.08 | 0.14
17+18+21+22 | Total Recurrent Expenditure | 53238152.34 | 77957457.44 | 90699943.68 | 95886070.38 | 1.4 | 1.23 | 1.29
15 minus 23 | Operating surplus | 26036241.23 | 6640648.4916 | 1162230.0039 | 9129595.9552 | -1.3328 | #DIV/0! | #DIV/0!
22 | Operating Surplus | 26036241.23 | 6640648.4916 | 1162230.0039 | 9129595.9552 | -1.3328 | #DIV/0! | #DIV/0!
1731 | 90% of lease income | 77994752.28 | 55654220.817 | 61219642.8987 | 67341607.1886 | -0.05 | 0.1 | 0.1
1733 | Community contribution | Actual 2012: 500000; plan 2013: 0; plan 2014: 0; plan 2015: 0
1791-1799 | Other capital receipts | 98314.91 | 10999.2495 | 11292.7779 | 11595.8539 | 0.45 | 0.1 | 0.05
26+27+28+29 | Total Municipal Capital Revenue | 104629308.42 | 62305868.5581 | 62393165.6804 | 76482798.9977 | -0.93284 | #DIV/0! | #DIV/0!
30 | UIIDP performance Grants for EFY 2012 | 57194318 | 72365702 | 94217124.38 | 100999400.25 | 0.27 | 0.24 | 0.24
31 | Zone Contribution to Performance grant /41.96%/ | 24000000 | 30000000 | 40000000 | 50000000 | 0.27 | 0.24 | 0.24
32 | City Contribution/41.96%/ | 24000000 | 30000000 | 40000000 | 50000000 | 0.27 | 0.24 | 0.24
33 | unreserved carry over from previous year /UIIDP/ | Actual 2012: 43573200.54; plan 2013: 41900732.83; plan 2014: 0; plan 2015: 0
| Capacity building{30+31+32}* | 4000 | 5040162.02 | 5947388.82 | 6958444.92 | 9 | 0.05 | 0.05
31+32+33+34 | Total IDA related capita revenues | 148767518.54 | 174266434.83 | 174217124.38 | 200999400.25 | 0.81 | 0.72 | 0.72
29 minus 32 | Municipal Capital Revenue for non IDA related CIP Projects net of city contribution | 80629308.42 | 32305868.5581 | 22393165.6804 | 26482798.9977 | -1.2028 | #DIV/0! | #DIV/0!
6400 | Compensation to be paid from 32 | 24830462.06 | 18856976.56 | 6254495.28 | 7116394.52 | -0.75 | 0.1 | 0.1
36-37 | Municipal Net Capital Revenue for non IDA related CIP Projects | 55798846.36 | 13448891.9981 | 16138670.4004 | 19366404.4777 | 1.47 | -0.1 | -0.09
B | State revenues and expenditures
35 | State Tax and Service charge Revenue | 174466948 | 206700000 | 212645136.2 | 266733760 | 0.31 | 0.09 | 0.35
36 | Regional Subsidy to City budget | 51601248 | 54960406 | 75181310.4 | 78657975.92 | 0.39 | 0.05 | 0.05
37 | Other revenue/Aid/ | Actual 2012: 302055; plan 2013: 0; plan 2014: 0
35+36+37 | Total State Revenue | 226370251 | 261660406 | 287826446.6 | 345391735.92 | 0.32 | 0.08 | 0.28
State Expenditure/function
| State Recurrent Expenditure | 209282516.52 | 247575406 | 270924446.6 | 325109335.92 | 0.18 | 0.14 | 0.3
43-45 | State Capital Expenditure inculding state compensation | 4900000 | 14085000 | 16902000 | 20282400 | 11.52 | -0.23 | -0.64
| construction and civil works | 3200000 | 14085000 | 16902000 | 20282400 | 11.52 | -0.23 | 0.36
| Procurement of light vehicles and heavy duty machineries | 950000 | 0 | 0 | 0 |  |  | -1
| compensation from RE{46} | Actual 2012: 750000; plan 2013: 0; plan 2014: 0; plan 2015: 0
| Total Capital | 4150000 | 14085000 | 16902000 | 20282400 | 11.52 | -0.23 | -0.64
40+41 | State Total Expenditure | 214182516.52 | 261660406 | 287826446.6 | 345391735.92 | 11.7 | -0.09 | -7.54
44 minus 42 | Surplus from state revenue for Municipal Services /Subsidy/ | 12187734.48 | 0 | 0 | 0 | -11.38 | 0.17 | 7.82
| State revenue subsidy to municipality recurrent expenditure | 12187734.48 | 0 | 0 | 0 | -0.18 | - | -
| From state surplus revenue for non IDA related CIP Projects | 4900000 | 14085000 | 16902000 | 20282400 | 11.52 | -0.2 | 0.23
35+38+50 | Total CIP Project | 208716364.9 | 201800326.8281 | 207257794.7804 | 240648204.7277 | 13.8 | 0.39 | -0.01
C
S
287826446.6
75181310.4
212645136.2

## Table 8. Past 3 year expenditur
No. | Expenditure Item | EFY 2010 | EFY 2011 | EFY 2012 | Three Year Total | % of total
Pillar 6. Integrated Urban Infrastructure
A | Movement Network[1]
1 | Roads
1.1 | Cobblestone Road | 42332689.8 | 28457709.96 | 54287499.57 | 125077899.33 | 64.26% | 45713758.34 | 18435170.38 | 27278587.96 | 31544471.56
1.2 | Asphalt Road | 23320019.02 | 0 |  | 23320019.02 | 11.98% |  |  | 1179122
1.3 | Gravel Road | 665160 | 0 | 12373738.4 | 13038898.4 | 6.699% | 59938439.31 |  | 28457709.96
1.4 | Other types of roads(Earthen) | 0 | 0 |  | 0 | 0%
2 | Culvert | 990104 | 1535690.11 | 2881001.16 | 5406795.27 | 2.778% | 1440317.23
3 | Ditchcover | 3137200 | 3234522.2 | 2012101.04 | 8383823.24 | 4.307%
4 | Cycle Ways | 0 | 0 |  | 0 | 0%
5 | Gamo Round about construction |  | 8613422.3 |  | 8613422.3 | 4.425%
6 | Foot paths: pavements | 0 | 0 |  | 0 | 0%
7 | Street lighting | 6934281.5 | 3874230.32 |  | 10808511.82 | 5.553%
| Sub-total Movement Network | 77379454.32 | 45715574.89 | 71554340.17 | 194649369.38 | 100%
B | Water Supply Network |  |  |  | 0
1 | Water resources |  |  |  | 0
2 | Water supply | 1038150 | 1000000 | 0 | 2038150 | 100%
| Sub-total Water Supply Network | 1038150 | 1000000 | 0 | 2038150 | 100%
C | Economic & Social Services |  |  |  | 0
1 | Markets |  |  |  | 0 |  | 5874125.78
2 | Abattoirs |  |  |  | 0
3 | MSE Facilities/Industrial Zones | 3399262.44 | 7155372.01 | 3268030.81 | 13822665.26 | 100% | 7203925.82 | 3268030.81 | 3935895.01 | 7155372.01
4 | Health Centres & Clinics |  |  |  | 0
5 | Schools |  |  |  | 0
| Sub-total Economic & Social Services | 3399262.44 | 7155372.01 | 3268030.81 | 13822665.26 | 100%
E | Other |  |  |  | 0
1 | Electricity reticulation | 2254502.33 | 0 | 6600000 | 8854502.33 | 100%
| Sub-total Other | 2254502.33 | 0 | 6600000 | 8854502.33 | 100%
Total Pillar 6. Integrated Urban Infrastructure total |  | 84071369.09 | 53870946.9 | 81422370.98 | 219364686.97 | 100%
Pillar 7: Environmental, Green Services & Recreation |  |  |  |  | 0
D | Environmental Services |  |  |  | 0
1 | Drainage | 11967039.54 | 6628723.77 | 5057949.96 | 23653713.27 | 54.7% | 5155982.45 | 5486683.85
2 | Sanitation | 0 |  |  | 0 | 0% | 3979603.75
3 | Solid Waste |  |  |  | 0 | 0% | 9135586.2
4 | Liquid Waste |  |  |  | 0 | 0%
5 | Urban Greenery | 5628482.45 | 1789421.51 | 12172688.5 | 19590592.46 | 45.3% | 6173499.53
6 | Parks and Play Areas | 0 |  |  | 0 | 0% | 18346188.03
7 | Rivers, wetlands, natural areas , watershed management |  |  |  | 0 | 0% | 12172688.5
| Subtotal Environmental Services | 17595521.99 | 8418145.28 | 17230638.46 | 43244305.73 | 100%
E | Other |  |  |  | 0
1 |  |  |  |  | 0
| Subtotal Other |  |  |  | 0
Total Pillar 7: Environmental, Green Services & Recreation |  | 17595521.99 | 8418145.28 | 17230638.46 | 43244305.73 | 100%
Pillar 8: Resilient, Inclusive and Safer Cities |  |  |  |  | 0
C | Economic & Social Services |  | 0 |  | 0 | 0%
1 | Youth/Women Centres & Projects |  |  |  | 0
2 | Fire and Ambulances Services |  |  |  | 0
| Subtotal Economic & Social Services |  | 0 |  | 0 | 0%
D | Environmental Services |  |  |  | 0
1 | Flood Protection (retaining walls etc) | 5890561.66 | 2591929.04 | 4212735.65 | 12695226.35 | 100% | 11189679.97
| Subtotal Environmental Services | 5890561.66 | 2591929.04 | 4212735.65 | 12695226.35 | 100% | 15402415.62
E | Other |  |  |  | 0 |  | 4212735.65
| Buildings, fence and goods |  |  |  | 0
1 | Buildings | 0 | 0 |  | 0 | 0%
2 | Fence construction | 4000000 | 1208526 |  | 5208526 | 29.09%
3 | Abattoir truck | 0 |  |  | 0 | 0%
4 | Skip loader | 0 |  |  | 0 | 0%
| Subtotal Other | 4000000 | 1208526 |  | 5208526 | 29.09%
Total Pillar 8: Resilient, Inclusive and Safer Cities |  | 9890561.66 | 3800455.04 | 4212735.65 | 17903752.35 | 100% | 4038512.4
Municipal Administration Buildings and Other Projects which cannot be put in Pillars |  |  |  |  | 0
Consultancy Services for designs and contract management/supervision |  |  |  |  | 0
0
Total Past Capital Investments |  | 111557452.74 | 66089547.22 | 102865745.09 | 280512745.05 | 100%
0
Total Past Capacity Building |  | 1247132.21 | 4038512.4 | 4000000 | 9285644.61 | 100%
Total past 3-year expenditure |  | 112804584.95 | 70128059.62 | 106865745.09 | 289798389.66 | 0
[1] CIP Projects are now grouped under the ECSPG Pillars and also under the following four strategic areas as defined by the revised Asset Management Plan Manual: A. Movement Network; B. Water Supply Network; C. Economic and Social Services; D. Environmental Services. Any infrastructure category which does not fit into these four areas will be put in E. Other.

## Table 9. Three-year Summary
No | Strategic Area | EFY 2013 | EFY 2014 | EFY 2015 | Total | % of total
A | Movement Network | 120019208.71 | 133075035.0842 | 157455462.8845 | 410549706.6787 | 63.19%
B | Water Supply Network | 1000000 | 0 | 0 | 1000000
C | Economic & Social Services | 5000000 | 5900000 | 6903000 | 17803000 | 2.74%
D | Environmental Services | 50974610.34 | 38680402.677 | 41059764.0221 | 130714777.0391 | 20.12%
E | Other(Capacity building) | 5040160.02 | 5947388.8236 | 6958444.9236 | 17945993.7672 | 2.762%
F | Municipal Administration Buildings and Other Projects which cannot be put in Pillars | 19766347.76 | 23654968.1968 | 28271532.9023 | 71692848.8591 | 11.03%
| Total | 201800326.83 | 207257794.7816 | 240648204.7325 | 649706326.3441 | 100%
|  | 161467518.5357 | 144441950.1403 | 170720306.4585 | 476629775.1345
|  |  | 62815844.6413 | 69927898.274
|  | 161467518.5357 | 143698647.2838 | 169122205.317
|  | -40332808.2943 | -63559147.4978 | -71525999.4155
| IBEX Total | 174266434.83 | 174217124.3816 | 200999400.2525 | 549482959.4641 | 1 | 1
| NON UIIDP | 27533892 | 33040670.4 | 39648804.48 | 100223366.88
|  | 201800326.83 | 207257794.7816 | 240648204.7325 | 649706326.3441

## 10. Three-year Rolling CIP
No | ECSPG Pillar & Project Name | Unit | Priority | EFY 2013 |  | EFY 2014 |  | EFY 2015 |  | Three Year Total
|  |  |  | Qty | Birr | Qty | Birr | Qty | Birr | Qty | Birr
Pillar 6. Integrated Urban Infrastructure
A | Movement Network[1]
1 | Roads
1.1 | Cobblestone Road
1.1.1 | New | m2 | 1 | 61486 | 77970295.16 | 70708.9 | 92004948.2888 | 81315.235 | 109369014.2979 | 213510.135 | 279344257.7467
1.1.2 | Rolled | m2 | 1 | 4200 | 5650939.74 |  | 0 |  | 0 | 4200 | 5650939.74
1.2 | Asphalt Road | [8 empty] | 0 | 0
1.2.1 | New | km |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2.2 | Rolled | km | [7 empty] | 0 | 0
1.3 | Gravel Road | [8 empty] | 0 | 0
1.3.1 | New | m | [7 empty] | 0 | 0
1.3.2 | Rolled |  |  | 0 | 0 |  |  |  |  | 0 | 0
1.4 | Other types of roads | [8 empty] | 0 | 0
1.4.1 | New | [8 empty] | 0 | 0
1.4.2 | Rolled | [8 empty] | 0 | 0
2 | Cycle Ways, Cycle Paths | [8 empty] | 0 | 0
2.1 | New | [8 empty] | 0 | 0
2.2 | Rolled | [8 empty] | 0 | 0
3 | Foot paths, | [8 empty] | 0 | 0
3.1 | pavements, | [8 empty] | 0 | 0
3.2 | Round about(Rolled) | No |  | 0.8 | 11000000 | 1 | 13200000 | 1 | 15840000 | 1 | 40040000
3.3 | pedestrian |  |  | 1 |  |  | 0 | 0 | 0 | 0 | 0
3.4 | walkways, | [8 empty] | 0 | 0
4 | Road Structure | [8 empty] | 0 | 0
4.1 | Bridge(New) | No |  | 1 | 5065074.31 | 2 | 5976787.6858 | 3 | 6992841.5924 | 6 | 18034703.5882
4.2 | Bridge(Rolled) | No |  | 1 | 7998959.38 |  | 9038824.0994 | 0 | 10213871.2323 | 1 | 27251654.7117
4.3 | Culvert(New) | No |  | 4 | 4319915.63 | 5 | 5097500.4434 | 6 | 5964075.5188 | 15 | 15381491.5922
4.4 | Culvert(Rolled) | No |  | 2 | 1440317.23 |  |  |  |  | 2 | 1440317.23
5 | Street lighting | [8 empty] | 0 | 0
5.1 | New | No |  | 1 | 6573707.26 | 2 | 7756974.5668 | 3 | 9075660.2432 | 6 | 23406342.07
5.2 | Rolled | No | [7 empty] | 0 | 0
6 | Bus terminals, , | [8 empty] | 0 | 0
6.1 | bus stops | [8 empty] | 0 | 0
6.2 | bus stations | [8 empty] | 0 | 0
7 | Road furniture, , | [8 empty] | 0 | 0
7.1 | road signs | [8 empty] | 0 | 0
7.2 | traffic lights | [8 empty] | 0 | 0
| Sub-total Movement Network |  |  |  | 120019208.71 | 0 | 133075035.0842 | 0 | 157455462.8845 | 0 | 410549706.6787
B | Water Supply Network | [8 empty] | 0 | 0
1 | Water resources | [8 empty] | 0 | 0
1.1 | Name of project | [8 empty] | 0 | 0
1.2 | Etc | [8 empty] | 0 | 0
2 | Water supply |  |  | 1 | [5 empty] | 1 | 0
2.1 | Name of project |  |  | 1 | 1000000 |  |  |  |  | 1 | 1000000
2.2 | Etc | [8 empty] | 0 | 0
| Sub-total Water Supply Network |  |  |  | 1000000 | 0 | 0 | 0 | 0 | 1 | 1000000
C | Economic & Social Services | [8 empty] | 0 | 0
1 | Markets | [8 empty] | 0 | 0
1.1 | Name of project | [8 empty] | 0 | 0
1.2 | Etc | [8 empty] | 0 | 0
2 | Abattoir truck |  |  | 1 | 5000000 | 2 | 5900000 | 3 | 6903000 | 6 | 17803000
2.1 | Name of project | [8 empty] | 0 | 0
2.2 | Etc | [8 empty] | 0 | 0
3 | MSE Facilities/Industrial Zones | [8 empty] | 0 | 0
3.1 | MSE Shade (New) | No | [7 empty] | 0 | 0
3.2 | MSE Shade (Rolled) | No |  | 0 | 0 |  |  |  |  | 0 | 0
3.3 | Etc | [8 empty] | 0 | 0
4 | Health Centres & Clinics | No | [7 empty] | 0 | 0
4.1 | Name of project | [8 empty] | 0 | 0
4.2 | Etc | [8 empty] | 0 | 0
5 | Schools | [8 empty] | 0 | 0
5.1 | Name of project | [8 empty] | 0 | 0
5.2 | Etc | [8 empty] | 0 | 0
| Sub-total Economic & Social Services |  | 0 |  | 5000000 |  | 5900000 |  | 6903000 | 0 | 17803000
E | Other | [8 empty] | 0 | 0
1 | Electricity reticulation | No |  | 1 | 3232455.76 | 2 | 3814297.7968 | 3 | 4462728.4223 | 6 | 11509481.9791
1.1. | Name of project | [8 empty] | 0 | 0
1.2 | Etc | [8 empty] | 0 | 0
| Sub-total Other |  |  |  | 3232455.76 | 2 | 3814297.7968 | 3 | 4462728.4223 | 6 | 11509481.9791
Total Pillar 6. Integrated Urban Infrastructure |  |  | 0 |  | 129251664.47 | 2 | 142789332.881 | 3 | 168821191.3068 | 7 | 440862188.6578
Pillar 7: Environmental, Green Services & Recreation | [9 empty] | 0 | 0
D | Environmental Services | [8 empty] | 0 | 0
1 | Drainage | [8 empty] | 0 | 0
1.1 | Name of drainage project(New) | m |  | 3311 | 13925595.93 | 3741.43 | 16432203.1974 | 4227.8159 | 19225677.741 | 11280.2459 | 49583476.8684
| Name of drainage project(Rolled) | m |  | 90 | 428733.89 |  |  |  |  | 90 | 428733.89
1.2 | Ditch cover (New) | No |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 | Etc | [5 empty] | 0 |  | 0 | 0 | 0
2 | Sanitation(Dust bin) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.1 | Name of project | [8 empty] | 0 | 0
2.2 | Etc | [8 empty] | 0 | 0
3 | Solid Waste | [8 empty] | 0 | 0
5 | Skip Loader | No |  | 1 | 4018603.09 | 2 | 4741951.6462 | 3 | 5548083.4261 | 6 | 14308638.1623
3.2 | Etc | [8 empty] | 0 | 0
4 | Liquid Waste | [8 empty] | 0 | 0
4.1 | Name of project | [8 empty] | 0 | 0
4.2 | Etc | [8 empty] | 0 | 0
5 | Urban Greenery | [8 empty] | 0 | 0
5.1 | Urban Greenery (New) | m2 |  | 15000 | 3849873.35 | 16950 | 4542850.553 | 19153.5 | 5315135.147 | 51103.5 | 13707859.05
5.2 | Urban Greenery (Rolled) | m2 |  | 22000 | 6173499.53 |  |  |  |  | 22000 | 6173499.53
6 | Parks and Play Areas(Rolled) | m2 | [7 empty] | 0 | 0
6.1 | Name of project | [8 empty] | 0 | 0
6.2 | Etc | [8 empty] | 0 | 0
7 | Rivers, wetlands, natural areas , watershed management | [8 empty] | 0 | 0
7.1 | Name of project | [8 empty] | 0 | 0
7.2 | Etc | [8 empty] | 0 | 0
| Subtotal Environmental Services |  |  |  | 28396305.79 | 20693.43 | 25717005.3966 | 23384.3159 | 30088896.314 | 84479.7459 | 84202207.5006
E | Other | [8 empty] | 0 | 0
Total Pillar 7: Environmental, Green Services & Recreation |  |  |  |  | 28396305.79 | 0 | 25717005.3966 | 0 | 30088896.314 | 0 | 84202207.5006
Total Pillar 8: Resilient, Inclusive and Safer Cities | [9 empty] | 0 | 0
C | Economic & Social Services | [8 empty] | 0 | 0
1 | Youth/Women Centres & Projects | No | [7 empty] | 0 | 0
1.1 | Name of project | [8 empty] | 0 | 0
1.2 | Etc | [8 empty] | 0 | 0
2 | Fire and Ambulances Services | No | [7 empty] | 0 | 0
2.1 | Fire Hydrant | No |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 | Etc | [8 empty] | 0 | 0
| Subtotal Economic & Social Services |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | Environmental Services | [8 empty] | 0 | 0
1 | Flood Protection (retaining walls etc) | m | [7 empty] | 0 | 0
1.1 | Retaining Wall (New) | m |  | 250 | 11388624.58 | 282.5 | 12963397.2804 | 319.225 | 10970867.7081 | 851.725 | 35322889.5685
1.2 | Retaining Wall (Rolled) | m |  | 330 | 11189679.97 |  |  |  |  | 330 | 11189679.97 | 130714777.0391
| Subtotal Environmental Services |  | 0 | 0 | 22578304.55 | 282.5 | 12963397.2804 | 319.225 | 10970867.7081 | 601.725 | 46512569.5385
E | Other | [5 empty] | 0 | 0 | 0 | 0 | 0
1 | [9 empty] | 0 | 0
1.1 | [9 empty] | 0 | 0
| Subtotal Other | [8 empty] | 0 | 0
Total Pillar 8: Resilient, Inclusive and Safer Cities total |  |  |  |  | 22578304.55 | 0 | 12963397.2804 | 0 | 10970867.7081 | 0 | 46512569.5385
[10 empty] | 0 | 0
[10 empty] | 0 | 0
1 | [9 empty] | 0 | 0
2 | [9 empty] | 0 | 0
3 etc. | [9 empty] | 0 | 0
Municipal Administration Buildings and Other Projects which cannot be put in Pillars | [9 empty] | 0 | 0
1 | Buildings(New) | No |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Buildings(Rolled) | No |  | 4 | 16533892 |  | 19840670.4 |  | 23808804.48 | 4 | 60183366.88
3 | Police Car | No |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Total station(New) | No |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Other |  | 0 | 4 | 16533892 | 0 | 19840670.4 | 0 | 23808804.48 | 4 | 60183366.88
0
| Total CIP |  |  |  | 196760166.81 |  | 201310405.958 |  | 233689759.8089 |  | 631760332.5769
0
Total Capacity Building Plan (from Table 15) |  |  |  |  | 5040160.02 |  | 5947388.8236 |  | 6958444.9236 |  | 17945993.7672
0
Grand Total Expenditure (CIP + CBP) |  |  |  |  | 201800326.83 | 0 | 207257794.7816 | 0 | 240648204.7325 | 0 | 649706326.3441
0
| Total Income |  |  |  | 201800326.8281 |  | 207257794.7804 |  | 240648204.7277 |  | 649706326.3363
0
| Surplus/Deficit |  |  |  | -0.00192 | 0 | -0.001151 | 0 | -0.0047656 | 0 | -0.0078367
0
[1] CIP Projects are now grouped under the ECSPG Pillars and also under the following four strategic areas as defined by the revised Asset Management Plan Manual: A. Movement Network; B. Water Supply Network; C. Economic and Social Services; D. Environmental Services. Any infrastructure category which does not fit into these four areas will be put in E. Other.
[6 empty] | 148767518.54 | 123654115.516 | 142202232.8434
[6 empty] | 105194318 | 0.14929 | 0.13043
[6 empty] | 0.05 | 0.05
[6 empty] | 1.0709 | 0.49258
[5 empty] | 174266434.83 | 174217124.38 | 200999400.25 | 549482959.46
[5 empty] | 27533892 | 33040670.4 | 39648804.48 | 100223366.88
[5 empty] | 201800326.83 | 207257794.78 | 240648204.73 | 649706326.34
0
0

## 11. Three-year-IBEX
No | Urban Investment Component | EFY 2013 | EFY 2014 | EFY 2015 | Total | % of total
1 | Road | 83621234.9 | 92004948.2888 | 109369014.2979 | 284995197.4867 | 51.87%
2 | Rehabilitation of Roads | 25397973.81 | 27870086.7954 | 32246448.5866 | 85514509.192 | 15.56%
3 | Integrated multiple infrastructure and land services | 4232455.76 | 3814297.7968 | 4462728.4223 | 12509481.9791 | 2.277%
4 | Sanitation (Liquid waste) including vacuum trucks etc. |  |  |  | 0
5 | Solid waste management | 4018603.09 | 4741951.6462 | 5548083.4261 | 14308638.1623 | 2.604%
6 | Urban Drainage | 36932634.37 | 29395600.4778 | 30196545.449 | 96524780.2968 | 17.57%
7 | Urban Disaster Risk Management | 0 | 0 | 0 | 0 | 0%
8 | Built facilities | 5000000 | 5900000 | 6903000 | 17803000 | 3.24%
9 | Urban Green Infrastructure | 10023372.88 | 4542850.553 | 5315135.147 | 19881358.58 | 3.618%
11 | Consultancy serv. for designs and Contract management |  |  |  | 0 | 0%
12 | Capacity Building support (up to 5% of CIP can be used on capacity building support). | 5040160.02 | 5947388.8236 | 6958444.9236 | 17945993.7672 | 3.266%
| Total | 174266434.83 | 174217124.3816 | 200999400.2525 | 549482959.4641 | 100% |  | 100%
7300000
| Asphalt | 174266434.83 | 174217124.38 | 200999400.25 | 549482959.46 |  |  |  | 5400000
|  | 0 | 0.0016 | 0.002496 | 0.0040959 |  |  |  | 186966434.83
|  | 800000 | 920000 | 1058000 |  |  | ,, MK,
|  |  | 920000.0016 | 1058000.0025 | 0.0040959
174266434.83
|  |  | 148767518.54 | 123654115.516 | 142202232.8434
|  |  | #REF! | #REF! | 0.15
-50563008.8656
-0.16881
9

## 12. Detail by source fund
S/N | Project | Unit | Qty | Total Cost | Funding Sources (Amount) , ETB
|  |  |  | EFY 2013 ( ETB) | UIIDP IDA Grant | Zonal Contribution | City Contribution | Additional state Funds | Additional Municipality Funds | Rolled from last year | Community Contribution
Pillar 6. Integrated Urban Infrastructure
A | Movement Network
UIIDP Funded projects
I | New projects
1 | Roads
1.1 | Cobblestone Road
1.1.1 | ASPHALT TO GETAHUN AYELE & GETAHUN LEMA TO GABALE TSARA | m2 | 2548 | 3409056.69 | 1863766.6465 | 772645.0217 | 772645.0217
1.1.2 | TAKELE TESEMA TO ELIYAS GAGA | m2 | 1470 | 2158666.98 | 1180165.6247 | 489250.6776 | 489250.6776
1.1.3 | DESALEGN DATA TO MEKANEYESUS GUEST HOUSE | m2 | 1470 | 1909901.61 | 1044163.0171 | 432869.2965 | 432869.2965
1.1.4 | ZERIHUN ZUMA TO TESFAYE DURE | m2 | 2310 | 2962220.34 | 1619476.58 | 671371.88 | 671371.88
1.1.5 | FROM CHICHE CHIBIRE TO TADELECH SHITAYE & LISANEWORK TO OLD BRIDGE | m2 | 2310 | 2707345.17 | 1480133.6813 | 613605.7443 | 613605.7443
1.1.6 | FROM AREGAWIYAN TO GULCHA DOKILE & YAPA YAYA TO ZENEBE ZIDA | m2 | 2380 | 3072009.34 | 1679499.3649 | 696254.9876 | 696254.9876
1.1.7 | HAILEMICHAEL HALALA TO BELAYNESH MERGIYA | m2 | 2625 | 3285820.16 | 1796391.9575 | 744714.1012 | 744714.1012
1.1.8 | ASHEBIR ASFA THROUGH ASFAW DAGNIE TO G/MEDIHIN ADINEW | m2 | 1750 | 2235173.13 | 1221992.3303 | 506590.3998 | 506590.3998 | [8 empty] | 0.41962
1.1.9 | ABEBE GEZAHAGN THROUGH MENGISTU MARKA TO PETROS | m2 | 1260 | 1687952.76 | 922821.279 | 382565.7405 | 382565.7405 | [8 empty] | 1.4196
1.1.10 | SOLOMON CHODA TO BITANE MENZA | m2 | 1890 | 2644387.71 | 1445714.185 | 599336.7625 | 599336.7625 | [8 empty] | 1.8392
1.1.11 | DAMENE TO SENODOS WOFCHO BET | m2 | 2240 | 2943135.74 | 1609042.8312 | 667046.4544 | 667046.4544
1.1.12 | MATEYOS LOHA TO KES KETEMA, MENZA TO AWUDE AHMED & CHAIN ACADAMY TO ASNAKECH LENCHA | m2 | 2310 | 2723883.57 | 1489175.3961 | 617354.0869 | 617354.0869 | [6 empty] | 57194318
1.1.13 | HUSEN YIMER TO ASKALECH GIZACHEW, LIYU MEAZA TO NATINAEL, TAGESE CHAFO TO MEDIHANIT METASEBIYA & DESALEGN LAFAMO TO MEKONNEN | m2 | 2590 | 3304230.95 | 1806457.3273 | 748886.8113 | 748886.8113 | [6 empty] | 24000000
1.1.14 | GETACHEW SEMERE TO ASPHALT | m2 | 2184 | 2682562.05 | 1466584.4926 | 607988.7787 | 607988.7787 | [6 empty] | 24000000
1.1.15 | BOMBOLO AGIDEW TO ASPHALT | m2 | 1470 | 1910331.97 | 1044398.2994 | 432966.8353 | 432966.8353 | [6 empty] | 105194318
1.1.16 | MOGES W/AMANUEL TO AEMIRO ALTO & MINALU BULGO TO TULO BOYZO | m2 | 1470 | 1910331.97 | 1044398.2994 | 432966.8353 | 432966.8353 | [6 empty] | 153194318
1.1.17 | CHALACHEW TAMIRU TO TESFAYE HAILE & BEDILU TO TIRUYE | m2 | 1890 | 2452169.02 | 1340626.2338 | 555771.3931 | 555771.3931 | [8 empty] | 0.41962
1.1.18 | WANSO WASHA TO THOMAS WASHE & JINKA BER TO MULUWONGEL | m2 | 2380 | 3079444.99 | 1683564.5118 | 697940.2391 | 697940.2391 | [8 empty] | 0.83924
1.1.19 | TSIGEREDA KEBEDE TO MENGISTU WORKU & D/R TESFAYE TO TADELE YILMA | m2 | 2700 | 3043254.7 | 1663778.905 | 689737.8975 | 689737.8975 | [8 empty] | 1.8392
1.1.20 | LABIYAJO THROUGH TSEGAYE BEKELE TO MOLA HABTE | m2 | 2320 | 2854440.11 | 1560552.0105 | 646944.0498 | 646944.0498
1.1.21 | MOLA HABTE THROUGH ASCHENAKI MAMO TO NEW ASPHALT | m2 | 2800 | 3405735.48 | 1861950.9066 | 771892.2867 | 771892.2867
1.1.22 | SHEWAYE MINDAYE THROUGH NEW CULVERT TO WONDWOSEN WUBAYEHU | m2 | 2450 | 3165314.25 | 1730510.1268 | 717402.0616 | 717402.0616
1.1.23 | TESFAYE KOIRA THROUGH ALMAZ ALEMAYEHU TO GUDELA KUSIYA | m2 | 1960 | 2570254.38 | 1405184.7247 | 582534.8276 | 582534.8276
1.1.24 | KASAHUN GEZAHAGN TO MINJA, MINJA TO WONBERA, WONBERA TO DEBEBE LOFA | m2 | 1960 | 2504746.3 | 1369370.778 | 567687.761 | 567687.761
1.1.25 | KASAHUN GEZAHAGN TO MENGISTU MEYA & ETENESH BEKELE TO DEREJE ALEMU | m2 | 1820 | 2334729.2 | 1276420.6663 | 529154.2669 | 529154.2669
1.1.26 | ADDIS ALEMAYEHU WOFCHO BET TO DEBEBE MAMACHA | m2 | 1620 | 1903508.31 | 1040667.7337 | 431420.2882 | 431420.2882
1.1.27 | ABUGIYA SHILE TO YIFTUSIRA MOLA | m2 | 2160 | 2606027.61 | 1424742.3206 | 590642.6447 | 590642.6447
1.1.28 | WADA DERE TO DEBEBE BIRHANE | m2 | 1869 | 2484813.76 | 1358473.4517 | 563170.1542 | 563170.1542
1.1.29 | RAHEL KULINO TO W/RO BIRHANE KASA | m2 | 1520 | 1870967.11 | 1022877.1222 | 424044.9939 | 424044.9939
1.1.30 | EJIGAYEHU DEBREWORK TO MESERET ADANE | m2 | 1760 | 2147879.8 | 1174268.1615 | 486805.8192 | 486805.8192
| Cobblestone Road total |  | 61486 | 77970295.16 | 42627168.9656 | 17671563.0972 | 17671563.0972 | 0 | 0 | 0 | 0
1.2 | Street Light
1.2.1 | From Konso sefer adebabay to Admasu house and from Fish Corporation to Zone Urban Dev't Office | Km | 2.4 | 6573707.26 | 3593913.9326 | 1489896.6637 | 1489896.6637 |  |  | 0
| Street Light total |  | 2.4 | 6573707.26 | 3593913.9326 | 1489896.6637 | 1489896.6637 |  |  | 0
1.3 | Bridges,Fords & Culvert construction
1.3.1 | HIBRET LELIMAT SCHOOL CULVERT | No | 1 | 1010619.57 | 552516.1997 | 229051.6852 | 229051.6852 |  |  |  |  | 1000 | 280 | 280000
1.3.2 | SINODOS CULVERT | No | 1 | 1203996.91 | 658237.5969 | 272879.6565 | 272879.6565 |  |  |  |  | 1000 | 200 | 200000
1.3.3 | CATHOLIC MISSION CULVERT | No | 1 | 1159160.31 | 633724.9627 | 262717.6736 | 262717.6736 |  |  |  |  | 1450 | 104 | 150800
1.3.4 | GURBA CULVERT | No | 1 | 946138.84 | 517263.9159 | 214437.4621 | 214437.4621 |  |  |  |  | 3450 | 584 | 630800
1.3.5 | TSEGAYE H/GIORGIS BRIDGE/GEBRIEL MESHAGERIYA | No | 1 | 5065074.31 | 2769128.6533 | 1147972.8283 | 1147972.8283 |  |  |  |  | 3.45 |  | 182.8406 | 182840.5797
| Bridges,Fords & Culvert construction total |  |  | 9384989.94 | 5130871.3285 | 2127059.3057 | 2127059.3057 | 0
| Movement Network (New Projects) Total |  |  | 93928992.36 | 51351954.2267 | 21288519.0667 | 21288519.0667 | 0 | 0 | 0 | 0
Movement Network (Rolled)
1 | Rolled Cobble stone
1.1 | From Ato Dubale Dunke to S/R Yirgedu, Alemu Ano to Mewale Hitsan Block 4 | m2 | 3745 | 2353222.57 | [5 empty] | 2353222.57
1.2 | From Endezihnew Kasaye to Wushu Pension | m2 | 70 | 653712.95 | [5 empty] | 653712.95
1.3 | From Eyob Kurka to Gida Gita | m2 | 140 | 674018.23 | [5 empty] | 674018.23
1.4 | From Lukas Woga to Dr. Melkamu Biniyam | m2 | 70 | 552825.18 | [5 empty] | 552825.18
1.5 | From Mesfin Albo to W/ro Tsehay house | m2 | 70 | 521796.62 | [5 empty] | 521796.62
1.6 | From Tefera Bizuneh to Almaz Gergeda | m2 | 70 | 419452.44 | [5 empty] | 419452.44
1.7 | Shaleka Debebe Sisay to New Asphalt | m2 | 35 | 475911.75 | [5 empty] | 475911.75
| Rolled Cobble stone total |  | 4200 | 5650939.74 | 0 | 0 | 0 |  |  | 5650939.74
1.3 | Rolled Bridges,Fords & Culvert construction
1.3.1 | Chamo Campus University Fence | No | 1 | 539035.66 | 0 | 0 | 0 |  |  | 539035.66
1.3.2 | Sebsibe Haile Culvert | No | 1 | 901281.57 | [5 empty] | 901281.57
1.3.3 | Dawit Dage to Ashewa Mado | No | 1 | 7998959.38 | [5 empty] | 7998959.38
| Rolled Bridges,Fords & Culvert construction total |  | 3 | 9439276.61 | 0 | 0 | 0 | 0 | 0 | 9439276.61 | 0
1.4 | Rolled Roundabout constrution
1.4.1 | Gamo Round about construction | 1 | 1 | 11000000 |  |  |  | 11000000 | 0
| Sub total | 1 | 1 | 11000000 |  |  |  | 11000000 | 0
| Movement Network (Rolled) Total |  |  | 26090216.35 | 0 | 0 | 0 | 11000000 | 0 | 15090216.35 | 0
| Movement Network Total |  |  | 120019208.71 | 51351954.2267 | 21288519.0667 | 21288519.0667 | 11000000 | 0 | 15090216.35 | 0
B | Economic & Social Services
Economic & Social Services(New Projects)
| Economic & Social Services(New Projects) Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Economic & Social Services(Rolled)
1.4.2 | Abattior car | No | 1 | 5000000 | [5 empty] | 5000000
| Economic & Social Services(Rolled)Total |  | 1 | 5000000 |  |  |  | 0 | 0 | 5000000
| Economic & Social Services Total |  | 1 | 5000000 | 0 | 0 | 0 | 0 | 0 | 5000000 | 0
E | Other
Electricity Reticulation
Electric Line Expansion /Transformer /
1.1 | SENODOS SEFER & AT THE BACK OF TEXTILE FACTORY | No | 2 | 3232455.76 | 1767217.0866 | 732619.3367 | 732619.3367
| Electric Line Expansion /Transformer /Total |  | 2 | 3232455.76 | 1767217.0866 | 732619.3367 | 732619.3367
| WATER SUPPLY |  |  |  | 0 | 0 | 0
| WATER SUPPLY PROJECT AT THE BACK OF TEXTILE FACTORY | No | 1 | 1000000 | 546710.3706 | 226644.8147 | 226644.8147
| WATER SUPPLY Total |  | 1 | 1000000 | 546710.3706 | 226644.8147 | 226644.8147 | 0 | 0 | 0 | 0
| Pillar 6. Integrated Urban Infrastructure Total |  |  | 129251664.47 | 53665881.6839 | 22247783.218 | 22247783.218 | 11000000 | 0 | 20090216.35 | 0
Pillar 7: Environmental, Green Services & Recreation
C | Environmental Services(New Projects)
1.2 | Drainage construction
1.2.1 | TESFAYE TEFERA TO BEZABIH WADA & AKIRSO KORA TO BONO | m | 412 | 1544014.58 | 844128.7833 | 349942.8983 | 349942.8983
1.2.2 | BRIDGE TO TESFAYE WORKINEH | m | 280 | 1030416.91 | 563339.6108 | 233538.6496 | 233538.6496
1.2.3 | GEDA GAZE TO MATEYOS ASHA | m | 134 | 576882.82 | 315387.8203 | 130747.4998 | 130747.4998
1.2.4 | GIRMA SANA TO BEKELE TADESE | m | 170 | 688277.63 | 376288.5182 | 155994.5559 | 155994.5559
1.2.5 | DAWIT DORKE THROUGH SAMSON TO GEZMO TINKU | m | 310 | 1119713.45 | 612158.9553 | 253777.2474 | 253777.2474
1.2.6 | BIRKABY THROUGH ABERA MOTA TO ENDALE H/MESKEL | m | 350 | 1243485.46 | 679826.3967 | 281829.5316 | 281829.5316
1.2.7 | KALEB KANKO TO DIDO ABUTE | m | 130 | 566271.85 | 309586.693 | 128342.5785 | 128342.5785
1.2.8 | YISIHAK MENA TO WONDIYIFRAW | m | 220 | 842992.65 | 460872.8241 | 191059.9129 | 191059.9129
1.2.9 | CHAMO CAMPUS ASPHALT TO BEHAILU ABOTA | m | 220 | 842992.65 | 460872.8241 | 191059.9129 | 191059.9129
1.2.10 | AZENEH TEKA TO GORGE & BIZUNEH BUSA TO BISAF LEMA | m | 480 | 1910208.79 | 1044330.9556 | 432938.9172 | 432938.9172
1.2.11 | KULIFO GREENERY SITE DITCH | M | 305 | 1240478.37 | 678182.3894 | 281147.9903 | 281147.9903
1.2.12 | S/R YIRGEDU MENGESHA TO SIYERE MEKURIYA | m | 300 | 2319860.77 | 1268291.9414 | 525784.4143 | 525784.4143
| Drainage total |  | 3311 | 13925595.93 | 7613267.7122 | 3156164.1089 | 3156164.1089 | 0 |  | 0 | 0
1.6 | Greenery development
1.6.2 | Public Park at the side of Kulufo river phase-IIII | m2 | 15000 | 3849873.35 | 2104765.6861 | 872553.832 | 872553.832
| Greenery development total |  | 15000 | 3849873.35 | 2104765.6861 | 872553.832 | 872553.832
5 | Municipal Non UIIDP Works (New)
Municipal Non UIIDP Works (New) Total
| Environmental Services(New Projects) Total |  |  | 17775469.28 | 9718033.3983 | 4028717.9408 | 4028717.9408 | 0 | 0 | 0 | 0
Environmental Services(Rolled)
5 | Rolled Greenery Development
5.2 | Public Park at the side of Kulufo river phase-3 | m2 | 18000 | 3498963.64 | [5 empty] | 3498963.64
5.3 | Omo Hall Compound Greenary Development phase-2 | m2 | 4000 | 726094.65 | [5 empty] | 726094.65
| Rolled Greenery Development Total |  | 22000 | 4225058.29 | 0 | 0 | 0 | 0 | 0 | 4225058.29
6 | Rolled Greenery protection fence
6.1 | From Referral Hospital to Lemlem Square phase-2 | km | 0.1 | 630392.95 | [5 empty] | 630392.95
| Rolled Greenery protection fence Total |  | 0.1 | 630392.95 | 0 | 0 | 0 | 0 | 0 | 630392.95 | 0
7 | Rolled Asphalt median and greenery
7.1 | From Haile Resort to Hawariyat Church | km | 0.1 | 1318048.29 | [5 empty] | 1318048.29
| Rolled Asphalt median and greenery Total |  | 0.1 | 1318048.29 | 0 | 0 | 0 | 0 | 0 | 1318048.29
6 | Rolled Drainage Projects
6.1 | From Alemu Ano to Pawlos Genta | m | 90 | 428733.89 | [5 empty] | 428733.89
| Rolled Drainage Projects Total |  | 90 | 428733.89 | 0 | 0 | 0 | 0 | 0 | 428733.89
2 | Solid Waste (Rolled)
1.4.1 | Skip loader | No | 1 | 4018603.09 | [5 empty] | 4018603.09
| Solid Waste (Rolled) total |  | 1 | 4018603.09 |  |  |  | 0 | 0 | 4018603.09
| Environmental Services (Rolled) Total |  |  | 10620836.51 | 0 | 0 | 0 | 0 | 0 | 10620836.51
| Environmental Services Total |  |  | 28396305.79 | 9718033.3983 | 4028717.9408 | 4028717.9408 | 0 | 0 | 10620836.51 | 0
Others
| Pillar 7: Environmental, Green Services & Recreation Total |  |  | 28396305.79 | 9718033.3983 | 4028717.9408 | 4028717.9408 | 0 | 0 | 10620836.51 | -
Pillar 8: Resilient, Inclusive and Safer Cities
Environmental Services
1.3 | Retaining wall construction(New)
1.3.1 | Retaining wall at the side of Kulufo river phase-III | m | 250 | 11388624.58 | 6226279.1652 | 2581172.7074 | 2581172.7074
| Retaining wall total |  | 250 | 11388624.58 | 6226279.1652 | 2581172.7074 | 2581172.7074
2 | Retaining wall(Rolled)
2.1 | Retaining wall at the side of Kulufo river phase-II | m3 | 250 | 9806360.5 |  | 0 | 0 |  |  | 9806360.5
2.2 | Konso Market to Stadium Retaining wall | m3 | 80 | 1383319.47 | [5 empty] | 1383319.47
| Rolled Retaining wall total |  | 330 | 11189679.97 | 0 | 0 | 0 | 0 | 0 | 11189679.97 |  |  | 11189679.97
| Retaining wall total |  | 580 | 22578304.55 | 6226279.1652 | 2581172.7074 | 2581172.7074 | 0 | 0 | 11189679.97
| Environmental Services Total |  |  | 22578304.55 | 6226279.1652 | 2581172.7074 | 2581172.7074 | 0 |  | 11189679.97
| Pillar 8: Resilient, Inclusive and Safer Cities total |  |  | 22578304.55 | 6226279.1652 | 2581172.7074 | 2581172.7074 | 0 |  | 11189679.97 | 0
Municipal Administration Buildings and Other Projects which cannot be put in Pillars
Municipal (New projects)
A | Buildings(New)
Buildings(Rolled)
1 | Low cot house | No | 1 | 4000000 |  |  |  |  | 4000000
2 | Cadaster office building | No | 1 | 9448892 |  |  |  |  | 9448892
3 | Animal Health Center | No | 1 | 1585000 |  |  |  | 1585000
3 | Rolled One shop serveice shed building | No | 1 | 1500000 |  |  |  | 1500000
| Buildings (Rolled) Total | No | 4 | 16533892 | 0 | 0 | 0 | 3085000 | 13448892 | 0 | 0
| Buildings Total | No | 4 | 16533892 | 0 | 0 | 0 | 3085000 | 13448892 | 0 | 0
| Municipal (Rolled projects) |  |  | 16533892 | 0 | 0 | 0 | 3085000 | 13448892 | 0
Consultancy Services for designs and contract management/supervision
1
[9 empty] | 0 | 0 | 0
6 | Capacity building
6.1 | Local training |  |  | 2225000 | 1216430.5747 | 504284.7127 | 504284.7127
6.2 | Office equipment |  |  | 2815160.02 | 1539077.1779 | 638041.421 | 638041.421
| Capacity building |  |  | 5040160.02 | 2755507.7526 | 1142326.1337 | 1142326.1337
| Total CIP Budget |  |  | 201800326.83 | 72365702 | 30000000 | 30000000 | 14085000 | 13448892 | 41900732.83 | 0
[5 empty] | 132365702 |  | 174266434.83
|  |  |  | 202412969.09 | [5 empty] | 201800326.83
| 2755507.75 |  |  |  | 882100.33 |  | 201800326.83
| 69610194.25 |  |  | 1.8291 | 3117899.33 |  | 27533892 |  |  | 612642.26
| 72365702 |  |  | 0.41456 | 3999999.66 |  | 174266434.83 |  |  | 42513375.09
132365702
|  |  |  | 72365702 |  | 3000000
|  |  |  | 30000000 |  | 3000000
30000000
|  |  |  | 132365702 | 30000000
[5 empty] | 72365702 |  | 1.8291 | 0.41456
[5 empty] | 0.41456 |  |  | 0.82912
1.8291

## 13. Detailed AAP
Action plan and Cash Flow Plan After Revision of CIP
New Assets
Region: SNNPR
City:Arbaminch
Title: Annual Action Plan (2013 E.C.)
SN | Activity | Category | Output Indicator /unit of measure/ | Implementation period |  |  |  | Annual total | Remark
|  |  |  | Q1 | Q2 | Q3 | Q4
Physical/Financial
Pillar 6. Integrated Urban Infrastructure
A | Movement Network
UIIDP Funded projects
I | New projects
1 | Roads
1.1 | Cobblestone Road
1.1.1 | ASPHALT TO GETAHUN AYELE & GETAHUN LEMA TO GABALE TSARA | Civil Work | m2 |  | 637 | 1274 | 637 | 2548
|  |  | km |  | 0.091 | 0.182 | 0.091 | 0.364
|  |  | ETB |  | 852264.1725 | 1704528.345 | 852264.1725 | 3409056.69
1.1.2 | TAKELE TESEMA TO ELIYAS GAGA | Civil Work | m2 |  | 367.5 | 735 | 367.5 | 1470
|  |  | km |  | 0.0525 | 0.105 | 0.0525 | 0.21
|  |  | ETB |  | 539666.745 | 1079333.49 | 539666.745 | 2158666.98
1.1.3 | DESALEGN DATA TO MEKANEYESUS GUEST HOUSE | Civil Work | m2 |  | 367.5 | 735 | 367.5 | 1470
|  |  | km |  | 0.0525 | 0.105 | 0.0525 | 0.21
|  |  | ETB |  | 477475.4025 | 954950.805 | 477475.4025 | 1909901.61
1.1.4 | ZERIHUN ZUMA TO TESFAYE DURE | Civil Work | m2 |  | 577.5 | 1155 | 577.5 | 2310
|  |  | km |  | 0.0825 | 0.165 | 0.0825 | 0.33
|  |  | ETB |  | 740555.085 | 1481110.17 | 740555.085 | 2962220.34
1.1.5 | FROM CHICHE CHIBIRE TO TADELECH SHITAYE & LISANEWORK TO OLD BRIDGE | Civil Work | m2 |  | 577.5 | 1155 | 577.5 | 2310
|  |  | km |  | 0.0825 | 0.165 | 0.0825 | 0.33
|  |  | ETB |  | 676836.2925 | 1353672.585 | 676836.2925 | 2707345.17
1.1.6 | FROM AREGAWIYAN TO GULCHA DOKILE & YAPA YAYA TO ZENEBE ZIDA | Civil Work | m2 |  | 595 | 1190 | 595 | 2380
|  |  | km |  | 0.085 | 0.17 | 0.085 | 0.34
|  |  | ETB |  | 768002.335 | 1536004.67 | 768002.335 | 3072009.34
1.1.7 | HAILEMICHAEL HALALA TO BELAYNESH MERGIYA | Civil Work | m2 |  | 656.25 | 1312.5 | 656.25 | 2625
|  |  | km |  | 0.09375 | 0.1875 | 0.09375 | 0.375
|  |  | ETB |  | 821455.04 | 1642910.08 | 821455.04 | 3285820.16
1.1.8 | ASHEBIR ASFA THROUGH ASFAW DAGNIE TO G/MEDIHIN ADINEW | Civil Work | m2 |  | 437.5 | 875 | 437.5 | 1750
|  |  | km |  | 0.0625 | 0.125 | 0.0625 | 0.25
|  |  | ETB |  | 558793.2825 | 1117586.565 | 558793.2825 | 2235173.13
1.1.9 | ABEBE GEZAHAGN THROUGH MENGISTU MARKA TO PETROS | Civil Work | m2 |  | 315 | 630 | 315 | 1260
|  |  | km |  | 0.045 | 0.09 | 0.045 | 0.18
|  |  | ETB |  | 421988.19 | 843976.38 | 421988.19 | 1687952.76
1.1.10 | SOLOMON CHODA TO BITANE MENZA | Civil Work | m2 |  | 472.5 | 945 | 472.5 | 1890
|  |  | km |  | 0.0675 | 0.135 | 0.0675 | 0.27
|  |  | ETB |  | 661096.9275 | 1322193.855 | 661096.9275 | 2644387.71
1.1.11 | DAMENE TO SENODOS WOFCHO BET | Civil Work | m2 |  | 560 | 1120 | 560 | 2240
|  |  | km |  | 0.08 | 0.16 | 0.08 | 0.32
|  |  | ETB |  | 735783.935 | 1471567.87 | 735783.935 | 2943135.74
1.1.12 | MATEYOS LOHA TO KES KETEMA, MENZA TO AWUDE AHMED & CHAIN ACADAMY TO ASNAKECH LENCHA | Civil Work | m2 |  | 577.5 | 1155 | 577.5 | 2310
|  |  | km |  | 0.0825 | 0.165 | 0.0825 | 0.33
|  |  | ETB |  | 680970.8925 | 1361941.785 | 680970.8925 | 2723883.57
1.1.13 | HUSEN YIMER TO ASKALECH GIZACHEW, LIYU MEAZA TO NATINAEL, TAGESE CHAFO TO MEDIHANIT METASEBIYA & DESALEGN LAFAMO TO MEKONNEN | Civil Work | m2 |  | 647.5 | 1295 | 647.5 | 2590
|  |  | km |  | 0.0925 | 0.185 | 0.0925 | 0.37
|  |  | ETB |  | 826057.7375 | 1652115.475 | 826057.7375 | 3304230.95
1.1.14 | GETACHEW SEMERE TO ASPHALT | Civil Work | m2 |  | 546 | 1092 | 546 | 2184
|  |  | km |  | 0.06825 | 0.1365 | 0.06825 | 0.273
|  |  | ETB |  | 670640.5125 | 1341281.025 | 670640.5125 | 2682562.05
1.1.15 | BOMBOLO AGIDEW TO ASPHALT | Civil Work | m2 |  | 367.5 | 735 | 367.5 | 1470
|  |  | km |  | 0.0525 | 0.105 | 0.0525 | 0.21
|  |  | ETB |  | 477582.9925 | 955165.985 | 477582.9925 | 1910331.97
1.1.16 | MOGES W/AMANUEL TO AEMIRO ALTO & MINALU BULGO TO TULO BOYZO | Civil Work | m2 |  | 367.5 | 735 | 367.5 | 1470
|  |  | km |  | 0.0525 | 0.105 | 0.0525 | 0.21
|  |  | ETB |  | 477582.9925 | 955165.985 | 477582.9925 | 1910331.97
1.1.17 | CHALACHEW TAMIRU TO TESFAYE HAILE & BEDILU TO TIRUYE | Civil Work | m2 |  | 472.5 | 945 | 472.5 | 1890
|  |  | km |  | 0.0675 | 0.135 | 0.0675 | 0.27
|  |  | ETB |  | 613042.255 | 1226084.51 | 613042.255 | 2452169.02
1.1.18 | WANSO WASHA TO THOMAS WASHE & JINKA BER TO MULUWONGEL | Civil Work | m2 |  | 595 | 1190 | 595 | 2380
|  |  | km |  | 0.085 | 0.17 | 0.085 | 0.34
|  |  | ETB |  | 769861.2475 | 1539722.495 | 769861.2475 | 3079444.99
1.1.19 | TSIGEREDA KEBEDE TO MENGISTU WORKU & D/R TESFAYE TO TADELE YILMA | Civil Work | m2 |  | 675 | 1350 | 675 | 2700
|  |  | km |  | 0.0675 | 0.135 | 0.0675 | 0.27
|  |  | ETB |  | 760813.675 | 1521627.35 | 760813.675 | 3043254.7
1.1.20 | LABIYAJO THROUGH TSEGAYE BEKELE TO MOLA HABTE | Civil Work | m2 |  | 580 | 1160 | 580 | 2320
|  |  | km |  | 0.0725 | 0.145 | 0.0725 | 0.29
|  |  | ETB |  | 713610.0275 | 1427220.055 | 713610.0275 | 2854440.11
1.1.21 | MOLA HABTE THROUGH ASCHENAKI MAMO TO NEW ASPHALT | Civil Work | m2 |  | 700 | 1400 | 700 | 2800
|  |  | km |  | 0.0875 | 0.175 | 0.0875 | 0.35
|  |  | ETB |  | 851433.87 | 1702867.74 | 851433.87 | 3405735.48
1.1.22 | SHEWAYE MINDAYE THROUGH NEW CULVERT TO WONDWOSEN WUBAYEHU | Civil Work | m2 |  | 612.5 | 1225 | 612.5 | 2450
|  |  | km |  | 0.0875 | 0.175 | 0.0875 | 0.35
|  |  | ETB |  | 791328.5625 | 1582657.125 | 791328.5625 | 3165314.25
1.1.23 | TESFAYE KOIRA THROUGH ALMAZ ALEMAYEHU TO GUDELA KUSIYA | Civil Work | m2 |  | 490 | 980 | 490 | 1960
|  |  | km |  | 0.07 | 0.14 | 0.07 | 0.28
|  |  | ETB |  | 642563.595 | 1285127.19 | 642563.595 | 2570254.38
1.1.24 | KASAHUN GEZAHAGN TO MINJA, MINJA TO WONBERA, WONBERA TO DEBEBE LOFA | Civil Work | m2 |  | 490 | 980 | 490 | 1960
|  |  | km |  | 0.07 | 0.14 | 0.07 | 0.28
|  |  | ETB |  | 626186.575 | 1252373.15 | 626186.575 | 2504746.3
1.1.25 | KASAHUN GEZAHAGN TO MENGISTU MEYA & ETENESH BEKELE TO DEREJE ALEMU | Civil Work | m2 |  | 455 | 910 | 455 | 1820
|  |  | km |  | 0.065 | 0.13 | 0.065 | 0.26
|  |  | ETB |  | 583682.3 | 1167364.6 | 583682.3 | 2334729.2
1.1.26 | ADDIS ALEMAYEHU WOFCHO BET TO DEBEBE MAMACHA | Civil Work | m2 |  | 405 | 810 | 405 | 1620
|  |  | km |  | 0.045 | 0.09 | 0.045 | 0.18
|  |  | ETB |  | 475877.0775 | 951754.155 | 475877.0775 | 1903508.31
1.1.27 | ABUGIYA SHILE TO YIFTUSIRA MOLA | Civil Work | m2 |  | 540 | 1080 | 540 | 2160
|  |  | km |  | 0.0675 | 0.135 | 0.0675 | 0.27
|  |  | ETB |  | 651506.9025 | 1303013.805 | 651506.9025 | 2606027.61
1.1.28 | WADA DERE TO DEBEBE BIRHANE | Civil Work | m2 |  | 467.25 | 934.5 | 467.25 | 1869
|  |  | km |  | 0.06675 | 0.1335 | 0.06675 | 0.267
|  |  | ETB |  | 621203.44 | 1242406.88 | 621203.44 | 2484813.76
1.1.29 | RAHEL KULINO TO W/RO BIRHANE KASA | Civil Work | m2 |  | 380 | 760 | 380 | 1520
|  |  | km |  | 0.0475 | 0.095 | 0.0475 | 0.19
|  |  | ETB |  | 467741.7775 | 935483.555 | 467741.7775 | 1870967.11
1.1.30 | EJIGAYEHU DEBREWORK TO MESERET ADANE | Civil Work | m2 |  | 440 | 880 | 440 | 1760
|  |  | km |  | 0.055 | 0.11 | 0.055 | 0.22
|  |  | ETB |  | 536969.95 | 1073939.9 | 536969.95 | 2147879.8
| Cobblestone Road total | Civil Work | m2 |  | 14636.5 | 29273 | 14636.5 | 61486 |  | 58546
|  |  | km |  | 1.9923 | 3.9845 | 1.9923 | 8.389 |  | 7.969
|  |  | ETB |  | 18537515.395 | 37075030.79 | 18537515.395 | 77970295.16 | 0 | 74150061.58
1.2 | Street Light
1.2.1 | From Konso sefer adebabay to Admasu house and from Fish Corporation to Zone Urban Dev't Office | Civil Work | m2
|  |  | km |  | 0.6 | 1.2 | 0.6 | 2.4
|  |  | ETB |  | 1643426.815 | 3286853.63 | 1643426.815 | 6573707.26
| Street Light total | Civil Work | m2 |  | 0 | 0 | 0
|  |  | km |  | 0.6 | 1.2 | 0.6 | 2.4
|  |  | ETB |  | 1643426.815 | 3286853.63 | 1643426.815 | 6573707.26 | 0
1.3 | Bridges,Fords & Culvert construction
1.3.1 | HIBRET LELIMAT SCHOOL CULVERT | Civil Work | No |  | 0.25 | 0.5 | 0.25 | 1
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 252654.8925 | 505309.785 | 252654.8925 | 1010619.57
1.3.2 | SINODOS CULVERT | Civil Work | No |  | 0.25 | 0.5 | 0.25 | 1
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 300999.2275 | 601998.455 | 300999.2275 | 1203996.91
1.3.3 | CATHOLIC MISSION CULVERT | Civil Work | No |  | 0.25 | 0.5 | 0.25 | 1
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 289790.0775 | 579580.155 | 289790.0775 | 1159160.31
1.3.4 | GURBA CULVERT | Civil Work | No |  | 0.25 | 0.5 | 0.25 | 1
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 236534.71 | 473069.42 | 236534.71 | 946138.84
1.3.5 | TSEGAYE H/GIORGIS BRIDGE/GEBRIEL MESHAGERIYA | Civil Work | No |  | 0.25 | 0.5 | 0.25 | 1
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 1266268.5775 | 2532537.155 | 1266268.5775 | 5065074.31
| Bridges,Fords & Culvert construction total | Civil Work | No |  | 1.25 | 2.5 | 1.25 | 5
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 2346247.485 | 4692494.97 | 2346247.485 | 9384989.94 | 0
| Movement Network (New Projects) Total |  | 0 | 0 | 22527189.695 | 45054379.39 | 22527189.695 | 93928992.36 | 0
Movement Network (Rolled)
1 | Rolled Cobble stone
1.1 | From Ato Dubale Dunke to S/R Yirgedu, Alemu Ano to Mewale Hitsan Block 4 | Civil Work | m2 | 3745 |  |  |  | 3745
|  |  | km | 0.535 | 0 | 0 | 0 | 0.535
|  |  | ETB | 2353222.57 |  |  |  | 2353222.57
1.2 | From Endezihnew Kasaye to Wushu Pension | Civil Work | m2 | 70 |  |  |  | 70
|  |  | km | 0.01 | 0 | 0 | 0 | 0.01
|  |  | ETB | 653712.95 |  |  |  | 653712.95
1.3 | From Eyob Kurka to Gida Gita | Civil Work | m2 | 140 |  |  |  | 140
|  |  | km | 0.02 | 0 | 0 | 0 | 0.02
|  |  | ETB | 674018.23 |  |  |  | 674018.23
1.4 | From Lukas Woga to Dr. Melkamu Biniyam | Civil Work | m2 | 70 |  |  |  | 70
|  |  | km | 0.01 | 0 | 0 | 0 | 0.01
|  |  | ETB | 552825.18 |  |  |  | 552825.18
1.5 | From Mesfin Albo to W/ro Tsehay house | Civil Work | m2 | 70 |  |  |  | 70
|  |  | km | 0.01 | 0 | 0 | 0 | 0.01
|  |  | ETB | 521796.62 |  |  |  | 521796.62
1.6 | From Tefera Bizuneh to Almaz Gergeda | Civil Work | m2 | 70 |  |  |  | 70
|  |  | km | 0.01 | 0 | 0 | 0 | 0.01
|  |  | ETB | 419452.44 |  |  |  | 419452.44
1.7 | Shaleka Debebe Sisay to New Asphalt | Civil Work | m2 | 70 |  |  |  | 70
|  |  | km | 0.01 | 0 | 0 | 0 | 0.01
|  |  | ETB | 475911.75 |  |  |  | 475911.75
| Rolled Cobble stone total | Civil Work | m2 | 4235 |  |  |  | 4235
|  |  | km | 0.605 | 0 | 0 | 0 | 0.605
|  |  | ETB | 5650939.74 |  |  | 0 | 5650939.74 | 0
1.2 | Rolled Bridges,Fords & Culvert construction
1.3.1 | Chamo Campus University Fence Culvert | Civil Work | No | 0.1 |  |  |  | 0.1
|  |  | km | 0
|  |  | ETB | 539035.66 |  |  |  | 539035.66 | 0
1.3.1 | Sebsibe Haile Culvert | Civil Work | No | 0.15 |  |  |  | 0.15
|  |  | km | 0
|  |  | ETB | 901281.57 |  |  |  | 901281.57 | 0
1.3.1 | Dawit Dage to Ashewa Mado Bridge | Civil Work | No | 0.1 |  |  |  | 0.1
|  |  | km | 0
|  |  | ETB | 7998959.38 |  |  |  | 7998959.38 | 0
| Rolled Bridges,Fords & Culvert construction total | Civil Work | No | 3 |  |  |  | 3
|  |  | km | 0
|  |  | ETB | 9439276.61 |  |  |  | 9439276.61 | 0
1.4 | Rolled Roundabout constrution
1.4.1 | Gamo Round about construction | Civil Work | No | 0.2 | 0.2 | 0.2 | 0.2 | 0.8
|  |  | km | 0 | 0 | 0 | 0
|  |  | ETB | 2750000 | 2750000 | 2750000 | 2750000 | 11000000
| Sub total | Civil Work | No | 0.2 | 0.2 | 0.2 | 0.2 | 0.8
|  |  | km | 0 | 0 | 0 | 0
|  |  | ETB | 2750000 | 2750000 | 2750000 | 2750000 | 11000000
| Movement Network (Rolled) Total |  |  | 17840216.35 | 2750000 | 2750000 | 2750000 | 26090216.35 | 0
| Movement Network Total |  |  | 17840216.35 | 25277189.695 | 47804379.39 | 25277189.695 | 120019208.71 | 0
B | Economic & Social Services
Economic & Social Services(New Projects)
Economic & Social Services(New Projects) Total
Economic & Social Services(Rolled Projects)
1.4.2 | Abattior car | Goods | No |  | 0.25 | 0.5 | 0.25 | 1
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 1250000 | 2500000 | 1250000 | 5000000
| Economic & Social Services(Rolled Projects)Total |  |  | 0 | 1250000 | 2500000 | 1250000 | 5000000
| Economic & Social Services Total |  |  | 0 | 1250000 | 2500000 | 1250000 | 5000000
E | Other
Electricity Reticulation
Electric Line Expansion /Transformer /
1.1 | SENODOS SEFER & AT THE BACK OF TEXTILE FACTORY | Civil Work | No |  | 0.5 | 1 | 0.5 | 2
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 808113.94 | 1616227.88 | 808113.94 | 3232455.76
| Electric Line Expansion /Transformer /Total | Civil Work | No |  | 0.5 | 1 | 0.5 | 2
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 808113.94 | 1616227.88 | 808113.94 | 3232455.76 | 0
WATER SUPPLY
1.1 | WATER SUPPLY PROJECT AT THE BACK OF TEXTILE FACTORY | Civil Work | No |  | 0.5 | 1 | 0.5 | 2
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 0 | 0 | 0 | 0
| WATER SUPPLY Total | Civil Work | No |  | 0.25 | 0.5 | 0.25 | 1
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 250000 | 500000 | 250000 | 1000000 | 0
| Pillar 6. Integrated Urban Infrastructure Total |  |  | 17840216.35 | 27585303.635 | 52420607.27 | 27585303.635 | 129251664.47 | 0
Pillar 7: Environmental, Green Services & Recreation
C | Environmental Services(New Projects)
1.2 | Drainage construction
1.2.1 | TESFAYE TEFERA TO BEZABIH WADA & AKIRSO KORA TO BONO | Civil Work | m |  | 103 | 206 | 103 | 412
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 386003.645 | 772007.29 | 386003.645 | 1544014.58
1.2.2 | BRIDGE TO TESFAYE WORKINEH | Civil Work | m |  | 70 | 140 | 70 | 280
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 257604.2275 | 515208.455 | 257604.2275 | 1030416.91
1.2.3 | GEDA GAZE TO MATEYOS ASHA | Civil Work | m |  | 33.5 | 67 | 33.5 | 134
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 144220.705 | 288441.41 | 144220.705 | 576882.82
1.2.4 | GIRMA SANA TO BEKELE TADESE | Civil Work | m |  | 42.5 | 85 | 42.5 | 170
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 172069.4075 | 344138.815 | 172069.4075 | 688277.63
1.2.5 | DAWIT DORKE THROUGH SAMSON TO GEZMO TINKU | Civil Work | m |  | 77.5 | 155 | 77.5 | 310
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 279928.3625 | 559856.725 | 279928.3625 | 1119713.45
1.2.6 | BIRKABY THROUGH ABERA MOTA TO ENDALE H/MESKEL | Civil Work | m |  | 87.5 | 175 | 87.5 | 350
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 310871.365 | 621742.73 | 310871.365 | 1243485.46
1.2.7 | KALEB KANKO TO DIDO ABUTE | Civil Work | m |  | 32.5 | 65 | 32.5 | 130
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 141567.9625 | 283135.925 | 141567.9625 | 566271.85
1.2.8 | YISIHAK MENA TO WONDIYIFRAW | Civil Work | m |  | 55 | 110 | 55 | 220
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 210748.1625 | 421496.325 | 210748.1625 | 842992.65
1.2.9 | CHAMO CAMPUS ASPHALT TO BEHAILU ABOTA | Civil Work | m |  | 55 | 110 | 55 | 220
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 210748.1625 | 421496.325 | 210748.1625 | 842992.65
1.2.10 | AZENEH TEKA TO GORGE & BIZUNEH BUSA TO BISAF LEMA | Civil Work | m |  | 120 | 240 | 120 | 480
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 477552.1975 | 955104.395 | 477552.1975 | 1910208.79
1.2.11 | KULIFO GREENERY SITE DITCH | Civil Work | m |  | 76.25 | 152.5 | 76.25 | 305
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 310119.5925 | 620239.185 | 310119.5925 | 1240478.37
1.2.12 | S/R YIRGEDU MENGESHA TO SIYERE MEKURIYA | Civil Work | m |  | 75 | 150 | 75 | 300
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 579965.1925 | 1159930.385 | 579965.1925 | 2319860.77
| Drainage total | Civil Work | m | 0 | 751.5 | 1503 | 751.5 | 3006
|  |  | km |  | 0 | 0 | 0
|  |  | ETB | 0 | 3171279.39 | 6342558.78 | 3171279.39 | 13925595.93 | 0
1.5 | Greenery development
1.5.2 | Public Park at the side of Kulufo river phase-IIII | Civil Work | m2 |  | 3750 | 7500 | 3750 | 15000
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 962468.3375 | 1924936.675 | 962468.3375 | 3849873.35
| Greenery development total | Civil Work | m2 |  | 3750 | 7500 | 3750 | 15000
|  |  | km |  | 0 | 0 | 0
|  |  | ETB | 0 | 962468.3375 | 1924936.675 | 962468.3375 | 3849873.35 | 0
| Environmental Services(New Projects) Total |  |  | 0 | 4133747.7275 | 8267495.455 | 4133747.7275 | 17775469.28 | 0
Environmental Services(Rolled)
5 | Rolled Greenery Development
5.1 | Public Park at the side of Kulufo river phase-3 | Civil Work | m2 | 18000 |  |  |  | 18000
|  |  | km | 0
|  |  | ETB | 3498963.64 |  |  |  | 3498963.64
5.2 | Omo Hall Compound Greenary Development phase-2 | Civil Work | m2 | 4000 |  |  |  | 4000
|  |  | km | 0
|  |  | ETB | 726094.65 |  |  |  | 726094.65
| Rolled Greenery Development Total | Civil Work | m2 | 22000 |  |  |  | 22000
|  |  | km | 0
|  |  | ETB | 4225058.29 |  |  |  | 4225058.29
Rolled Greenery protection fence
5.4 | From Referral Hospital to Lemlem Square phase-2 | Civil Work | m | 0.1 |  |  |  | 0.1
|  |  | km | 0.1 |  |  |  | 0.1
|  |  | ETB | 630392.95 |  |  |  | 630392.95
| Rolled Greenery protection fence Total | Civil Work | m | 0.1 |  |  |  | 0.1
|  |  | km | 0 |  |  |  | 0
|  |  | ETB | 630392.95 |  |  |  | 630392.95
Rolled Asphalt median and greenery
5.5 | From Haile Resort to Hawariyat Church | Civil Work | m | 0.1 |  |  |  | 0.1
|  |  | km | 0 |  |  |  | 0
|  |  | ETB | 1318048.29 |  |  |  | 1318048.29
| Rolled Asphalt median and greenery Total | Civil Work | m | 0.1 |  |  |  | 0.1
|  |  | km | 0 |  |  |  | 0
|  |  | ETB | 1318048.29 |  |  |  | 1318048.29
6 | Rolled Drainage Projects
6.1 | From Alemu Ano to Pawlos Genta | Civil Work | m | 90 |  |  |  | 90
|  |  | km | 0
|  |  | ETB | 428733.89 |  |  |  | 428733.89
| Rolled Drainage Projects Total | Civil Work | m | 90 |  |  |  | 90
|  |  | km | 0
|  |  | ETB | 428733.89 |  |  |  | 428733.89
1.7 | Solid Waste
1.7.1 | Skip loader | Goods | No |  | 0.25 | 0.5 | 0.25 | 1
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 1004650.7725 | 2009301.545 | 1004650.7725 | 4018603.09
| Solid Waste Total |  |  |  | 1004650.7725 | 2009301.545 | 1004650.7725 | 4018603.09
| Environmental Services(Rolled) Total |  |  | 6602233.42 | 1004650.7725 | 2009301.545 | 1004650.7725 | 10620836.51
| Environmental Services Total |  |  | 6602233.42 | 5138398.5 | 10276797 | 5138398.5 | 28396305.79 | 0
Others
| Pillar 7: Environmental, Green Services & Recreation Total |  |  | 6602233.42 | 5138398.5 | 10276797 | 5138398.5 | 28396305.79 | 0
Pillar 8: Resilient, Inclusive and Safer Cities
Environmental Services
1.3 | Retaining wall construction(New)
1.3.1 | Retaining wall at the side of Kulufo river phase-III | Civil Work | m |  | 62.5 | 125 | 62.5 | 250
|  |  | km |  | 0 | 0 | 0
|  |  | ETB |  | 2847156.145 | 5694312.29 | 2847156.145 | 11388624.58
| Retaining wall total | Civil Work | m |  | 62.5 | 125 | 62.5 | 250
|  |  | km |  | 0 | 0 | 0
|  |  | ETB | 0 | 2847156.145 | 5694312.29 | 2847156.145 | 11388624.58 | 0
2 | Retaining wall(Rolled)
2.1 | Konso Market to Stadium Retaining wall | Civil Work | m3 | 80 |  |  |  | 80
|  |  | km | 0
|  |  | ETB | 1383319.47 |  |  |  | 1383319.47
2.2 | Retaining wall at the side of Kulufo river phase-II | Civil Work | m3 | 250 |  |  |  | 250
|  |  | km | 0
|  |  | ETB | 9806360.5 |  |  |  | 9806360.5
| Rolled Retaining wall total | Civil Work | m | 330 |  |  |  | 330
|  |  | km | 0
|  |  | ETB | 11189679.97 | 0 | 0 | 0 | 11189679.97 | 0
| Retaining wall total |  |  | 11189679.97 | 2847156.145 | 5694312.29 | 2847156.145 | 22578304.55 | 0
| Environmental Services Total |  |  | 11189679.97 | 2847156.145 | 5694312.29 | 2847156.145 | 22578304.55 | 0
| Pillar 8: Resilient, Inclusive and Safer Cities total |  |  | 11189679.97 | 2847156.145 | 5694312.29 | 2847156.145 | 22578304.55 | 0
Municipal Administration Buildings and Other Projects which cannot be put in Pillars
A | Buildings(New)
B | Buildings(Rolled)
1 | Low cot house | Civil Work | No | 0.25 | 0.25 | 0.25 | 0.25 | 1
|  |  | km | 0 | 0 | 0 | 0
|  |  | ETB | 1000000 | 1000000 | 1000000 | 1000000 | 4000000
2 | Cadaster office building | Civil Work | No | 0.25 | 0.25 | 0.25 | 0.25 | 1
|  |  | km | 0 | 0 | 0 | 0
|  |  | ETB | 2362223 | 2362223 | 2362223 | 2362223 | 9448892
2 | Rolled One shop serveice shed building | Civil Work | No | 1 |  |  |  | 1
|  |  | km | 0
|  |  | ETB | 1500000 |  |  |  | 1500000
3 | Animal Health Center | Civil Work | No | 0.5 | 0.5 |  |  | 1
|  |  | km | 0 | 0
|  |  | ETB | 792500 | 792500 |  |  | 1585000
| Building total | Civil Work | No | 2 | 1 | 0.5 | 0.5 | 4
|  |  | km |  | 0 | 0 | 0
|  |  | ETB | 5654723 | 4154723 | 3362223 | 3362223 | 16533892 | 0
| Buildings(Rolled) total |  |  | 5654723 | 4154723 | 3362223 | 3362223 | 16533892
| Buildings Total | - |  | 5654723 | 4154723 | 3362223 | 3362223 | 16533892
Consultancy Services for designs and contract management/supervision
1
Consultancy Services for designs total
6 | Capacity building
6.1 | Local training |  |  |  | 835000 | 1048000 | 342000 | 2225000
6.2 | Office equipment |  |  |  | 2815160.02 | 0 | 0 | 2815160.02 |  | 18533892
| Capacity building |  |  | 0 | 3650160.02 | 1048000 | 342000 | 5040160.02 | 0
| Total CIP Budget |  |  | 41286852.74 | 43375741.3 | 72801939.56 | 39275081.28 | 201800326.83 | 0 | 174266434.83
192800326.83
#REF!
|  |  |  | 17636903.22 | 8629379.395 | 10104535.54 |  |  |  | 0 | 0 | 0
|  |  |  | 2815160.02 | 0 | 0 |  | 202412969.09
196739614.88

## 14. Three Year Maintenance
S/N | Infrastructure sub category | Total Cost for 3 years | Maintenance Budget for EFY 2013 | Maintenance Budget for EFY 2014 | Maintenance Budget for EFY 2015
A | Movement Network |  |  |  | - |  | 1569.432
1 | Roads |  |  |  | -
1.2 | Cobble Stone road |  |  |  | - |  | Strategic and Supportive Activity Areas | Budget for reducing the maintenance deficit | %
1.2.1 | Four sub cities cobble Stone Road Maintenance | 1655000 | 500000 | 550000 | 605000 | 151250 | The Movement Network | 7500000 | 0.44115
1.3 | Gravel Roads | 0 | 0 | 0 | 0 | 0 | Environmental Services | 5500000 | 0.32351
1.3.1 | Four sub cities gravel road Maintenance | 12586283.7715 | 3802502.65 | 4182752.915 | 4601028.2065 | 1150257.0516 | Social and Economic Services & others | 3001207.13 | 0.17653
1.4 | Asphalt Median Fence Maintenance | 1655000 | 500000 | 550000 | 605000
1.5 | Engineering machine maintenance | 4096292.3205 | 1237550.55 | 1361305.605 | 1497436.1655 | 374359.0414
| Movement Network Total | 19992576.092 | 6040053.2 | 6644058.52 | 7308464.372 | 1827116.093
B | Water Supply Network |  | 0 |  |  | 0
1 | Four sub cities water supply maintenance | 11078375.8685 | 3346941.35 | 3681635.485 | 4049799.0335 | 1012449.7584
| Water Supply total | 11078375.8685 | 3346941.35 | 3681635.485 | 4049799.0335 | 1012449.7584
C | Environmental Services |  | 3802502.65 |  |  | 0
| Environmental Services |  | 0
1 | Four sub cities masonry maintenance | 13357702.2098 | 4035559.58 | 4439115.538 | 4883027.0918 | 1220756.7729
2 | Abbatior maintenance | 1655000 | 500000 | 550000 | 605000
3 | Abbatior Fence maintenance | 993000 | 300000 | 330000 | 363000 | 90750
| Environmental Services Total | 16005702.2098 | 4835559.58 | 5319115.538 | 5851027.0918 | 1462756.7729
D | Others |  | 0 |  |  | 0
1 | Four sub cities electricity maintenance | 14771171.0464 | 4462589.44 | 4908848.384 | 5399733.2224 | 1349933.3056
2 | Other Plants and Equipments Maintenance | 4965000 | 1500000 | 1650000 | 1815000 | 453750
| Others Total | 19736171.0464 | 5962589.44 | 6558848.384 | 7214733.2224 | 1803683.3056
| Total maintenance budget | 66812825.2167 | 20185143.57 | 22203657.927 | 24424023.7197 | 6106005.9299 | 2252860
20035143.57
[5 empty] | 4388880.1497 | #REF!
22171163.7197
[5 empty] | 161467518.54 | 16146751.854
8277271.8657
Strategic and Supportive Activity Areas
The Movement Network
The Water Supply Network
Environmental Services
Social and Economic Services & others
Total budget: maintenance deficit
[5 empty] | 82549768 | 24764930.4

## 15. Maintenance action plan
S/N | Description of Activities | Physical /Financial | Unit | Implementation Period |  |  |  | Annual Total for EFY 2013
|  |  |  | Q1 | Q2 | Q3 | Q4
A | Movement Network | [6 empty] | - |  | 1569.432
1 | Roads | [6 empty] | -
1.2 | Cobble Stone road |  |  |  |  | - | - | - |  | Strategic and Supportive Activity Areas | Budget for reducing the maintenance deficit | %
1.2.1 | Four sub cities cobble Stone Road Maintenance | Physical | m2 | 1461.79 | 1461.79 | 1461.79 | 1461.79 | 5847.16 | 1461.79 | The Movement Network | 7500000 | 0.44115
|  | Financial | ETB | 125000 | 125000 | 125000 | 125000 | 500000 | 125000 | The Water Supply Network | 1000000 | 0.058819
1.3 | Gravel Roads | [6 empty] | - | #VALUE! | Environmental Services | 5500000 | 0.32351
1.3.1 | Four sub cities gravel road | Physical | km | 2 | 2 | 2 | 2 | 8 | 2 | Social and Economic Services & others | 3001207.13 | 0.17653
|  | Financial | ETB | 950625.6625 | 950625.6625 | 950625.6625 | 950625.6625 | 3802502.65 | 950625.6625 | Total budget: maintenance | 17001207.13 | 1
1.4 | Asphalt Median Fence Maintenance | Physical | km | 0.625 | 0.625 | 0.625 | 0.625 | 2.5
|  | Financial | ETB | 125000 | 125000 | 125000 | 125000 | 500000
1.5 | Engineering machine maintenance | Physical | No | 0 | 3 | 0 | 0 | 3 | 0.75
|  | Financial | ETB | 309387.6375 | 309387.6375 | 309387.6375 | 309387.6375 | 1237550.55 | 309387.6375
| Movement Network Total |  |  | 1510013.3 | 1510013.3 | 1510013.3 | 1510013.3 | 6040053.2 | 1510013.3
B | Water Supply Network |  |  | - | - | - | - | - | #VALUE!
1 | Four sub cities water supply maintenance | Physical | m | 625.25 | 625.25 | 625.25 | 625.25 | 2501 | 625.25 | 201800326.83
|  | Financial | ETB | 836735.3375 | 836735.3375 | 836735.3375 | 836735.3375 | 3346941.35 | 836735.3375 | 20180032.683
| Water Supply total |  |  | 836735.3375 | 836735.3375 | 836735.3375 | 836735.3375 | 3346941.35 | 836735.3375 | 20035143.57
C | Environmental Services |  |  | - | - | - | - | - | #VALUE! | 144889.113
1 | Four sub cities masonry maintenance | Physical | m | 137.5 | 137.5 | 137.5 | 137.5 | 550 | 137.5
|  | Financial | ETB | 1008889.895 | 1008889.895 | 1008889.895 | 1008889.895 | 4035559.58 | 1008889.895
2 | Abbatior maintenance | Physical | no | 0 | 0 | 1 | 0 | 1
|  | Financial | ETB | 125000 | 125000 | 125000 | 125000 | 500000
3 | Abbatior Fence maintenance | Physical | m | 25 | 25 | 25 | 25 | 100 | 25
|  | Financial | ETB | 75000 | 75000 | 75000 | 75000 | 300000 | 75000
| Environmental Services Total |  |  | 1208889.895 | 1208889.895 | 1208889.895 | 1208889.895 | 4835559.58 | 1208889.895
D | Others |  |  | - | - | - | - | - | #VALUE!
1 | Four sub cities electricity maintenance | Physical | m | 105 | 105 | 105 | 105 | 420 | 105
|  | Financial | ETB | 1115647.36 | 1115647.36 | 1115647.36 | 1115647.36 | 4462589.44 | 1115647.36
2 | Other Plants and Equipments Maintenance | Physical | No | 3 | 3 | 3 | 3 | 12 | 3
|  | Financial | ETB | 375000 | 375000 | 375000 | 375000 | 1500000 | 375000
| Others Total |  |  | 1490647.36 | 1490647.36 | 1490647.36 | 1490647.36 | 5962589.44 | 1490647.36
| Total maintenance budget |  |  | 5046285.8925 | 5046285.8925 | 5046285.8925 | 5046285.8925 | 20185143.57 | 5046285.8925 | 2252860
20035143.57
[8 empty] | 150000 | 424197.724
17932283.57
[7 empty] | cip | 161467518.54 | 16146751.854
4038391.716
|  |  | Strategic and Supportive Activity Areas | Budget for reducing the maintenance deficit |  | 7500000
|  |  | The Movement Network | 12264930 |  | 4764930
|  |  | The Water Supply Network | 2500000
|  |  | Environmental Services | 6000000 |  |  | 24764930
|  |  | Social and Economic Services & others | 4000000
|  |  | Total budget: maintenance deficit | 24764930
[8 empty] | 82549768 | 24764930.4

## 16. APP UIIDP
COUNTRY
Responsible Agency |  | Ministry of Urban Development & Construction
REGION |  | SNNPR Regional State
CITY ADMINISTRATION |  | Arbaminch City Administration
PROGRAM |  | URBAN INSTITUTIONAL INFRUCTURE DEVELOPMENT PROGRAM (UIIDP) IDA CR. NO.5435ET
PROCUREMENT CATEGORY/TYPE * |  | WORKS AnnualProcurement plan
BUDGET YEAR |  | ANNUAL PROCUREMENT PLAN- FOR THE YEAR | [8 empty] | 2020/2021(2013E.C)
Exchange rate ** |  | 1USD =……………ETB | [23 empty] | ETB
S.No. | Project Description | Measurement |  | Basic Data | [10 empty] | Draft Bidding Documents, including specs and quantities, draft SPN |  | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation
|  | Unit | Qty | Package Number | Lot Number | Estimated Amount in ETH. Bir | Estimated Amount for 2012 EFY in ETH. Birr | Source of Finance |  |  |  | Procurement Method | Pre-or Post Qualification | Plan vs. Actual | Prep & Submission by Ex Agency | Approval by Endorsing Committee Date | Bid Invitation Date /On-line Agency website National Press/ | Bid Closing Opening | Submission Bid Eval Rpt | Approval by Endorsing Committee Date | Contract Amount in ETH | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
[8 empty] | Government Treasury | Internal Revenue | IDA | AID |  |  |  | 1--3wks | 1 - 2 wks | 1 - 8 wks | 1day | 1--4wks | 1 --2 wks |  | 1 --2 wks | 1--3 wks | 2--4wks | As per contract | 24--52wks
UIIDP Works
Cobble stone Road Construction
1 | ASPHALT TO GETAHUN AYELE & GETAHUN LEMA TO GABALE TSARA | M2 |  | Arbaminch/UIIDP/CW-001/2020 |  | 3409056.69 | 3409056.69 | 772645.0217 | 772645.0217 | 1863766.6465 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 3409056.69 | 102271.7007 | 1 | 3306784.9893 | 3409056.69 | 3 | 3409056.69 | 85226.4172 | 3323830.2728
|  |  | 2548 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
2 | TAKELE TESEMA TO ELIYAS GAGA | M2 |  | Arbaminch/UIIDP/CW-002/2020 |  | 2158666.98 | 2158666.98 | 489250.6776 | 489250.6776 | 1180165.6247 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2158666.98 | 64760.0094 | 2 | 2093906.9706 | 2158666.98 | 4 | 2158666.98 | 53966.6745 | 2104700.3055
|  |  | 1470 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
3 | DESALEGN DATA TO MEKANEYESUS GUEST HOUSE | M2 |  | Arbaminch/UIIDP/CW-003/2020 |  | 1909901.61 | 1909901.61 | 432869.2965 | 432869.2965 | 1044163.0171 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 1909901.61 | 57297.0483 | 3 | 1852604.5617 | 1909901.61 | 5 | 1909901.61 | 47747.5402 | 1862154.0698
|  |  | 1470 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
4 | ZERIHUN ZUMA TO TESFAYE DURE | M2 |  | Arbaminch/UIIDP/CW-004/2020 |  | 2962220.34 | 2962220.34 | 671371.88 | 671371.88 | 1619476.58 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2962220.34 | 88866.6102 | 3 | 2873353.7298 | 2962220.34 | 5 | 2962220.34 | 74055.5085 | 2888164.8315
|  |  | 2310 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
5 | FROM CHICHE CHIBIRE TO TADELECH SHITAYE & LISANEWORK TO OLD BRIDGE | M2 |  | Arbaminch/UIIDP/CW-005/2020 |  | 2707345.17 | 2707345.17 | 613605.7443 | 613605.7443 | 1480133.6813 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2707345.17 | 81220.3551 | 4 | 2626124.8149 | 2707345.17 | 3 | 2707345.17 | 67683.6292 | 2639661.5408
|  |  | 2310 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
6 | FROM AREGAWIYAN TO GULCHA DOKILE & YAPA YAYA TO ZENEBE ZIDA | M2 |  | Arbaminch/UIIDP/CW-006/2020 |  | 3072009.34 | 3072009.34 | 696254.9876 | 696254.9876 | 1679499.3649 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 3072009.34 | 92160.2802 | 5 | 2979849.0598 | 3072009.34 | 4 | 3072009.34 | 76800.2335 | 2995209.1065
|  |  | 2380 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
7 | HAILEMICHAEL HALALA TO BELAYNESH MERGIYA | M2 |  | Arbaminch/UIIDP/CW-0007/2020 |  | 3285820.16 | 3285820.16 | 744714.1012 | 744714.1012 | 1796391.9575 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 3285820.16 | 98574.6048 | 6 | 3187245.5552 | 3285820.16 | 5 | 3285820.16 | 82145.504 | 3203674.656
|  |  | 2625 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
8 | ASHEBIR ASFA THROUGH ASFAW DAGNIE TO G/MEDIHIN ADINEW | M2 |  | Arbaminch/UIIDP/CW-008/2020 |  | 2235173.13 | 2235173.13 | 506590.3998 | 506590.3998 | 1221992.3303 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2235173.13 | 67055.1939 | 7 | 2168117.9361 | 2235173.13 | 3 | 2235173.13 | 55879.3282 | 2179293.8018
|  |  | 1750 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
9 | ABEBE GEZAHAGN THROUGH MENGISTU MARKA TO PETROS | M2 |  | Arbaminch/UIIDP/CW-009/2020 |  | 1687952.76 | 1687952.76 | 382565.7405 | 382565.7405 | 922821.279 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 1687952.76 | 50638.5828 | 8 | 1637314.1772 | 1687952.76 | 4 | 1687952.76 | 42198.819 | 1645753.941
|  |  | 1260 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
10 | SOLOMON CHODA TO BITANE MENZA | M2 |  | Arbaminch/UIIDP/CW-010/2020 |  | 2644387.71 | 2644387.71 | 599336.7625 | 599336.7625 | 1445714.185 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2644387.71 | 79331.6313 | 9 | 2565056.0787 | 2644387.71 | 5 | 2644387.71 | 66109.6928 | 2578278.0173
|  |  | 1890 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
11 | DAMENE TO SENODOS WOFCHO BET | M2 |  | Arbaminch/UIIDP/CW-011/2020 |  | 2943135.74 | 2943135.74 | 667046.4544 | 667046.4544 | 1609042.8312 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2943135.74 | 88294.0722 | 10 | 2854841.6678 | 2943135.74 | 3 | 2943135.74 | 73578.3935 | 2869557.3465
|  |  | 2240 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
12 | MATEYOS LOHA TO KES KETEMA, MENZA TO AWUDE AHMED & CHAIN ACADAMY TO ASNAKECH LENCHA | M2 |  | Arbaminch/UIIDP/CW-012/2020 |  | 2723883.57 | 2723883.57 | 617354.0869 | 617354.0869 | 1489175.3961 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2723883.57 | 81716.5071 | 11 | 2642167.0629 | 2723883.57 | 4 | 2723883.57 | 68097.0893 | 2655786.4808
|  |  | 2310 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
13 | HUSEN YIMER TO ASKALECH GIZACHEW, LIYU MEAZA TO NATINAEL, TAGESE CHAFO TO MEDIHANIT METASEBIYA & DESALEGN LAFAMO TO MEKONNEN | M2 |  | Arbaminch/UIIDP/CW-013/2020 |  | 3304230.95 | 3304230.95 | 748886.8113 | 748886.8113 | 1806457.3273 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 3304230.95 | 99126.9285 | 12 | 3205104.0215 | 3304230.95 | 5 | 3304230.95 | 82605.7737 | 3221625.1763
|  |  | 2590 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
14 | GETACHEW SEMERE TO ASPHALT | M2 |  | Arbaminch/UIIDP/CW-014/2020 |  | 2682562.05 | 2682562.05 | 607988.7787 | 607988.7787 | 1466584.4926 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2682562.05 | 80476.8615 | 13 | 2602085.1885 | 2682562.05 | 3 | 2682562.05 | 67064.0513 | 2615497.9987
|  |  | 2184 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
15 | BOMBOLO AGIDEW TO ASPHALT | M2 |  | Arbaminch/UIIDP/CW-015/2020 |  | 1910331.97 | 1910331.97 | 432966.8353 | 432966.8353 | 1044398.2994 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 1910331.97 | 57309.9591 | 14 | 1853022.0109 | 1910331.97 | 4 | 1910331.97 | 47758.2992 | 1862573.6708
|  |  | 1470 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
16 | MOGES W/AMANUEL TO AEMIRO ALTO & MINALU BULGO TO TULO BOYZO | M2 |  | Arbaminch/UIIDP/CW-016/2020 |  | 1910331.97 | 1910331.97 | 432966.8353 | 432966.8353 | 1044398.2994 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 1910331.97 | 57309.9591 | 14 | 1853022.0109 | 1910331.97 | 4 | 1910331.97 | 47758.2992 | 1862573.6708
|  |  | 1470 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
17 | CHALACHEW TAMIRU TO TESFAYE HAILE & BEDILU TO TIRUYE | M2 |  | Arbaminch/UIIDP/CW-017/2020 |  | 2452169.02 | 2452169.02 | 555771.3931 | 555771.3931 | 1340626.2338 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2452169.02 | 73565.0706 | 15 | 2378603.9494 | 2452169.02 | 5 | 2452169.02 | 61304.2255 | 2390864.7945
|  |  | 1890 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
18 | WANSO WASHA TO THOMAS WASHE & JINKA BER TO MULUWONGEL | M2 |  | Arbaminch/UIIDP/CW-018/2020 |  | 3079444.99 | 3079444.99 | 697940.2391 | 697940.2391 | 1683564.5118 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 3079444.99 | 92383.3497 | 16 | 2987061.6403 | 3079444.99 | 3 | 3079444.99 | 76986.1248 | 3002458.8652
|  |  | 2380 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
19 | TSIGEREDA KEBEDE TO MENGISTU WORKU & D/R TESFAYE TO TADELE YILMA | M2 |  | Arbaminch/UIIDP/CW-019/2020 |  | 3043254.7 | 3043254.7 | 689737.8975 | 689737.8975 | 1663778.905 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 3043254.7 | 91297.641 | 17 | 2951957.059 | 3043254.7 | 4 | 3043254.7 | 76081.3675 | 2967173.3325
|  |  | 2700 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
20 | LABIYAJO THROUGH TSEGAYE BEKELE TO MOLA HABTE | M2 |  | Arbaminch/UIIDP/CW-020/2020 |  | 2854440.11 | 2854440.11 | 646944.0498 | 646944.0498 | 1560552.0105 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2854440.11 | 85633.2033 | 18 | 2768806.9067 | 2854440.11 | 5 | 2854440.11 | 71361.0027 | 2783079.1072
|  |  | 2320 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
21 | MOLA HABTE THROUGH ASCHENAKI MAMO TO NEW ASPHALT | M2 |  | Arbaminch/UIIDP/CW-021/2020 |  | 3405735.48 | 3405735.48 | 771892.2867 | 771892.2867 | 1861950.9066 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 3405735.48 | 102172.0644 | 19 | 3303563.4156 | 3405735.48 | 3 | 3405735.48 | 85143.387 | 3320592.093
|  |  | 2800 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
22 | SHEWAYE MINDAYE THROUGH NEW CULVERT TO WONDWOSEN WUBAYEHU | M2 |  | Arbaminch/UIIDP/CW-022/2020 |  | 3165314.25 | 3165314.25 | 717402.0616 | 717402.0616 | 1730510.1268 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 3165314.25 | 94959.4275 | 20 | 3070354.8225 | 3165314.25 | 4 | 3165314.25 | 79132.8562 | 3086181.3937
|  |  | 2450 | [10 empty] | Revised | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
23 | TESFAYE KOIRA THROUGH ALMAZ ALEMAYEHU TO GUDELA KUSIYA | M2 |  | Arbaminch/UIIDP/CW-023/2020 |  | 2570254.38 | 2570254.38 | 582534.8276 | 582534.8276 | 1405184.7247 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2570254.38 | 77107.6314 | 21 | 2493146.7486 | 2570254.38 | 5 | 2570254.38 | 64256.3595 | 2505998.0205
|  |  | 1960 | [10 empty] | Revised | 2020-10-19: 0 | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
24 | KASAHUN GEZAHAGN TO MINJA, MINJA TO WONBERA, WONBERA TO DEBEBE LOFA | M2 |  | Arbaminch/UIIDP/CW-024/2020 |  | 2504746.3 | 2504746.3 | 567687.761 | 567687.761 | 1369370.778 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2504746.3 | 75142.389 | 21 | 2429603.911 | 2504746.3 | 5 | 2504746.3 | 62618.6575 | 2442127.6425
|  |  | 1960 | [10 empty] | Revised | 2020-10-19: 0 | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
25 | KASAHUN GEZAHAGN TO MENGISTU MEYA & ETENESH BEKELE TO DEREJE ALEMU | M2 |  | Arbaminch/UIIDP/CW-025/2020 |  | 2334729.2 | 2334729.2 | 529154.2669 | 529154.2669 | 1276420.6663 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2334729.2 | 70041.876 | 21 | 2264687.324 | 2334729.2 | 5 | 2334729.2 | 58368.23 | 2276360.97
|  |  | 1820 | [10 empty] | Revised | 2020-10-19: 0 | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
26 | ADDIS ALEMAYEHU WOFCHO BET TO DEBEBE MAMACHA | M2 |  | Arbaminch/UIIDP/CW-026/2020 |  | 1903508.31 | 1903508.31 | 431420.2882 | 431420.2882 | 1040667.7337 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 1903508.31 | 57105.2493 | 21 | 1846403.0607 | 1903508.31 | 5 | 1903508.31 | 47587.7078 | 1855920.6022
|  |  | 1620 | [10 empty] | Revised | 2020-10-19: 0 | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
27 | ABUGIYA SHILE TO YIFTUSIRA MOLA | M2 |  | Arbaminch/UIIDP/CW-027/2020 |  | 2606027.61 | 2606027.61 | 590642.6447 | 590642.6447 | 1424742.3206 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2606027.61 | 78180.8283 | 21 | 2527846.7817 | 2606027.61 | 5 | 2606027.61 | 65150.6902 | 2540876.9197
|  |  | 2160 | [10 empty] | Revised | 2020-10-19: 0 | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
28 | WADA DERE TO DEBEBE BIRHANE | M2 |  | Arbaminch/UIIDP/CW-028/2020 |  | 2484813.76 | 2484813.76 | 563170.1542 | 563170.1542 | 1358473.4517 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2484813.76 | 74544.4128 | 21 | 2410269.3472 | 2484813.76 | 5 | 2484813.76 | 62120.344 | 2422693.416
|  |  | 1869 | [10 empty] | Revised | 2020-10-19: 0 | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
29 | RAHEL KULINO TO W/RO BIRHANE KASA | M2 |  | Arbaminch/UIIDP/CW-029/2020 |  | 1870967.11 | 1870967.11 | 424044.9939 | 424044.9939 | 1022877.1222 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 1870967.11 | 56129.0133 | 21 | 1814838.0967 | 1870967.11 | 5 | 1870967.11 | 46774.1778 | 1824192.9323
|  |  | 1520 | [10 empty] | Revised | 2020-10-19: 0 | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
30 | EJIGAYEHU DEBREWORK TO MESERET ADANE | M2 |  | Arbaminch/UIIDP/CW-030/2020 |  | 2147879.8 | 2147879.8 | 486805.8192 | 486805.8192 | 1174268.1615 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07 |  | 2147879.8 | 64436.394 | 21 | 2083443.406 | 2147879.8 | 5 | 2147879.8 | 53696.995 | 2094182.805
|  |  | 1760 | [10 empty] | Revised | 2020-10-19: 0 | [7 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0
[14 empty] | Actual | [13 empty] | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | bar: 2020-10-05 to 2020-10-12; 2020-11-10 to 2020-11-17
| Cobble stone sub total |  | 61486 |  |  | 77970295.16 | 77970295.16 | 17671563.0972 | 17671563.0972 | 42627168.9656 | [10 empty] | 0 | [6 empty] | 77970295.16 | 2339108.8548 |  | 75631186.3052 | 77970295.16 |  | 77970295.16 | 1949257.379 | 76021037.781
| Massonary Drainage | [30 empty] | 0 |  |  | 0 | 0
31 | TESFAYE TEFERA TO BEZABIH WADA & AKIRSO KORA TO BONO | m | 412 | Arbaminch/UIIDP/CW-031/2020 |  | 1544014.58 | 1544014.58 | 349942.8983 | 349942.8983 | 844128.7833 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30 | [9 empty] | 0
Revised
[14 empty] | Actual | [16 empty] | 2339108.8548 | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
32 | BRIDGE TO TESFAYE WORKINEH | m | 280 | Arbaminch/UIIDP/CW-032/2020 |  | 1030416.91 | 1030416.91 | 233538.6496 | 233538.6496 | 563339.6108 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30 | [7 empty] | 389851.4758 |  |  | 1949257.379
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
33 | GEDA GAZE TO MATEYOS ASHA | m | 134 | Arbaminch/UIIDP/CW-033/2020 |  | 576882.82 | 576882.82 | 130747.4998 | 130747.4998 | 315387.8203 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
34 | GIRMA SANA TO BEKELE TADESE | m | 170 | Arbaminch/UIIDP/CW-034/2020 |  | 688277.63 | 688277.63 | 155994.5559 | 155994.5559 | 376288.5182 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
35 | DAWIT DORKE THROUGH SAMSON TO GEZMO TINKU | m | 310 | Arbaminch/UIIDP/CW-035/2020 |  | 1119713.45 | 1119713.45 | 253777.2474 | 253777.2474 | 612158.9553 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
36 | BIRKABY THROUGH ABERA MOTA TO ENDALE H/MESKEL | m | 350 | Arbaminch/UIIDP/CW-036/2020 |  | 1243485.46 | 1243485.46 | 281829.5316 | 281829.5316 | 679826.3967 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
37 | KALEB KANKO TO DIDO ABUTE | m | 130 | Arbaminch/UIIDP/CW-037/2020 |  | 566271.85 | 566271.85 | 128342.5785 | 128342.5785 | 309586.693 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
38 | YISIHAK MENA TO WONDIYIFRAW | m | 220 | Arbaminch/UIIDP/CW-038/2020 |  | 842992.65 | 842992.65 | 191059.9129 | 191059.9129 | 460872.8241 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
39 | CHAMO CAMPUS ASPHALT TO BEHAILU ABOTA | m | 220 | Arbaminch/UIIDP/CW-039/2020 |  | 842992.65 | 842992.65 | 191059.9129 | 191059.9129 | 460872.8241 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
40 | AZENEH TEKA TO GORGE & BIZUNEH BUSA TO BISAF LEMA | m | 480 | Arbaminch/UIIDP/CW-040/2020 |  | 1910208.79 | 1910208.79 | 432938.9172 | 432938.9172 | 1044330.9556 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
41 | KULIFO GREENERY SITE DITCH | m | 305 | Arbaminch/UIIDP/CW-041/2020 |  | 1240478.37 | 1240478.37 | 281147.9903 | 281147.9903 | 678182.3894 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
42 | S/R YIRGEDU MENGESHA TO SIYERE MEKURIYA | m | 300 | Arbaminch/UIIDP/CW-042/2020 |  | 2319860.77 | 2319860.77 | 525784.4143 | 525784.4143 | 1268291.9414 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
| Drainage total |  | 3311 |  |  | 13925595.93 | 13925595.93 | 3156164.1089 | 3156164.1089 | 7613267.7122 | bar: 2020-10-27
Retaining wall | bar: 2020-10-27
43 | Retaining wall at the side of Kulufo river phase-III | m | 250 | Arbaminch/UIIDP/CW-043/2020 |  | 11388624.58 | 11388624.58 | 2581172.7074 | 2581172.7074 | 6226279.1652 |  | NCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-11-11 | 2020-11-18 | 2020-11-25 |  | 2020-12-02 | 2020-12-09 | 2020-12-16 | 2021-06-14 | 2022-06-14
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-18 to 2020-11-25
| Retaining wall sub total |  | 250 | - | 0 | 11388624.58 | 11388624.58 | 2581172.7074 | 2581172.7074 | 6226279.1652
Grenery Development
44 | Public Park at the side of Kulufo river phase-IIII | m2 | 15000 | Arbaminch/UIIDP/CW-044/2020 |  | 3849873.35 | 3849873.35 | 872553.832 | 872553.832 | 2104765.6861 |  | LCB | Post | Plan | 2020-10-05 | 2020-10-12 | 2020-10-19 | 2020-11-03 | 2020-11-10 | 2020-11-17 |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07
Revised
Actual | bar: 2020-11-10 to 2020-11-17
| Grenery Development total |  | 15000 | - | 0 | 3849873.35 | 3849873.35 | 872553.832 | 872553.832 | 2104765.6861
Culvert construction
45 | HIBRET LELIMAT SCHOOL CULVERT | No | 1 | Arbaminch/UIIDP/CW-045/2020 |  | 1010619.57 | 1010619.57 | 229051.6852 | 229051.6852 | 552516.1997 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
46 | SINODOS CULVERT | No | 1 | Arbaminch/UIIDP/CW-046/2020 |  | 1203996.91 | 1203996.91 | 272879.6565 | 272879.6565 | 658237.5969 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
47 | CATHOLIC MISSION CULVERT | No | 1 | Arbaminch/UIIDP/CW-047/2020 |  | 1159160.31 | 1159160.31 | 262717.6736 | 262717.6736 | 633724.9627 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
48 | GURBA CULVERT | No | 1 | Arbaminch/UIIDP/CW-048/2020 |  | 946138.84 | 946138.84 | 214437.4621 | 214437.4621 | 517263.9159 |  | LCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-10-27 | 2020-11-03 | 2020-11-10 |  | 2020-11-17 | 2020-11-24 | 2020-12-01 | 2021-04-30 | 2022-04-30
[14 empty] | Revised | 2020-10-12: 0
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-03 to 2020-11-10
| Culvert construction Total\ |  | 4 |  |  | 4319915.63 | 4319915.63 | 979086.4774 | 979086.4774 | 2361742.6752
Bridge construction
49 | TSEGAYE H/GIORGIS BRIDGE/GEBRIEL MESHAGERIYA | No | 1 | Arbaminch/UIIDP/CW-049/2020 |  | 5065074.31 | 5065074.31 | 1147972.8283 | 1147972.8283 | 2769128.6533 |  | NCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-11-11 | 2020-11-18 | 2020-11-25 |  | 2020-12-02 | 2020-12-09 | 2020-12-16 | 2021-06-14 | 2022-06-14
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-18 to 2020-11-25
| Bridge construction Total |  |  |  |  | 5065074.31 | 5065074.31 | 1147972.8283 | 1147972.8283 | 2769128.6533
Electric Line Expansion /Transformer /
50 | SENODOS SEFER & AT THE BACK OF TEXTILE FACTORY | No | 2 | Arbaminch/UIIDP/CW-050/2020 |  | 3232455.76 | 3232455.76 | 732619.3367 | 732619.3367 | 1767217.0866 |  | DC | Post | Plan | 2019-09-30 | 2019-10-07 | NA | NA | NA | NA |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-18 to 2020-11-25
| Electric Line Expansion total |  | 2 |  |  | 3232455.76 | 3232455.76 | 732619.3367 | 732619.3367 | 1767217.0866
Street Light /solar/
51 | From Konso sefer adebabay to Admasu house and from Fish Corporation to Zone Urban Dev't Office | Km | 2.4 | Arbaminch/UIIDP/CW-051/2020 |  | 6573707.26 | 6573707.26 | 1489896.6637 | 1489896.6637 | 3593913.9326 |  | NCB | Post | Plan | 2020-09-28 | 2020-10-05 | 2020-10-12 | 2020-11-11 | 2020-11-18 | 2020-11-25 |  | 2020-12-02 | 2020-12-09 | 2020-12-16 | 2021-06-14 | 2022-06-14
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-18 to 2020-11-25
| Street Light Total |  | 2.4 |  |  | 6573707.26 | 6573707.26 | 1489896.6637 | 1489896.6637 | 3593913.9326
Water Supply Project
52 | WATER SUPPLY PROJECT AT THE BACK OF TEXTILE FACTORY | No | 1 | Arbaminch/UIIDP/CW-052/2020 |  | 1000000 | 1000000 | 226644.8147 | 226644.8147 | 546710.3706 |  | DC | Post | Plan | 2019-09-30 | 2019-10-07 | NA | NA | NA | NA |  | 2020-11-24 | 2020-12-01 | 2020-12-08 | 2021-05-07 | 2022-05-07
Revised
Actual | bar: 2020-09-28 to 2020-10-05; 2020-11-18 to 2020-11-25
| Water Supply Project Total |  | 1 |  |  | 1000000 | 1000000 | 226644.8147 | 226644.8147 | 546710.3706
| ULGDP Work |  |  |  |  | 127325541.98 | 127325541.98 | 28857673.8663 | 28857673.8663 | 69610194.2474
Rolled Works
1. Rolled Cobble Stone
1 | From Ato Dubale Dunke to S/R Yirgedu, Alemu Ano to Mewale Hitsan Block 4 | M2 |  | Arbaminch/UIIDP/CW-044/2019 |  | 2353222.57 | 2353222.57 | 536885.858 | 536885.858 | 1279450.8539 |  | LCB | Post | Plan | 2019-10-14 | 2019-10-21 | 2020-03-26 | 2020-04-10 | 2020-04-16 | 2020-04-23 |  | 2020-04-29 | 2020-05-04 | 2020-05-08 | 2020-07-03 | 2021-07-03
|  |  | 3745 | [10 empty] | Revised | [6 empty] | 2353222.57 |  |  |  | 2020-10-10 | 2021-10-10 |  | 2353222.57
[14 empty] | Actual | 2019-10-14 | 2019-10-21 | 2020-03-30 | 2020-04-14 | 2020-04-17 | 2020-04-23 |  | 2020-05-06 | 2020-05-07 | 2020-05-08 |  |  |  | 0
2 | From Endezihnew Kasaye to Wushu Pension | M2 |  | Arbaminch/UIIDP/CW-005/2019 |  | 653712.95 | 653712.95 | 149144.0897 | 149144.0897 | 355424.7706 |  | LCB | Post | Plan | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-12 | 2019-12-03 | 2019-12-10 |  | 2019-12-17 | 2019-12-30 | 2020-01-04 | 2020-05-03 | 2021-05-03 |  | 0
|  |  | 70 | [10 empty] | Revised | [6 empty] | 1931915.31 |  |  |  | 2020-10-10 | 2021-10-10 | 1278202.36 | 653712.95
[14 empty] | Actual | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-12 | 2019-12-03 | 2019-12-10 |  | 2019-12-17 | 2019-12-26 | 2020-01-06 |  |  |  | 0
3 | From Eyob Kurka to Gida Gita | M2 |  | Arbaminch/UIIDP/CW-006/2019 |  | 674018.23 | 674018.23 | 153776.7232 | 153776.7232 | 366464.7836 |  | LCB | Post | Plan | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-12 | 2019-12-03 | 2019-12-10 |  | 2019-12-17 | 2019-12-30 | 2020-01-04 | 2020-05-03 | 2021-05-03 |  | 0
|  |  | 140 | [10 empty] | Revised | [6 empty] | 2706749.21 |  |  |  | 2020-10-10 | 2021-10-10 | 2032730.98 | 674018.23
[14 empty] | Actual | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-12 | 2019-12-03 | 2019-12-10 |  | 2019-12-17 | 2019-12-26 | 2020-01-06 |  |  |  | 0
4 | From Lukas Woga to Dr. Melkamu Biniyam | M2 |  | Arbaminch/UIIDP/CW-007/2019 |  | 552825.18 | 552825.18 | 126126.6252 | 126126.6252 | 300571.9296 |  | LCB | Post | Plan | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-12 | 2019-12-03 | 2019-12-10 |  | 2019-12-17 | 2019-12-30 | 2020-01-04 | 2020-05-03 | 2021-05-03 |  | 0
|  |  | 70 | [10 empty] | Revised | [6 empty] | 1910739.55 |  |  |  | 2020-10-10 | 2021-10-10 | 1357914.37 | 552825.18
[14 empty] | Actual | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-12 | 2019-12-03 | 2019-12-10 |  | 2019-12-17 | 2019-12-26 | 2020-01-06 |  |  |  | 0
5 | From Mesfin Albo to W/ro Tsehay house | M2 |  | Arbaminch/UIIDP/CW-015/2019 |  | 521796.62 | 521796.62 | 119047.4839 | 119047.4839 | 283701.6522 |  | LCB | Post | Plan | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-12 | 2019-12-03 | 2019-12-10 |  | 2019-12-17 | 2019-12-30 | 2020-01-04 | 2020-05-03 | 2021-05-03 |  | 0
|  |  | 70 | [10 empty] | Revised | [6 empty] | 1614090.43 |  |  |  | 2020-10-10 | 2021-10-10 | 1092293.81 | 521796.62
[14 empty] | Actual | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-12 | 2019-12-03 | 2019-12-10 |  | 2019-12-17 | 2019-12-26 | 2020-01-06 |  |  |  | 0
6 | From Tefera Bizuneh to Almaz Gergeda | M2 |  | Arbaminch/UIIDP/CW-020/2019 |  | 419452.44 | 419452.44 | 95697.7406 | 95697.7406 | 228056.9587 |  | LCB | Post | Plan | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-12 | 2019-12-03 | 2019-12-10 |  | 2019-12-17 | 2019-12-30 | 2020-01-04 | 2020-05-03 | 2021-05-03 |  | 0
|  |  | 70 | [10 empty] | Revised | [6 empty] | 1713255.59 |  |  |  | 2020-10-10 | 2021-10-10 | 1293803.15 | 419452.44
[14 empty] | Actual | 2019-10-14 | 2019-10-21 | 2019-10-28 | 2019-11-12 | 2019-12-03 | 2019-12-10 |  | 2019-12-17 | 2019-12-26 | 2020-01-06 |  |  |  | 0
7 | Shaleka Debebe Sisay to New Asphalt | M2 |  | Arbaminch/UIIDP/CW-010/2018 |  | 475911.75 | 475911.75 | 108578.8873 | 108578.8873 | 258753.9754 |  | LCB | Post | Plan | 2018-10-16 | 2018-10-23 | 2018-10-30 | 2018-11-14 | 2018-11-28 | 2018-12-05 |  | 2018-12-19 | 2019-01-02 | 2019-01-09 | 2019-06-08 | 2020-06-07 |  | 0
|  |  | 35 | [10 empty] | Revised | [6 empty] | 3653870 |  |  |  | 2020-10-10 | 2021-10-10 | 3177958.25 | 475911.75
[14 empty] | Actual | 2018-10-16 | 2018-11-20 | 2019-03-07 | 2019-03-22 | 2019-03-27 | 2019-04-01 |  | 2019-04-08 | 2019-04-08 | 2019-04-13 |  |  |  | 0
| Rolled Cobble Stone Total |  | 4200 |  |  | 5650939.74 | 5650939.74 | 1289257.408 | 1289257.408 | 3072424.924 | [10 empty] | 15883842.66 | [5 empty] | 10232902.92 | 5650939.74
Rolled Masonry Drainage
1 | From Alemu Ano to Pawlos Genta | m | 90 | Arbaminch/UIIDP/CW-045/2019 |  | 428733.89 | 428733.89 | 97815.2961 | 97815.2961 | 233103.2979 |  | LCB | Post | Plan | 2019-10-14 | 2019-10-21 | 2020-03-26 | 2020-04-10 | 2020-04-16 | 2020-04-23 |  | 2020-04-29 | 2020-05-04 | 2020-05-08 | 2020-07-03 | 2021-07-03 | 471176.67
[14 empty] | Revised | [6 empty] | 899910.56 |  |  |  | 2020-10-10 | 2021-10-10
[14 empty] | Actual | 2019-10-14 | 2019-10-21 | 2020-03-30 | 2020-04-14 | 2020-04-17 | 2020-04-23 |  | 2020-05-06 | 2020-05-07 | 2020-05-08
| Rolled Masonry Drainage Total |  | 90 | - | 0 | 428733.89 | 428733.89 | 97815.2961 | 97815.2961 | 233103.2979 | [10 empty] | 899910.56 | [5 empty] | 471176.67 | 428733.89
Rolled Retaining Wall
1 | Konso Market to Stadium Retaining wall | m | 80 | Arbaminch/UIIDP/CW-026/2019 |  | 1383319.47 | 1383319.47 | 315603.237 | 315603.237 | 752112.9959 |  | LCB | Post | Plan | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-12-04 | 2019-12-11 | 2019-12-18 |  | 2019-12-25 | 2020-01-06 | 2020-01-16 | 2020-05-15 | 2021-05-15 | 2513070.74
[14 empty] | Revised | [6 empty] | 3896390.21 |  |  |  | 2020-10-10 | 2021-10-10 |  | 1383319.47
[14 empty] | Actual | 2019-11-04 | 2019-11-11 | 2019-12-24 | 2020-01-15 | 2020-01-27 | 2020-02-06 |  | 2020-02-17 | 2020-02-24 | 2020-05-05
2 | Retaining wall at the side of Kulufo river phase-II | m | 250 | Arbaminch/UIIDP/CW-025/2019 |  | 9806360.5 | 9806360.5 | 2237313.3499 | 2237313.3499 | 5331733.8001 |  | LCB | Post | Plan | 2019-11-18 | 2019-11-25 | 2020-03-12 | 2020-04-02 | 2020-04-09 | 2020-04-16 |  | 2020-04-23 | 2020-04-30 | 2020-05-04 | 2020-07-03 | 2021-07-03
[14 empty] | Revised | [6 empty] | 9806360.5 |  |  |  | 2020-11-14 | 2021-11-14
[14 empty] | Actual | 2019-11-18 | 2019-11-25 | 2020-03-12 | 2020-04-02 | 2020-05-07 | 2020-05-08 |  | 2020-06-16 | 2020-06-16 | 2020-06-17
| Rolled Retaining Wall Total |  | 330 | - | 0 | 11189679.97 | 11189679.97 | 2552916.587 | 2552916.587 | 6083846.796 | [10 empty] | 13702750.71 | [5 empty] | 2513070.74
Rolled Greenery Protection Fence
1 | From Referral Hospital to Lemlem Square phase-II | Km | 0.05 | Arbaminch/UIIDP/CW-027/2019 |  | 630392.95 | 630392.95 | 143823.6502 | 143823.6502 | 342745.6495 |  | LCB | Post | Plan | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-12-04 | 2019-12-11 | 2019-12-18 | 1374076.87 | 2019-12-25 | 2020-01-06 | 2020-01-16 | 2020-05-15 | 2021-05-15 | 743683.92
[14 empty] | Revised | [10 empty] | 2020-10-10 | 2021-10-10
[14 empty] | Actual | 2019-11-04 | 2019-11-11 | 2020-01-28 | 2020-02-12 | 2020-02-21 | 2020-03-03 |  | 2020-03-11 | 2020-03-17 | 2020-03-20
| Rolled Greenery Protection Fence total |  | 0.05 | - | 0 | 630392.95 | 630392.95 | 143823.6502 | 143823.6502 | 342745.6495 | [10 empty] | 1374076.87 | [5 empty] | 743683.92 | 630392.95
Rolled Asphalt Median Development
1 | From Haile Resort to Hawariyat Church | Km | 0.1 | Arbaminch/UIIDP/CW-030/2019 |  | 1318048.29 | 1318048.29 | 300711.6692 | 300711.6692 | 716624.9515 |  | LCB | Post | Plan | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-12-04 | 2019-12-11 | 2019-12-18 | 3378865.36 | 2019-12-25 | 2020-01-06 | 2020-01-16 | 2020-05-15 | 2021-05-15 | 2060817.07
[14 empty] | Revised | [10 empty] | 2020-10-10 | 2021-10-10
[14 empty] | Actual | 2019-11-04 | 2019-11-11 | 2020-01-28 | 2020-02-12 | 2020-02-21 | 2020-03-03 |  | 2020-03-11 | 2020-03-17 | 2020-03-20
| Rolled Asphalt Median Development total |  | 0.1 | - | 0 | 1318048.29 | 1318048.29 | 300711.6692 | 300711.6692 | 716624.9515 | [10 empty] | 3378865.36 | [5 empty] | 2060817.07 | 1318048.29
Rolled Grenery Development
1 | Public Park at the side of Kulufo river phase-III | m2 | 18000 | Arbaminch/UIIDP/CW-029/2019 |  | 3498963.64 | 3498963.64 | 798285.7721 | 798285.7721 | 1902392.0959 |  | LCB | Post | Plan | 2019-11-04 | 2019-11-11 | 2020-03-16 | 2020-03-31 | 2020-04-07 | 2020-04-15 | 3498963.64 | 2020-04-27 | 2020-05-04 | 2020-05-08 | 2020-08-06 | 2021-08-06
[14 empty] | Revised | [10 empty] | 2020-10-10 | 2021-10-10
[14 empty] | Actual | 2019-11-04 | 2019-11-11 | 2020-03-23 | 2020-04-07 | 2020-04-15 | 2020-04-24 |  | 2020-05-07 | 2020-05-19 | 2020-05-27
2 | Omo Hall Compound Greenary Development phase-II | M2 | 4000 | Arbaminch/UIIDP/CW-028/2019 |  | 726094.65 | 726094.65 | 165657.917 | 165657.917 | 394778.816 |  | LCB | Post | Plan | 2019-11-04 | 2019-11-11 | 2020-03-16 | 2020-03-31 | 2020-04-07 | 2020-04-15 | 1299999.79 | 2020-04-27 | 2020-05-04 | 2020-05-08 | 2020-08-06 | 2021-08-06 | 573905.14
[14 empty] | Revised | [10 empty] | 2020-10-10 | 2021-10-10
[14 empty] | Actual | 2019-11-04 | 2019-11-11 | 2020-03-23 | 2020-04-07 | 2020-04-15 | 2020-04-24 |  | 2020-05-07 | 2020-05-17 | 2020-05-18
| Rolled Grenery Development total |  | 22000 | - | 0 | 4225058.29 | 4225058.29 | 963943.689 | 963943.689 | 2297170.9119 | [10 empty] | 4798963.43 | [5 empty] | 573905.14 | 4225058.29
Rolled Culvert & Bridge construction
1 | Chamo Campus University Fence Culvert | No | 1 | Arbaminch/UIIDP/CW-032/2019 |  | 539035.66 | 539035.66 | 122980.5572 | 122980.5572 | 293074.5456 |  | LCB | Post | Plan | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-12-04 | 2019-12-11 | 2019-12-18 |  | 2019-12-25 | 2020-01-06 | 2020-01-16 | 2020-05-15 | 2021-05-15 | 724585.32
[14 empty] | Revised | [6 empty] | 1263620.98 |  |  |  | 2020-10-10 | 2021-10-10 |  | 539035.66
[14 empty] | Actual | 2019-11-04 | 2019-11-11 | 2019-12-24 | 2020-01-15 | 2020-01-27 | 2020-02-06 |  | 2020-02-17 | 2020-02-24 | 2020-05-05 |  |  |  | 0
2 | Sebsibe Haile Culvert | No | 1 | Arbaminch/UIIDP/CW-033/2019 |  | 901281.57 | 901281.57 | 205626.6735 | 205626.6735 | 490028.223 |  | LCB | Post | Plan | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-12-04 | 2019-12-11 | 2019-12-18 |  | 2019-12-25 | 2020-01-06 | 2020-01-16 | 2020-05-15 | 2021-05-15 | 446722.56 | 0
[14 empty] | Revised | [6 empty] | 1348004.13 |  |  |  | 2020-10-10 | 2021-10-10 |  | 901281.57
[14 empty] | Actual | 2019-11-04 | 2019-11-11 | 2019-12-24 | 2020-01-15 | 2020-01-27 | 2020-02-06 |  | 2020-02-17 | 2020-02-24 | 2020-05-05 |  |  |  | 1440317.23
3 | Dawit Dage to Ashewa Mado Bridge | No | 1 | Arbaminch/UIIDP/CW-036/2019 |  | 7998959.38 | 7998959.38 | 1824956.2217 | 1824956.2217 | 4349046.9366 |  | LCB | Post | Plan | 2019-11-18 | 2019-11-25 | 2020-03-12 | 2020-04-02 | 2020-04-09 | 2020-04-16 |  | 2020-04-23 | 2020-04-30 | 2020-05-04 | 2020-07-03 | 2021-07-03
[14 empty] | Revised | [6 empty] | 7998959.38 |  |  |  | 2020-11-14 | 2021-11-14
[14 empty] | Actual | 2019-11-18 | 2019-11-25 | 2020-03-12 | 2020-04-02 | 2020-05-07 | 2020-05-08 |  | 2020-06-16 | 2020-06-16 | 2020-06-17
| Rolled Culvert construction total |  | 3 | - | 0 | 9439276.61 | 9439276.61 | 2153563.4524 | 2153563.4524 | 5132149.7053 | 0 | [9 empty] | 10610584.49 | [5 empty] | 1171307.88
| Rolled Works Total |  |  |  |  | 32882129.74 | 32882129.74 | 7502031.7519 | 7502031.7519 | 17878066.2361 | [10 empty] | 50648994.08 | 0 | 0 | 0 | 0 | 0 | 17766864.34 | 32882129.74
| ULGDP Work Total |  |  |  |  | 160207671.72 | 160207671.72 | 36359705.6182 | 36359705.6182 | 87488260.4835
160207671.72
[6 empty] | 9018603.09 | 9018603.09
[6 empty] | 5040160.02 | 5040160.02 | 1142326.1337 | 1142326.1337 | 2755507.7526
|  |  |  | 41900732.83 |  | 14058763.11 |  | 30000000 | 30000000 | 72365702
174266434.83
[9 empty] | UIIDP NEW | 132365702
[9 empty] | UIIDP ROLLED | 41900732.83
[9 empty] | STATE | 14085000
[9 empty] | MUNICIPAL | 13448892
201800326.83
Formulas:
Date Contract Award = [Approval by Endorsing Committee Date]+7
Date Contract Signature = [Date Contract Award]+7
Contract Implementation = [Date Contract Signature]+7
Substantial Completion = [Contract Implementation]+150
Substantial Completion = [Contract Implementation, row below]+150
Final Acceptance = [Substantial Completion]+365

## State projects APP
COUNTRY |  | Federal Democratic Republic of Ethiopia
Responsible Agency |  | Ministry of Urban Development &Construction
REGION |  | SNNPR Regional State
CITY ADMINISTRATION |  | Arbaminch City Administration
PROGRAM |  | URBAN INSTITUTIONAL INFRUCTURE DEVELOPMENT PROGRAM (UIIDP) IDA CR. NO.5435ET
PROCUREMENT CATEGORY/TYPE * |  | WORKS AnnualProcurement plan
BUDGET YEAR |  | ANNUAL PROCUREMENT PLAN- FOR THE YEAR | [8 empty] | 2020/2021(2013E.C)
Exchange rate ** |  | 1USD =……………ETB | [23 empty] | ETB |  | #REF!
S.No. | Project Description | Measurement |  | Basic Data | [10 empty] | Draft Bidding Documents, including specs and quantities, draft SPN |  | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation
|  | Unit | Qty | Package Number | Lot Number | Estimated Amount in ETH. Birr | Estimated Amount for 2013 EFY in ETH. Birr | Source of Finance |  |  |  | Procurement Method | Pre-or Post Qualification | Plan vs. Actual | Prep & Submission by Ex Agency | Approval by Endorsing Committee Date | Bid Invitation Date /On-line Agency website National Press/ | Bid Closing Opening | Submission Bid Eval Rpt | Approval by Endorsing Committee Date | Contract Amount in ETH | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
[8 empty] | Government Treasury | Internal Revenue | IDA | AID |  |  |  | 1--3wks | 1 - 2 wks | 1 - 8 wks | 1day | 1--4wks | 1 --2 wks |  | 1 --2 wks | 1--3 wks | 2--4wks | As per contract | 24--52wks
State Non UIIDP Works
New Projects
| New Projects Total | [5 empty] | 0 | 0 | 0 | 0 | 0
Rolled Projects
1 | Gamo square construction | No | 1 | Arbaminch/Non UIIDP/CW-048/2018 |  | 44442813.77 | 11000000 |  | 11000000 |  |  | NCB | Post | Plan | 2018-10-08 | 2018-10-15 | 2018-10-22 | 2018-11-21 | 2018-12-05 | 2018-12-12 | 43067111.5 | 2018-12-26 | 2019-01-09 | 2019-01-16 | 2019-04-16 | 2020-04-15 | 13587860.7
[14 empty] | Revised | [10 empty] | 2021-06-29 | 2022-06-29
[14 empty] | Actual | 2018-10-08 | 2018-10-15 | 2018-11-19 | 2018-12-05 | 2018-12-17 | 2019-01-01 |  | 2019-01-10 | 2019-01-14 | 2019-04-06
2 | Animal Health Center | No | 1 | Arbaminch/State/CW-043/2018 |  | 1800000 | 1585000 |  | 1585000 |  |  | NCB | Post | Plan | 2019-11-04 | 2019-11-11 | 2019-11-18 | 2019-12-03 | 2019-12-24 | 2019-12-31 | 1815818.43 | 2020-01-07 | 2020-01-14 | 2020-01-17 | 2020-05-16 | 2021-05-16
[14 empty] | Revised | [10 empty] | 2021-07-07 | 2022-07-07
[14 empty] | Actual | 2019-11-04 | 2019-11-11 | 2020-05-07 | 2020-05-29 | 2020-06-22 | 2020-06-30 |  | 2020-07-03 | 2020-07-06 | 2020-07-08
3 | Rolled One shop serveive shade building | No | 1 | Arbaminch/Non UIIDP/CW-038/2017 |  | 4000000 | 1500000 |  | 1500000 |  |  | LCB | Post | Plan | 2017-10-22 | 2017-10-29 | 2017-11-05 | 2017-11-20 | 2017-12-04 | 2017-12-11 | 3956175.89 | 2017-12-25 | 2018-01-08 | 2018-01-15 | 2018-06-14 | 2019-06-14 | 2000000
[14 empty] | Revised | [10 empty] | 2020-07-07 | 2021-07-07
[14 empty] | Actual | 2018-01-08 | 2018-01-15 | 2018-01-29 | 2018-02-13 | 2018-02-20 | 2018-02-27 |  | 2018-03-13 | 2018-03-27 | 2018-04-03
| Rolled Projects Total | [5 empty] | 14085000 | 0 | 14085000 | 0 | 0 | [9 empty] | 47023287.39 | [5 empty] | 15587860.7
| State Projects Total | [5 empty] | 14085000 |  | 14085000
8613422.3
514354.78
Formulas:
Date Contract Award = [Approval by Endorsing Committee Date]+14
Date Contract Signature = [Date Contract Award]+14
Contract Implementation = [Date Contract Signature]+7
Substantial Completion = [Contract Implementation]+90
Final Acceptance = [Substantial Completion]+365

## Municipal Projects APP
COUNTRY |  | Federal Democratic Republic of Ethiopia
Responsible Agency |  | Ministry of Urban Development & Construction
REGION |  | SNNPR Regional State
CITY ADMINISTRATION |  | Arbaminch City Administration
PROGRAM |  | URBAN INSTITUTIONAL INFRUCTURE DEVELOPMENT PROGRAM (UIIDP) IDA CR. NO.5435ET
PROCUREMENT CATEGORY/TYPE * |  | WORKS AnnualProcurement plan
BUDGET YEAR |  | ANNUAL PROCUREMENT PLAN- FOR THE YEAR | [8 empty] | 2020/2021(2013E.C)
Exchange rate ** |  | 1USD =……………ETB | [23 empty] | ETB |  | #REF!
S.No. | Project Description | Measurement |  | Basic Data | [10 empty] | Draft Bidding Documents, including specs and quantities, draft SPN |  | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation
|  | Unit | Qty | Package Number | Lot Number | Estimated Amount in ETH. Birr | Estimated Amount for 2012 EFY in ETH. Birr | Source of Finance |  |  |  | Procurement Method | Pre-or Post Qualification | Plan vs. Actual | Prep & Submission by Ex Agency | Approval by Endorsing Committee Date | Bid Invitation Date /On-line Agency website National Press/ | Bid Closing Opening | Submission Bid Eval Rpt | Approval by Endorsing Committee Date | Contract Amount in ETH | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
[8 empty] | Government Treasury | Internal Revenue | IDA | AID |  |  |  | 1--3wks | 1 - 2 wks | 1 - 8 wks | 1day | 1--4wks | 1 --2 wks |  | 1 --2 wks | 1--3 wks | 2--4wks | As per contract | 24--52wks
Municipal Non UIIDP Works
| Municipal Non UIIDP Works total | [5 empty] | 0 | 0 | 0 | 0 | 0
Roller Municipal Project
1 | Low cot house | No | 16 | Arbaminch/Non UIIDP/CW-040/2019 |  | 11300000 | 4000000 |  | 4000000 |  |  | NCB | Post | Plan | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-14 | 2020-04-21 | 2020-04-28 |  | 2020-05-06 | 2020-05-11 | 2020-05-15 | 2020-07-14 | 2021-07-14
[14 empty] | Revised | [6 empty] | 11269023.08 |  |  |  | 2021-06-29 | 2022-06-29
[14 empty] | Actual | 2020-03-16 | 2020-03-23 | 2020-05-07 | 2020-05-29 | 2020-06-03 | 2020-06-20 |  | 2020-06-23 | 2020-06-26 | 2020-06-29
2 | Cadaster office building | No | 1 | Arbaminch/Non UIIDP/CW-041/2019 |  | 55000000 | 9448892 |  | 9448892 |  |  | NCB | Post | Plan | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-14 | 2020-04-21 | 2020-04-28 |  | 2020-05-06 | 2020-05-11 | 2020-05-15 | 2020-07-14 | 2021-07-14
[14 empty] | Revised | [6 empty] | 56314629.28 |  |  |  | 2021-06-29 | 2022-06-29
[14 empty] | Actual | 2019-11-18 | 2019-11-25 | 2020-02-14 | 2020-03-13 | 2020-03-24 | 2020-06-12 |  | 2020-06-15 | 2020-06-17 | 2020-06-19
| Total |  |  |  |  | 66300000 | 13448892 | 0 | 13448892 | 0
| Total municipal Work |  |  |  |  | 66300000 | 13448892 | 0 | 13448892
Formulas:
Final Acceptance = [Substantial Completion]+365

## Goods APP
COUNTRY |  | Federal Democratic Republic of Ethiopia -
Responible Agency |  | Ministry of Urban Development & Construction
REGION |  | SNNPR REGIONAL STATE
CITY ADMINISTRATION/ULG |  | Arbaminch City Administration
PROGRAM |  | URBAN INSTITUTIONAL INFRUCTURE DEVELOPMENT PROGRAM (UIIDP) IDA CR. NO.5435ET
PROCUREMENT CATEGORY/TYPE * |  | Goods Annual procurement plan
BUDGET YEAR |  | ANNUAL PROCUREMENT PLAN- FOR THE YEAR | [7 empty] | 2020/2021(2013E.C)
Exchange rate ** |  | 1USD =……………ETB
|  | Measurement |  | Basic data | [9 empty] | Bidding Documents, including specs and quantities, Draft SPN |  | Spec Proc Notice /Advertisement |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation
No. | Procurement Description | Unit | Quantity | Package Number | Lot Number | Estimated Amount ETB | Source of Finance |  |  |  | Procurement method | Pre-or Post Qualification | Plan vs. Actual | Prep & Submission by Ex Agency | Approval by Endorsing Committee Date | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | Approval by Endorsing Committee Date | Contract Amount ETH. | Date Contract Award | Date Contract Signature | Mobilization/ Advance Payment | Opening Letter of Credit | Arrival of Goods | Inspection Final Acceptance
[7 empty] | Government Treasury | Internal Revenue | IDA | AID |  |  |  | 1--6 wks | 1 - 2 wks | 2--6wks | 1day | 1 --4 wks | 1--2wks | 1--3 wks | 1--2wks | 1--4wks | 1wk | 1--4wks | 0--16wks | 0--4wks
1 | Vehicles
1.1 | Abbiator car | No | 1 | Arbaminch/UIIDP/G-001/2019 |  | 5000000 | 1140746.0239 | 1140746.0239 | 2718507.9521 |  | NCB | Post | Plan | 2020-10-07 | 2020-10-14 | 2020-10-21 | 2020-11-20 | 2020-12-04 | 2020-12-11 |  | 2020-12-18 | 2020-12-25 | 2021-01-01 | 2021-12-31 | 2022-12-31
Revised
Actual | bar: 2020-10-07 to 2020-10-14; 2020-12-04 to 2020-12-11
1.2 | Skip Loader | No | 1 | Arbaminch/UIIDP/G-002/2019 |  | 4018603.09 | 916841.0993 | 916841.0993 | 2184920.8913 |  | NCB | Post | Plan | 2020-10-07 | 2020-10-14 | 2020-10-21 | 2020-11-20 | 2020-12-04 | 2020-12-11 |  | 2020-12-18 | 2020-12-25 | 2021-01-01 | 2021-12-31 | 2022-12-31
Revised
Actual | bar: 2020-10-07 to 2020-10-14; 2020-12-04 to 2020-12-11
| Sub total |  |  |  |  | 9018603.09 | 2057587.1233 | 2057587.1233 | 4903428.8434
2 | Equipments
2.1 | Motor Bike | No | 9 | Arbaminch/UIIDP/G-001/2020 |  | 900000 | 203980.3332 | 203980.3332 | 492039.3336 |  | NCB |  | Plan | 2020-09-22 | 2020-10-06 | 2020-10-21 | 2020-11-06 | 2020-11-13 | 2020-11-20 |  | 2020-11-27 | 2020-12-09 | 2020-12-16 | NA | 2020-12-23 | 2021-01-07
Revised
Actual
2.2 | Video Camera | No | 1 |  |  | 300162.02 | 68030.1654 | 68030.1654 | 164101.6892 |  | NCB |  | Plan | 2020-09-22 | 2020-10-06 | 2020-10-21 | 2020-11-06 | 2020-11-13 | 2020-11-20 |  | 2020-11-27 | 2020-12-09 | 2020-12-16 | NA | 2020-12-23 | 2021-01-07
Revised
Actual
2.3 | Desktop Computer | No | 19 |  |  | 285000 | 64593.7722 | 64593.7722 | 155812.4556 |  | NCB |  | Plan | 2020-09-22 | 2020-10-06 | 2020-10-21 | 2020-11-06 | 2020-11-13 | 2020-11-20 |  | 2020-11-27 | 2020-12-09 | 2020-12-16 | NA | 2020-12-23 | 2021-01-07
Revised
Actual
2.4 | Laptop Computer | No | 19 |  |  | 570000 | 129187.5444 | 129187.5444 | 311624.9113 |  | NCB |  | Plan | 2020-09-22 | 2020-10-06 | 2020-10-21 | 2020-11-06 | 2020-11-13 | 2020-11-20 |  | 2020-11-27 | 2020-12-09 | 2020-12-16 | NA | 2020-12-23 | 2021-01-07
Revised
Actual
2.5 | Black Printer | No | 19 |  |  | 285000 | 64593.7722 | 64593.7722 | 155812.4556 |  | NCB |  | Plan | 2020-09-22 | 2020-10-06 | 2020-10-21 | 2020-11-06 | 2020-11-13 | 2020-11-20 |  | 2020-11-27 | 2020-12-09 | 2020-12-16 | NA | 2020-12-23 | 2021-01-07
Revised
Actual
2.6 | Photocopy Machin | No | 5 |  |  | 150000 | 33996.7222 | 33996.7222 | 82006.5556 |  | NCB |  | Plan | 2020-09-22 | 2020-10-06 | 2020-10-21 | 2020-11-06 | 2020-11-13 | 2020-11-20 |  | 2020-11-27 | 2020-12-09 | 2020-12-16 | NA | 2020-12-23 | 2021-01-07
Revised
Actual
| Sub total |  |  |  |  | 2490162.02 | 564382.3096 | 564382.3096 | 1361397.4009
3 | Furniture
3.1 | Tables | No | 8 | Arbaminch/UIIDP/G-002/2020 |  | 84000 | 19038.1644 | 19038.1644 | 45923.6711 |  | LCB |  | Plan | 2020-09-22 | 2020-10-06 | 2020-10-21 | 2020-11-06 | 2020-11-13 | 2020-11-20 |  | 2020-11-27 | 2020-12-09 | 2020-12-16 | NA | 2020-12-23 | 2021-01-07
Revised
Actual
3.2 | Shelf | No | 10 |  |  | 140000 | 31730.2741 | 31730.2741 | 76539.4519 |  | LCB |  | Plan | 2020-09-22 | 2020-10-06 | 2020-10-21 | 2020-11-06 | 2020-11-13 | 2020-11-20 |  | 2020-11-27 | 2020-12-09 | 2020-12-16 | NA | 2020-12-23 | 2021-01-07
Revised
Actual
3.3 | Managerial Chair | No | 9 |  |  | 100000 | 22664.4815 | 22664.4815 | 54671.0371 |  | LCB |  | Plan | 2020-09-22 | 2020-10-06 | 2020-10-21 | 2020-11-06 | 2020-11-13 | 2020-11-20 |  | 2020-11-27 | 2020-12-09 | 2020-12-16 | NA | 2020-12-23 | 2021-01-07
Revised
Actual
3.4 | Single Chair | no | 10 |  |  | 72000 | 16318.4267 | 16318.4267 | 39363.1467 |  | NCB | Post | Plan | 2020-09-22 | 2020-10-06 | 2020-10-21 | 2020-11-06 | 2020-11-13 | 2020-11-20 |  | 2020-11-27 | 2020-12-09 | 2020-12-16 | NA | 2020-12-23 | 2021-01-07
Revised
Actual
| Sub total |  |  |  |  | 396000 | 89751.3466 | 89751.3466 | 216497.3068
| Goods total |  |  |  |  | 11904765.11 | 2711720.7795 | 2711720.7795 | 6481323.5511
[6 empty] | 2814162.02 | 637815.2295 | 637815.2295 | 1538531.561 |  | 11904765.11
9018603.09
[6 empty] | 1171000 |  | 2814162.02 |  |  | 2886162.02
[6 empty] | #REF! |  | #REF!
2886162.02
Formulas:
Date Contract Award = [Approval by Endorsing Committee Date]+7
Date Contract Signature = [Date Contract Award]+7
Contract Implementation = [Date Contract Signature]+7
Arrival of Goods = [Opening Letter of Credit]+365
Inspection Final Acceptance = [Arrival of Goods]+15

## Maintenance APP
COUNTRY |  | Federal Democratic Republic of Ethiopia
Responsible Agency |  | Ministry of Urban Development & Construction
REGION |  | SNNPR Regional State
CITY ADMINISTRATION |  | Arbaminch City Administration
PROGRAM |  | URBAN INSTITUTIONAL INFRUCTURE DEVELOPMENT PROGRAM (UIIDP) IDA CR. NO.5435ET
PROCUREMENT CATEGORY/TYPE * |  | WORKS AnnualProcurement plan
BUDGET YEAR |  | ANNUAL PROCUREMENT PLAN- FOR THE YEAR | [6 empty] | 2020/2021(2013E.C)
Exchange rate ** |  | 1USD =……………ETB | [21 empty] | ETB |  | #REF!
S.No. | Project Description | Measurement |  | Basic Data | [8 empty] | Draft Bidding Documents, including specs and quantities, draft SPN |  | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  | Contract Implementation
|  | Unit | Qty | Package Number | Estimated Amount in ETH. Birr | Source of Finance |  |  |  | Procurement Method | Pre-or Post Qualification | Plan vs. Actual | Prep & Submission by Ex Agency | Approval by Endorsing Committee Date | Bid Invitation Date /On-line Agency website National Press/ | Bid Closing Opening | Submission Bid Eval Rpt | Approval by Endorsing Committee Date | Contract Amount in ETH | Date Contract Award | Date Contract Signature | Mobilization Advance Payment | Substantial Completion | Final Acceptance | Final Cost
[6 empty] | Government Treasury | Internal Revenue | IDA | AID |  |  |  | 1--3wks | 1 - 2 wks | 1 - 8 wks | 1day | 1--4wks | 1 --2 wks |  | 1 --2 wks | 1--3 wks | 2--4wks | As per contract | 24--52wks
State Non UIIDP Maintenece Works
1 | Works
1.1 | Four sub cities cobble Stone Road | m2 | 5847.16 | Arbaminch/Munic/Maint-001/2020 | 500000 |  | 500000 |  |  | LCB | Post | Plan | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-25 | 2020-10-09 | 2020-10-16 |  | 2020-10-30 | 2020-11-13 | 2020-11-20 | 2021-03-20 | 2022-03-20
Revised
Actual
1.2 | Asphalt Median Fence Maintenance | km | 2.5 | Arbaminch/Munic/Maint-002/2020 | 500000 |  | 500000 |  |  | LCB | Post | Plan | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-25 | 2020-10-09 | 2020-10-16 |  | 2020-10-30 | 2020-11-13 | 2020-11-20 | 2021-03-20 | 2022-03-20
Revised
Actual
1.3 | Four sub cities gravel road | km | 8 | Arbaminch/Munic/Maint-003/2020 | 3802502.65 |  | 3802502.65 |  |  | LCB | Post | Plan | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-25 | 2020-10-09 | 2020-10-16 |  | 2020-10-30 | 2020-11-13 | 2020-11-20 | 2021-03-20 | 2022-03-20
Revised
Actual
1.4 | Abbatior maintenance | No | 1 | Arbaminch/Munic/Maint-004/2020 | 500000 |  | 500000 |  |  | LCB | Post | Plan | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-25 | 2020-10-09 | 2020-10-16 |  | 2020-10-30 | 2020-11-13 | 2020-11-20 | 2021-03-20 | 2022-03-20
Revised
Actual
1.5 | Abbatior Fence maintenance | m | 100 | Arbaminch/Munic/Maint-005/2020 | 300000 |  | 300000 |  |  | LCB | Post | Plan | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-25 | 2020-10-09 | 2020-10-16 |  | 2020-10-30 | 2020-11-13 | 2020-11-20 | 2021-03-20 | 2022-03-20
Revised
Actual
1.6 | Engineering machine maintenance | No | 3 | Arbaminch/Munic/Maint-006/2020 | 1237550.55 |  | 1237550.55 |  |  | LCB | Post | Plan | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-25 | 2020-10-09 | 2020-10-16 |  | 2020-10-30 | 2020-11-13 | 2020-11-20 | 2021-03-20 | 2022-03-20
Revised
Actual
1.7 | Four sub cities water supply maintenance | m | 2501 | Arbaminch/Munic/Maint-007/2020 | 3346941.35 |  | 3346941.35 |  |  | DC | Post | Plan | 2019-08-12 | 2019-08-19 | NA | NA | NA | NA |  | NA | NA | NA | 2020-06-19 | 2021-06-19
Revised
Actual
1.8 | Four sub cities masonry maintenance | m | 550 | Arbaminch/Munic/Maint-008/2020 | 4035559.58 |  | 4035559.58 |  |  | LCB | Post | Plan | 2020-08-12 | 2020-08-19 | 2020-08-26 | 2020-09-25 | 2020-10-09 | 2020-10-16 |  | 2020-10-30 | 2020-11-13 | 2020-11-20 | 2021-03-20 | 2022-03-20
Revised
Actual
1.9 | Four sub cities electric line maintenance | m | 420 | Arbaminch/Munic/Maint-009/2020 | 4462589.44 |  | 4462589.44 |  |  | DC | Post | Plan | 2019-08-12 | 2019-08-19 | NA | NA | NA | NA |  | NA | NA | NA | 2020-06-19 | 2021-06-19
Revised
Actual
1.1 | Other Plants and Equipments Maintenance | No | 12 | Arbaminch/Munic/Maint-010/2020 | 1500000 |  | 1500000 |  |  | LCB | Post | Plan | 2019-08-12 | 2019-08-19 | NA | NA | NA | NA |  | NA | NA | NA | 2020-06-19 | 2021-06-19
Revised
Actual
[5 empty] | 20185143.57 | 0 | 20185143.57 |  | 0
Formulas:
Date Contract Award = [Approval by Endorsing Committee Date]+14
Date Contract Signature = [Date Contract Award]+14
Contract Implementation = [Date Contract Signature]+7
Substantial Completion = [Contract Implementation]+120
Final Acceptance = [Substantial Completion]+365

## Consultancy
COUNTRY |  | Federal Democratic Republic of Ethiopia
Responsible Agency |  | Ministry of Urban Development & Construction
REGION |  | SNNPR Regional State
CITY ADMINISTRATION |  | Arbaminch City Administration
PROGRAM |  | URBAN INSTITUTIONAL INFRUCTURE DEVELOPMENT PROGRAM (UIIDP) IDA CR. NO.5435ET
PROCUREMENT CATEGORY/TYPE * |  | CONSULTANCY Annual Procurement plan
BUDGET YEAR |  | ANNUAL PROCUREMENT PLAN- FOR THE YEAR | [7 empty] | 2019/2020(2012E.C)
Exchange rate ** |  | 1USD =……………ETB | [22 empty] | ETB
|  | Basic data | [10 empty] | Preparation of TOR/ Request for Proposals |  | Request for EOI |  | Short List & Request For Proposal |  | Consultant Proposals |  | Proposal Evaluation and Negotiation Technical (T) & Financial (F) and Negotiations (N) |  |  |  |  | Draft Contract |  | Contract Finalization |  |  | Contract Implementation
No. | Procurement Description | Package number | Lot number | Estimated Amount ETB | Source of Finance |  |  |  | Procurement Method | Selection Method | Contract Type | Plan vs. Actual | Prep & Submission by Ex Ag | Approval by Endorsing Committee | On-line Agency website / National Press/ | Lead-time before shortlist | Submission Date | Approval by Endorsing Committee | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | Evaluation Report Approval by Endorsing Committee (T) | Opening Financial Proposals | Preparation Eval Report (Combined) | Negotiations (N) | Submission Date | Approval by Endorsing Committee Evaluation Report (T) & (F) | Contract Amount ETB | Contract Award | Contract Signature | Mobilization/ Advance Payment | Draft Report | Final Report | Final Cost
| Consultancy Service and construction |  |  |  | Government Treasury | Internal Revenue | IDA | AID |  |  |  |  | 3 - 6 wks | 1 wk | 1- 2wks | 2wks | 1- 2wks | 1 wk | 1- 2wks | 1day | 1- 3wks | 1wk | 1- 2wks | 2 wks | 2 wks | 1 - 2 wks | 1 - 2 wks |  | 1 wk | 1 - 3 wks
1 | Design of City Adminstration Building | Arbaminch/Stat/CS-01/2019 |  | 500000 |  | 500000 |  |  | RFP | QCBS | LS | Plan | 2019-10-07 | 2019-10-14 | 2019-10-19 | 2019-11-03 | 2019-10-26 | 2019-10-31 | 2019-11-05 | 2019-11-20 | 2019-11-27 | 2019-12-04 | 2019-12-11 | 2019-12-16 | NA | 2019-12-17 | 2019-12-22 |  | 2019-12-29 | 2020-01-05 | 2020-01-12 | 2020-04-11 | 2020-05-11
Revised
Actual
|  | On behalf of the City Administration | [5 empty] | On behalf of the Regional Team
|  | Name:_________________________________________________ | [5 empty] | Name:_________________________________________________
|  | Signatue:__________________________ |  |  | Date:_______________ |  |  | Signatue:__________________________ |  |  | Date:_______________
Formulas:
Approval by Endorsing Committee = [Prep & Submission by Ex Ag]+7
Approval by Endorsing Committee = [Short List & Request For Proposal]+5
Request for EOI = [Approval by Endorsing Committee]+5
Lead-time before shortlist = [Request for EOI]+15
Short List & Request For Proposal = [Request for EOI]+7
Consultant Proposals = [Approval by Endorsing Committee]+5
Submission/ Opening Date = [Consultant Proposals]+15
Submission Evaluation Report (T) = [Submission/ Opening Date]+7
Preparation Eval Report (Combined) = [Opening Financial Proposals]+5
Draft Contract = [Preparation Eval Report (Combined)]+1
Contract Signature = [Contract Award]+7
Contract Implementation = [Contract Signature]+7
Draft Report = [Contract Implementation]+90
Final Report = [Draft Report]+30

## 17. Staffing
Table 1. Staffing for Delivery and Management of the CIP
S/N | Infrastructure Category | Responsible Department | No. of Staff
|  |  | Required | Available
1 | The Movement Network | Performance capacity building department | 6 | 5
2 | The Water Supply Network | Water supply Office | 25 | 19
3 | Environmental Services | Performance capacity building department | 9 | 4
4 | Social and Economic Services | Performance capacity building department | 3 | 2
|  | Food security and job creation department | 160 | 57
| Total |  | 203 | 87

## 18.JOB CREATION
S/N | Project | Unit | Qty | Temporary Jobs Creation by Age Group
|  |  |  | Males |  | Females |  | Total
|  |  |  | 30 years & under | Over 30 year | 30 years & under | Over 30 year | 30 years & under | Over 30 year
Pillar 6. Integrated Urban Infrastructure
A | Movement Network
UIIDP Funded projects
I | New projects
1 | Roads
1.1 | Cobblestone Road
1.1.1 | ASPHALT TO GETAHUN AYELE & GETAHUN LEMA TO GABALE TSARA | m2 | 2548 | 27 | 15 | 20 | 12 | 47 | 27
1.1.2 | TAKELE TESEMA TO ELIYAS GAGA | m2 | 1470 | 22 | 12 | 18 | 10 | 40 | 22
1.1.3 | DESALEGN DATA TO MEKANEYESUS GUEST HOUSE | m2 | 1470 | 22 | 12 | 18 | 10 | 40 | 22
1.1.4 | ZERIHUN ZUMA TO TESFAYE DURE | m2 | 2310 | 27 | 15 | 20 | 12 | 47 | 27
1.1.5 | FROM CHICHE CHIBIRE TO TADELECH SHITAYE & LISANEWORK TO OLD BRIDGE | m2 | 2310 | 27 | 15 | 20 | 12 | 47 | 27
1.1.6 | FROM AREGAWIYAN TO GULCHA DOKILE & YAPA YAYA TO ZENEBE ZIDA | m2 | 2380 | 27 | 15 | 20 | 12 | 47 | 27
1.1.7 | HAILEMICHAEL HALALA TO BELAYNESH MERGIYA | m2 | 2625 | 28 | 16 | 21 | 13 | 49 | 29
1.1.8 | ASHEBIR ASFA THROUGH ASFAW DAGNIE TO G/MEDIHIN ADINEW | m2 | 1750 | 22 | 12 | 18 | 10 | 40 | 22 |  |  | 0.41962
1.1.9 | ABEBE GEZAHAGN THROUGH MENGISTU MARKA TO PETROS | m2 | 1260 | 22 | 12 | 18 | 10 | 40 | 22 |  |  | 1.4196
1.1.10 | SOLOMON CHODA TO BITANE MENZA | m2 | 1890 | 22 | 12 | 18 | 10 | 40 | 22 |  |  | 1.8392
1.1.11 | DAMENE TO SENODOS WOFCHO BET | m2 | 2240 | 26 | 14 | 20 | 12 | 46 | 26
1.1.12 | MATEYOS LOHA TO KES KETEMA, MENZA TO AWUDE AHMED & CHAIN ACADAMY TO ASNAKECH LENCHA | m2 | 2310 | 27 | 15 | 20 | 12 | 47 | 27
1.1.13 | HUSEN YIMER TO ASKALECH GIZACHEW, LIYU MEAZA TO NATINAEL, TAGESE CHAFO TO MEDIHANIT METASEBIYA & DESALEGN LAFAMO TO MEKONNEN | m2 | 2590 | 27 | 15 | 20 | 12 | 47 | 27
1.1.14 | GETACHEW SEMERE TO ASPHALT | m2 | 2184 | 27 | 14 | 20 | 12 | 47 | 26
1.1.15 | BOMBOLO AGIDEW TO ASPHALT | m2 | 1470 | 22 | 12 | 18 | 10 | 40 | 22
1.1.16 | MOGES W/AMANUEL TO AEMIRO ALTO & MINALU BULGO TO TULO BOYZO | m2 | 1470 | 22 | 12 | 18 | 10 | 40 | 22
1.1.17 | CHALACHEW TAMIRU TO TESFAYE HAILE & BEDILU TO TIRUYE | m2 | 1890 | 22 | 12 | 18 | 10 | 40 | 22 |  |  | #DIV/0!
1.1.18 | WANSO WASHA TO THOMAS WASHE & JINKA BER TO MULUWONGEL | m2 | 2380 | 27 | 15 | 20 | 12 | 47 | 27 |  |  | #DIV/0!
1.1.19 | TSIGEREDA KEBEDE TO MENGISTU WORKU & D/R TESFAYE TO TADELE YILMA | m2 | 2700 | 28 | 16 | 21 | 13 | 49 | 29 |  |  | #DIV/0!
1.1.20 | LABIYAJO THROUGH TSEGAYE BEKELE TO MOLA HABTE | m2 | 2320 | 27 | 15 | 20 | 12 | 47 | 27
1.1.21 | MOLA HABTE THROUGH ASCHENAKI MAMO TO NEW ASPHALT | m2 | 2800 | 28 | 16 | 21 | 13 | 49 | 29
1.1.22 | SHEWAYE MINDAYE THROUGH NEW CULVERT TO WONDWOSEN WUBAYEHU | m2 | 2450 | 27 | 15 | 20 | 12 | 47 | 27
1.1.23 | TESFAYE KOIRA THROUGH ALMAZ ALEMAYEHU TO GUDELA KUSIYA | m2 | 1960 | 22 | 12 | 18 | 10 | 40 | 22
1.1.24 | KASAHUN GEZAHAGN TO MINJA, MINJA TO WONBERA, WONBERA TO DEBEBE LOFA | m2 | 1960 | 22 | 12 | 18 | 10 | 40 | 22
1.1.25 | KASAHUN GEZAHAGN TO MENGISTU MEYA & ETENESH BEKELE TO DEREJE ALEMU | m2 | 1820 | 22 | 12 | 18 | 10 | 40 | 22
1.1.26 | ADDIS ALEMAYEHU WOFCHO BET TO DEBEBE MAMACHA | m2 | 1620 | 22 | 12 | 18 | 10 | 40 | 22
1.1.27 | ABUGIYA SHILE TO YIFTUSIRA MOLA | m2 | 2160 | 22 | 15 | 20 | 12 | 42 | 27
1.1.28 | WADA DERE TO DEBEBE BIRHANE | m2 | 1869 | 22 | 12 | 18 | 10 | 40 | 22
1.1.29 | RAHEL KULINO TO W/RO BIRHANE KASA | m2 | 1520 | 22 | 12 | 18 | 10 | 40 | 22
1.1.30 | EJIGAYEHU DEBREWORK TO MESERET ADANE | m2 | 1760 | 22 | 12 | 18 | 10 | 40 | 22
| Cobblestone Road total |  | 61486 | 732 | 406 | 573 | 333 | 1305 | 739 | 1249 | 739
1.2 | Street Light
1.2.1 | From Konso sefer adebabay to Admasu house and from Fish Corporation to Zone Urban Dev't Office | Km | 2.4 | 3 | 2 | 3 | 2 | 6 | 4
| Street Light total |  | 2.4 | 3 | 2 | 3 | 2 | 6 | 4 | 6 | 4
1.3 | Bridges,Fords & Culvert construction
1.3.1 | HIBRET LELIMAT SCHOOL CULVERT | No | 1 | 25 | 15 | 22 | 18 | 47 | 33
1.3.2 | SINODOS CULVERT | No | 1 | 20 | 12 | 18 | 15 | 38 | 27
1.3.3 | CATHOLIC MISSION CULVERT | No | 1 | 20 | 12 | 18 | 15 | 38 | 27
1.3.4 | GURBA CULVERT | No | 1 | 25 | 15 | 30 | 22 | 55 | 37
1.3.5 | MAMO MEKURIYA BRIDGE/GEBRIEL MESHAGERIYA | No | 1 | 55 | 42 | 49 | 32 | 104 | 74
| Bridges,Fords & Culvert construction total |  | 5 | 145 | 96 | 137 | 102 | 282 | 198 | 221 | 136
| Movement Network (New Projects) Total |  |  | 880 | 504 | 713 | 437 | 1593 | 941
Movement Network (Rolled)
1 | Rolled Cobble stone
1.1 | From Ato Dubale Dunke to S/R Yirgedu, Alemu Ano to Mewale Hitsan Block 4 | m2 | 3745 | 30 | 20 | 25 | 18 | 55 | 38
1.2 | From Endezihnew Kasaye to Wushu Pension | m2 | 70 | 10 | 6 | 8 | 6 | 18 | 12
1.3 | From Eyob Kurka to Gida Gita | m2 | 140 | 15 | 13 | 14 | 12 | 29 | 25
1.4 | From Lukas Woga to Dr. Melkamu Biniyam | m2 | 70 | 10 | 6 | 8 | 6 | 18 | 12
1.5 | From Mesfin Albo to W/ro Tsehay house | m2 | 70 | 10 | 6 | 8 | 6 | 18 | 12
1.6 | From Tefera Bizuneh to Almaz Gergeda | m2 | 70 | 10 | 6 | 8 | 6 | 18 | 12
1.7 | Shaleka Debebe Sisay to New Asphalt | m2 | 35 | 7 | 5 | 6 | 5 | 13 | 10
| Rolled Cobble stone total |  | 4200 | 92 | 62 | 77 | 59 | 169 | 121 | 169 | 121
1.3 | Rolled Bridges,Fords & Culvert construction
1.3.1 | Chamo Campus University Fence | No | 1 | 10 | 6 | 8 | 6 | 18 | 12
1.3.2 | Sebsibe Haile Culvert | No | 1 | 6 | 5 | 6 | 4 | 12 | 9
1.3.3 | Dawit Dage to Ashewa Mado | No | 1 | 55 | 45 | 51 | 35 | 106 | 80
| Rolled Bridges,Fords & Culvert construction total |  | 3 | 71 | 56 | 65 | 45 | 136 | 101 | 105 | 77
1.4 | Rolled Roundabout constrution
1.4.1 | Gamo Round about construction | 1 | 1 | 65 | 55 | 50 | 45 | 115 | 100
| Sub total | 1 | 1 | 65 | 55 | 50 | 45 | 115 | 100 | 115 | 100
| Movement Network (Rolled) Total |  |  | 228 | 173 | 192 | 149 | 420 | 322
| Movement Network Total |  |  | 1108 | 677 | 905 | 586 | 2013 | 1263
B | Economic & Social Services
Economic & Social Services(New Projects)
| Economic & Social Services(New Projects) Total |  | 0
Economic & Social Services(Rolled)
1.4.2 | Abattior car | No | 1 | 3 | 2 | 3 | 2 | 6 | 4
| Economic & Social Services(Rolled)Total |  | 1 | 3 | 2 | 3 | 2 | 6 | 4 | 6 | 4
| Economic & Social Services Total |  | 1 | 3 | 2 | 3 | 2 | 6 | 4
E | Other
Electricity Reticulation
Electric Line Expansion /Transformer /
1.1 | SENODOS SEFER & AT THE BACK OF TEXTILE FACTORY | No | 2 | 10 | 6 | 8 | 6 | 18 | 12
| Electric Line Expansion /Transformer /Total |  | 2 | 10 | 6 | 8 | 6 | 18 | 12 | 18 | 12
WATER SUPPLY
| WATER SUPPLY PROJECT AT THE BACK OF TEXTILE FACTORY | No | 1 | 15 | 13 | 14 | 12 | 29 | 25
| WATER SUPPLY Total |  | 1 | 15 | 13 | 14 | 12 | 29 | 25 | 29 | 25
| Pillar 6. Integrated Urban Infrastructure Total |  |  | 1136 | 698 | 930 | 606 | 2066 | 1304
Pillar 7: Environmental, Green Services & Recreation
C | Environmental Services(New Projects)
1.2 | Drainage construction
1.2.1 | TESFAYE TEFERA TO BEZABIH WADA & AKIRSO KORA TO BONO | m | 412 | 23 | 16 | 17 | 12 | 40 | 28
1.2.2 | BRIDGE TO TESFAYE WORKINEH | m | 280 | 20 | 14 | 14 | 10 | 34 | 24
1.2.3 | GEDA GAZE TO MATEYOS ASHA | m | 134 | 16 | 12 | 13 | 8 | 29 | 20
1.2.4 | GIRMA SANA TO BEKELE TADESE | m | 170 | 17 | 12 | 14 | 9 | 31 | 21
1.2.5 | DAWIT DORKE THROUGH SAMSON TO GEZMO TINKU | m | 310 | 20 | 15 | 17 | 12 | 37 | 27
1.2.6 | BIRKABY THROUGH ABERA MOTA TO ENDALE H/MESKEL | m | 350 | 20 | 15 | 17 | 12 | 37 | 27
1.2.7 | KALEB KANKO TO DIDO ABUTE | m | 130 | 17 | 12 | 13 | 8 | 30 | 20
1.2.8 | YISIHAK MENA TO WONDIYIFRAW | m | 220 | 17 | 12 | 14 | 9 | 31 | 21
1.2.9 | CHAMO CAMPUS ASPHALT TO BEHAILU ABOTA | m | 220 | 17 | 12 | 14 | 9 | 31 | 21
1.2.10 | AZENEH TEKA TO GORGE & BIZUNEH BUSA TO BISAF LEMA | m | 480 | 25 | 16 | 19 | 12 | 44 | 28
1.2.11 | KULIFO GREENERY SITE DITCH | M | 305 | 21 | 15 | 17 | 12 | 38 | 27
1.2.12 | S/R YIRGEDU MENGESHA TO SIYERE MEKURIYA | m | 300 | 21 | 15 | 17 | 12 | 38 | 27
| Drainage total |  | 3311 | 234 | 166 | 186 | 125 | 420 | 291 | 292 | 248
1.6 | Greenery development
1.6.1 | Public Park at the side of Kulufo river phase-IV | m2 | 15000 | 25 | 13 | 19 | 12 | 44 | 25
| Greenery development total |  | 15000 | 25 | 13 | 19 | 12 | 44 | 25 | 29 | 25
5 | Municipal Non UIIDP Works (New)
Municipal Non UIIDP Works (New) Total
| Environmental Services(New Projects) Total |  |  | 259 | 179 | 205 | 137 | 464 | 316
Environmental Services(Rolled)
5 | Rolled Greenery Development
5.2 | Public Park at the side of Kulufo river phase-3 | m2 | 18000 | 15 | 16 | 14 | 12 | 29 | 28
5.3 | Omo Hall Compound Greenary Development phase-2 | m2 | 4000 | 12 | 14 | 10 | 8 | 22 | 22
| Rolled Greenery Development Total |  | 22000 | 27 | 30 | 24 | 20 | 51 | 50 | 51 | 44
6 | Rolled Greenery protection fence
6.1 | From Referral Hospital to Lemlem Square phase-2 | km | 0.1 | 7 | 5 | 6 | 5 | 13 | 10
| Rolled Greenery protection fence Total |  | 0.1 | 7 | 5 | 6 | 5 | 13 | 10 | 13 | 10
7 | Rolled Asphalt median and greenery
7.1 | From Haile Resort to Hawariyat Church | km | 0.1 | 12 | 11 | 10 | 8 | 22 | 19
| Rolled Asphalt median and greenery Total |  | 0.1 | 12 | 11 | 10 | 8 | 22 | 19 | 22 | 19
6 | Rolled Drainage Projects
6.1 | From Alemu Ano to Pawlos Genta | m | 90 | 7 | 5 | 6 | 5 | 13 | 10
| Rolled Drainage Projects Total |  | 90 | 7 | 5 | 6 | 5 | 13 | 10 | 13 | 10
2 | Solid Waste (Rolled)
1.4.1 | Skip loader | No | 1 | 3 | 2 | 3 | 2 | 6 | 4
| Solid Waste (Rolled) total |  | 1 | 3 | 2 | 3 | 2 | 6 | 4 | 6 | 4
| Environmental Services (Rolled) Total |  |  | 56 | 53 | 49 | 40 | 105 | 93
| Environmental Services Total |  |  | 315 | 232 | 254 | 177 | 569 | 409
Others
| Pillar 7: Environmental, Green Services & Recreation Total |  |  | 315 | 232 | 254 | 177 | 569 | 409
Pillar 8: Resilient, Inclusive and Safer Cities
Environmental Services
1.3 | Retaining wall construction(New)
1.3.1 | Retaining wall at the side of Kulufo river phase-III | m | 250 | 65 | 48 | 61 | 32 | 126 | 80
| Retaining wall total |  | 250 | 65 | 48 | 61 | 32 | 126 | 80 | 75 | 56
2 | Retaining wall(Rolled)
2.1 | Retaining wall at the side of Kulufo river phase-II | m3 | 250 | 60 | 48 | 62 | 31 | 122 | 79
2.2 | Konso Market to Stadium Retaining wall | m3 | 80 | 22 | 16 | 18 | 12 | 40 | 28
| Rolled Retaining wall total |  | 330 | 82 | 64 | 80 | 43 | 162 | 107 | 104 | 81
| Retaining wall total |  | 580 | 147 | 112 | 141 | 75 | 288 | 187
| Environmental Services Total |  |  | 147 | 112 | 141 | 75 | 288 | 187
| Pillar 8: Resilient, Inclusive and Safer Cities total |  |  | 147 | 112 | 141 | 75 | 288 | 187
Municipal Administration Buildings and Other Projects which cannot be put in Pillars
Municipal (New projects)
A | Buildings(New)
Buildings(Rolled)
1 | Low cot house | No | 16 | 55 | 43 | 52 | 39 | 107 | 82
2 | Cadaster office building | No | 1 | 60 | 48 | 64 | 41 | 124 | 89
3 | Animal Health Center | No | 1 | 35 | 26 | 28 | 15 | 63 | 41
3 | Rolled One shop serveice shed building | No | 1 | 7 | 5 | 6 | 5 | 13 | 10
| Buildings (Rolled) Total | No | 19 | 157 | 122 | 150 | 100 | 307 | 222 | 162 | 118
| Buildings Total | No | 19 | 157 | 122 | 150 | 100 | 307 | 222
Municipal (Rolled projects)
Consultancy Services for designs and contract management/supervision
1
| Total CIP Job Creation |  |  | 1755 | 1164 | 1475 | 958 | 3230 | 2122 | 2685 | 1833
[5 empty] | 2919 |  | 2433 |  |  |  | 4518
|  |  |  | 4394 |  | 6516 |  | 5352 | -1 | 5352
10704
| 2755507.75 |  |  | 882100.33 |  | 10704
| 69610194.25 |  |  | 3117899.33 |  | 4188 |  |  | 612642.26 |  | 3537
| 72365702 |  |  | 3999999.66 |  | 6516 |  |  | 614764.26 |  | 1814
5351
132365702
3000000
3000000
30000000
|  |  |  | 72365702 |  | 1.8291 | 0.41456
|  |  |  | 0.41456 |  |  | 0.82912
1.8291

## 19. capacity Building Plan
Table 19. UIIDP Capacity Building Plan of the City for EFY 2013
No | ECSPG Pillar & Capacity Building Activities /investments | UIIDP POM Thematic Area | Gaps identified | Capacity Building Modality[1] | Performance Indicators[2] | Target[3] | Lead Person Responsible | Year (E.C) | Start date | End date | Resources required (budget) in Birr | Packaging: Goods, Works, Services, Training Adm.
Pillar 1: Urban Transformational Leadership
1 | Induction training will be conducted for newly assigned leaders and focal persons on overall view of UIIDP | P and B | Lack of awareness on the new programme and continios integration | Classroom training | No. of trainees | 45 | P and B | 2013 | 2020-10-11 | 2020-04-08 | 100000 | Training
2 | Provide a training to all leaders , focal persons and communty members on project site selection and CIP preparation , Revision and aproval | P and B | Lack of awareness on the new programme and continios integration | Classroom training | No. of trainees | 45 | P and B | 2013 | 2020-01-09 | 2020-07-07 | 98000 | Training
3 | Provide training on CIP for those implimentors requiring special support. | P and B | Lack of awareness on the new programme | Classroom training | No. of trainees | 45 | P and B | 2013 | 2020-01-09 | 2020-07-07 | 18000 | Training
4 | Experience sharing program will be conducted for City council representatives, steering committee and UIIDP programe focal persons to scaling up best practices of Programme planning management, implementation and evaluation systems from Debrezeit City | P&B and M&E | Lack of integration, lack of commitment and lack of awareness | Classroom training | No. of trainees | 35 | P&B and M&E | 2013 | 2020-10-11 | 2020-07-07 | 431000 | Training
5 | Refreshment training preparing by FMT and RMT for city cordinator, CIP focal, plan & budget, CB, REP, PE, AMP, FM, REP, PM, LM, LED, GD, ESMS, AT, PC, CH, M&E Specialists or all focal persons | P&B and M&E | Less efficiency in performance | Learning exchange | No. of trainees | 35 | P&B and M&E | 2013 | 2020-10-11 | 2020-07-07 | 150000 | Training
| Subtotal | [9 empty] | 797000
Pillar 2: Micro & Small Enterprise and Urban Productivity (Economy)
6 | Awareness creation training will be provided for leaders, enterprises and industry development sector experts and community on job creation, guidelines of selection of jobless youths and organization, preparation of business plan and audit system of MSEs | LED&JC | Problem of attitude because of lack of training | Classroom training | No. of trainees | 100 | LED&JC | 2013 | 2020-10-11 | 2020-07-07 | 70000 | Training
7 | Computation will be conducted among MSEs on new business idea innovation in the city | LED&JC | Problem of attitude because of lack of training | Classroom training | No. of trainees | 30 | LED&JC | 2013 | 2020-01-09 | 2020-07-07 | 50000 | Training
8 | public pribat dialoge work shop | LED&JC | less encareging of bisness plan idea | Classroom training | No. of trainees | 10 | LED&JC | 2013 | 2020-10-11 | 2020-07-07 | 65000 | Training
| Subtotal | [9 empty] | 185000
Pillar 3: Urban Developmental Good Governance & Services
9 | Awareness creation Training will be provided for municipality, administration and finance anti-corruption and compliance handling units, steering committee, focal persons, leaders and community representatives on corruption attitudes, practices, challenges and transparency and accountability of project implementation. | A & T and UP | Lack of integration, lack of commitment and lack of awareness | Classroom training b) On-job trainings | No. of trainees | 80 | A & T and UP | 2013 | 2020-10-11 | 2020-04-08 | 145000 | Training
10 | Provision of Training to strength kebele leaders and community development committee on good governance issues specially land related cases | A & T and UP | Lack of awareness and ownership | Classroom training | No. of trainees | 500 | A & T and UP | 2013 | 2020-10-11 | 2020-04-08 | 80000 | Training
| Subtotal | [9 empty] | 225000
Pillar 4: Urban Planning, Land Development and Management
11 | Giving Training on, revision of ten years city plan, asset inventory in GIS for land management experts and community members. | LM and UP | Shortage of sufficient land inventory because of commitment problem | Classroom training | No. of trainees | 45 | LM and UP | 2013 | 2020-10-11 | 2020-04-08 | 120000 | Training
12 | The awareness creation training will be given on land inventory for cadaster experts, leaders, council members and community | UP | Shortage of integration with others | Classroom training | No. of trainees | 45 | UP | 2013 | 2020-10-11 | 2020-04-08 | 100000 | Training
| Subtotal | [9 empty] | 220000
Pillar 5: Integrated Urban Infrastructure
13 | Awareness creation training will be prepared for focal persons, steering committee ,community representatives on guideline for project site selection, distribution, administration and implementation strategy | LED&UP | Lack of integration with others, turnover of professionals, awareness problem | Classroom training | No. of trainees | 65 | LED&UP | 2013 | 2020-01-09 | 2020-07-07 | 100000 | Training
14 | Providing Training on preparing of construction cost estimation and bid for construction office engineers, professionals and leaders. | LED&UP | Lack of integration with others, turnover of professionals, awareness problem | Classroom training | No. of trainees | 20 | LED&UP | 2013 | 2020-01-09 | 2020-07-07 | 60000 | Training
| Subtotal | [9 empty] | 160000
Pillar 6: Environmental, Green Services & Recreation
15 | providing Training on how to make safe, clean, green and waste management for community/citizen through building sense of ownership | ESMS | Problem of commitment, lack of integration | Classroom training | No. of trainees | 15 | ESMS | 2013 | 2020-10-11 | 2020-04-08 | 75000 | Training
| Subtotal | [9 empty] | 75000
Pillar 7: Resilient, Inclusive and Safer Cities
16 | Providing Training on risk map preparation, risk gap assessment and risk management for resilient department professionals, leaders and community members to make safe city | UR & DRM | Problem of commitment, lack of integration | Classroom training | No. of trainees | 15 | UR & DRM | 2013 | 2020-10-11 | 2020-04-08 | 60000 | Training
| Subtotal | [9 empty] | 60000
Pillar 8: Urban Finance
17 | Providing training for Finance office heads, Procurement committee, auditors and stakeholders on finance transparency and accountability, procurement guidelines and project agreement implementation in order to implement the proposed tasks based required quality and types at right cost and time to improve the project effectiveness and efficiency. | FM & A and CB | Lack of integration with others, turnover of professionals, awareness problem | Classroom training | No. of trainees | 110 | FM & A and CB | 2013 | 2020-10-11 | 2020-04-08 | 80000 | Training
18 | Refreshment training will be prepared for all stakeholders on IBEX, other basic computer software applications. | FM & A and CB | Lack of integration with others, turnover of professionals, awareness problem | Classroom training | No. of trainees | 110 | FM & A and CB | 2013 | 2020-10-11 | 2020-04-08 | 60000 | Training
19 | Training will be given for Revenue branch employees, municipality and trade and marketing development experts on tax assessment, tax administration and revenue collection system to maximize revenue bases in order to improve municipality Revenue. | REP | Weak performance on revenue | Classroom training | No. of trainees | 150 | REP | 2013 | 2020-10-11 | 2020-04-08 | 140000 | Training
20 | Refreshing training will be prepared for newly recruited employees on SIGTAS and basic computer skills to ensure quality data for tax payers. | REP | Lack of software knowledge and skill | Learning exchange | No. of trainees | 40 | REP | 2013 | 2020-10-11 | 2020-04-08 | 60000 | Training
| Subtotal | [9 empty] | 340000
Pillar 9- Institutionalizing Gender issue
21 | Provide training for gender focal persons and other concerned experts on how to mainstreaming gender into all development plan in the city | GED | decision making skill gap | Classroom training b) On-job trainings | No. of trainees | 50 | GED | 2013 | 2020-10-11 | 2020-07-07 | 63000 | Training
22 | Provide training for gender focal persons and other concerned experts on how to mainstreaming gender into all development plan in the city | GED | gender development plan preparetion gap | Classroom training b) On-job trainings | No. of trainees | 100 | GED | 2013 | 2020-01-09 | 2020-07-07 | 50000 | Training
23 | Provide training for UIIDP SME heads, civil contractors and government officials as to facilitate equal payment for the same jobs regardless of gender difference. | GED | Lack of awareness | Learning exchange | No. of trainees | 50 | GED | 2013 | 2020-01-09 | 2020-07-07 | 50000 | Training
| sub total | [9 empty] | 163000
| Training total | [9 empty] | 2225000 | Training
| Supporting office equipments for the sector |  | lack of office equipments |  | No. of equipments |  | PM | 2012 | 2020-10-11 | 2020-04-08 | 2815160.02 | Goods
| Total Capacity Building Plan for EFY 2013 | [9 empty] | 5040160.02

## 20. AAP Capacity Building
No | ECSPG Pillar & Capacity Building Activities /investments | UIIDP POM Thematic Area | Gaps identified | Performance indicators | Annual Target | Lead Person Responsible | Implementation period |  |  |  | Executors | Packaging (goods, works, services, trainings | Financial requirement in (Birr)
[7 empty] | Q1 | Q2 | Q3 | Q4
Pillar 1: Urban Transformational Leadership
1 | Induction training will be conducted for newly assigned leaders and focal persons on overall view of UIIDP | P and B | Lack of strategic leadership | No. of trainees | 65 | P and B |  | 50000 | 50000 |  | Municipality | Training | 100000
2 | Provide a training to all leaders , focal persons and communty members on project site selection and CIP preparation , Revision and aproval | P and B | Lack of awareness on the new programme and contineous integration | No. of trainees | 45 | P and B |  | 0 | 78000 | 20000 | Municipality | Training | 98000
3 | Provide on the on CIP for those implimentors requiring special support. | P and B | Lack of awareness on the new programme | No. of trainees | 45 | P and B |  |  | 8000 | 10000 | Municipality and finance | Training | 18000
4 | Experience sharing program will be conducted for City council representatives, steering committee and UIIDP programe focal persons to scaling up best practices of Programme planning management, implementation and evaluation systems from Debrezeit City | P&B and M&E | Lack experience, exchange knowledge | No. of trainees | 35 | P&B and M&E |  | 200000 | 200000 | 31000 | Municipality and finance | Training | 431000
5 | Refreshment training preparing by FMT and RMT for city cordinator, CIP focal, plan & budget, CB, REP, PE, AMP, FM, REP, PM, LM, LED, GD, ESMS, AT, PC, CH, M&E Specialists or all focal persons | CB & FM | Less efficiency in performance | No. of trainees | 60 | CB & FM |  | 100000 | 50000 | 0 | Municipality | Training | 150000
| Subtotal |  |  |  | 250 |  |  | 350000 | 386000 | 61000 |  |  | 797000
Pillar 2: Micro & Small Enterprise and Urban Productivity (Economy)
6 | Awareness creation training will be provided for leaders, enterprises and industry development sector experts and community on job creation, guidelines of selection of jobless youths and organization, preparation of business plan and audit system of MSEs | LED&JC | Problem of attitude because of lack of training | No. of trainees | 100 | LED&JC |  | 10000 | 30000 | 30000 | LED&JC | Training | 70000
7 | Computation will be conducted among MSEs on new business idea innovation in the city | LED&JC | less encareging of bisness plan idea | No. of trainees | 10 | LED&JC |  |  | 20000 | 30000 | LED&JC | Training | 50000
8 | public pribat dialoge work shop | LED&JC | less encareging of bisness plan idea | No. of trainees | 140 | LED&JC |  | 10000 | 25000 | 30000 | LED&JC | Training | 65000
| Subtotal | [6 empty] | 20000 | 75000 | 90000 |  |  | 185000
Pillar 3: Urban Developmental Good Governance & Services
9 | Awareness creation Training will be provided for municipality, administration and finance anti-corruption and compliance handling units, steering committee, focal persons, leaders and community representatives on corruption attitudes, practices, challenges and transparency and accountability of project implementation. | A & T and UP | Community conflict, lack of commitment on the program implantation | No. of trainees | 80 | A & T and UP |  | 85000 | 60000 | 0 | Municipality | Training | 145000
10 | Provision of Training to strength kebele leaders and community development committee on good governance issues specially land related cases | A & T and UP | Community conflict, lack of commitment on the program implantation | No. of trainees | 500 | A & T and UP |  | 40000 | 40000 | 0 | Municipality | Training | 80000
| Subtotal | [6 empty] | 125000 | 100000 | 0 |  |  | 225000
Pillar 4: Urban Planning, Land Development and Management
11 | Giving Training on, revision of ten years city plan, asset inventory in GIS for land management experts and community members. | CB & FM | Lack of knowledge, commitment | No. of trainees | 45 | LM and UP |  | 60000 | 60000 | 0 | Municipality | Training | 120000
12 | The awareness creation training will be given on land inventory for cadaster experts, leaders, council members and community | CB&FM | Weak focus/attention, | No. of trainees | 45 | UP |  | 50000 | 50000 | 0 | Municipality | Training | 100000
| Subtotal | [5 empty] | 0 | 110000 | 110000 | 0 |  |  | 220000
Pillar 5: Integrated Urban Infrastructure
13 | Awareness creation training will be prepared for focal persons, steering committee ,community representatives on guideline for project site selection, distribution, administration and implementation strategy | LED&UP | Lack of knowledge, commitment | No. of trainees | 65 | LED&UP |  |  | 50000 | 50000 | Municipality | Training | 100000
14 | Providing Training on preparing of construction cost estimation and bid for construction office engineers, professionals and leaders. | LED&UP | Weak focus/attention, | [5 empty] | 30000 | 30000 | Municipality | Training | 60000
| Subtotal | [7 empty] | 80000 | 80000 |  |  | 160000 | Municipality | Training
Pillar 6: Environmental, Green Services & Recreation
15 | providing Training on how to make safe, clean, green and waste management for community/citizen through building sense of ownership | ESMS | Poor attention on environment protection | No. of trainees | 15 | ESMS |  | 40000 | 35000 | 0 | Municipality | Training | 75000
| Subtotal | [5 empty] | 0 | 40000 | 35000 | 0 |  |  | 75000
Pillar 7: Resilient, Inclusive and Safer Cities
16 | Providing Training on risk map preparation, risk gap assessment and risk management for resilient department professionals, leaders and community members to make safe city | UR & DRM | lack of knowledge, weak commitment | No. of trainees | 15 | UR & DRM |  | 30000 | 30000 | 0 | Municipality | Training | 60000
| Subtotal | [5 empty] | 0 | 30000 | 30000 | 0 |  |  | 60000
Pillar 8: Urban Finance
17 | Providing training for Finance office heads, Procurement committee, auditors and stakeholders on finance transparency and accountability, procurement guidelines and project agreement implementation in order to implement the proposed tasks based required quality and types at right cost and time to improve the project effectiveness and efficiency. | FM & A and CB | Lack of awareness and attention | No. of trainees | 110 | FM & A and CB |  | 40000 | 40000 | 0 | finance | Training | 80000
18 | Refreshment training will be prepared for all stakeholders on IBEX, other basic computer software applications. | FM & A and CB | Weak performance | No. of trainees | 110 | FM & A and CB |  | 30000 | 30000 | 0 | finance | Training | 60000
19 | Training will be given for Revenue branch employees, municipality and trade and marketing development experts on tax assessment, tax administration and revenue collection system to maximize revenue bases in order to improve municipality Revenue. | REP | Weak performance on revenue | No. of trainees | 150 | REP |  | 50000 | 50000 | 40000 | Revenue | Training | 140000
20 | Refreshing training will be prepared for newly recruited employees on SIGTAS and basic computer skills to ensure quality data for tax payers. | REP | Lack of software knowledge and skill | No. of trainees | 40 | REP |  | 30000 | 30000 |  | Revenue | Training | 60000
| Subtotal | [5 empty] | 0 | 150000 | 150000 | 40000 |  |  | 340000
Pillar 9- Institutionalizing Gender issue
21 | Provide training for gender focal persons and other concerned experts on how to mainstreaming gender into all development plan in the city | GED | Low Participation of women in decision | No. of trainees | 100 | GED |  | 10000 | 22000 | 31000 | Gender office | Training | 63000
22 | Provide training for gender focal persons and other concerned experts on how to mainstreaming gender into all development plan in the city | GED | Knowledge and skill gap on planning | No. of trainees | 50 | GED |  |  | 30000 | 20000 | Gender office | Training | 50000
23 | Provide training for UIIDP SME heads, civil contractors and government officials as to facilitate equal payment for the same jobs regardless of gender difference. | GED | Lack of awareness | No. of trainees | 50 | GED |  |  | 30000 | 20000 | Gender office | Training | 50000
| sub total | [5 empty] | 0 | 10000 | 82000 | 71000 |  |  | 163000
| Training total | [5 empty] | 0 | 835000 | 1048000 | 342000 | 0 | 0 | 2225000
| Supporting office equipments for the sector |  | lack of office equipments | No. of equipments |  | PM | 0 | 2815160.02 | 0 | 0 | finance | goods | 2815160.02 | 2225000
| Total Capacity Building Plan for EFY 2011 | [5 empty] | 0 | 3650160.02 | 1048000 | 342000 |  |  | 5040160.02 | 0
2225000
5040160.02
0

## Sheet4
Table 7: Goods & Equipment Plan for EFY 2012
No | Description of Goods & equipment | Units | Qty | Unit cost | Lead person | Target group | Total Budget | Implementation Period
[8 empty] | Qtr I | Qtr II | Qtr III | Qtr IV
Stationery, office supplies & cleaning materials
1 | Motor bike | No | 9 | 100000 | Procurement Focal person | Municipality | 900000 |  | P |  |  | 100000
2 | Photo copy machine | No | 5 | 30000 | Procurement Focal person | Municipality Office and Finance Office | 150000 |  | P |  |  | 30000
3 | Desk top computer | No | 19 | 15000 | Procurement Focal person | Municipality and Job Creation office | 285000 |  | P |  |  | 15000
4 | Black printer | No | 19 | 15000 | Procurement Focal person | Municipality, Finance and Job Creation office | 285000 |  | P |  |  | 15000
5 | Lap top computer core i 7 | No | 19 | 30000 | Procurement Focal person | Municipality, Finance and Job Creation office | 570000 |  | P |  |  | 30000
6 | Video camera | No | 1 | 300162.02 | Procurement Focal person | Municipality | 300162.02 |  | P |  |  | 300162.02
| Shelf | No | 20 | 7000 | Procurement Focal person | Municipality, Finance office, Gender office, revenue office and Job Creation office | 140000 |  | P |  |  | 7000
8 | Table desk | No | 21 | 4000 | Procurement Focal person | Municipality, Finance office, Gender office, revenue office and Job Creation office | 84000 |  | P |  |  | 4000
9 | Managerial chair | No | 20 | 5000 | Procurement Focal person | Municipality, Finance office, Gender office, revenue office and Job Creation office | 100000 |  | P |  |  | 5000
10 | Single chair | No | 36 | 2000 | Procurement Focal person | Municipality, Finance office, Gender office, revenue office and Job Creation office | 72000 |  | P
| Total | [5 empty] | 2886162.02 |  |  |  |  | #DIV/0!
2886162.02
0